## Plan
Sr. | Work Area | Task | Responsible Team | Start Date | End Date | Status | Notes
1 | Enabling Accesses | Establishing connection between CSAA and Amazon cloud | CSAA |  |  | In progress
2 |  | Setting up CSAA VPN on Deloitte laptops to connect to Amazon cloud | Deloitte |  |  | Not started
3 |  | Validate remote login on all equipment(with root/admin/qauser access) | Deloitte |  |  | Not started
4 |  | User Management(for login into tools like Jenkins) | EIS |  |  | Not started
5 |  | Validate connectivity to live services(like DCS endpoint etc.) for Integration. | Deloitte |  |  | Not started
6 | Configuration Audit | Compare Hardware-Software version between Exigen and Amazon cloud | Deloitte |  |  | Failed | Observation: WAS Servers have 16 gb RAM on AWS v/s 20 Gb RAM on Deloitte Cloud, disk space on AWS servers is 40Gb less on app servers and 80Gb less on DB servers.
7 | CM activities | Creating PAS Build(deployable WAR file) | Deloitte |  |  | Completed
8 |  | Deploying PAS build using automation | Deloitte |  |  | Completed
9 |  | Deploying Operational Report | Deloitte |  |  | Completed
10 |  | Export of DB dump from an instance | Deloitte |  |  | Completed
11 |  | Cloning of dev2aaa3hub500.eqxdev.exigengroup.com hosting SmartRCA, stack trace and other utilities | EIS |  |  | In progress
12 |  | Validate installation of Zabbix agent on all equipment(Zabbix monitor equiment for conditions like running low on memory) | Deloitte |  |  | Failed | AWS has CloudWatch which is similar to Zabbix, we are working with Exigen to procure details reagrding access/configuration of CloudWatch.
13 |  | Validate utilities - WAS Monitor, Build History page | Deloitte |  |  | Completed
14 |  | Restarting application server in debug mode | Deloitte |  |  | Completed
15 |  | Validate functioning of time-setter utility, especially for clustered instance | Deloitte |  |  | Completed
16 |  | Validating generation of logs for PAS' app, admin, stub, rating applications and changing log level(DEBUG, INFO etc) | Deloitte |  |  | Not started | Requires root access. We are working with Exigen to sort out access issues
17 |  | Hotfixing stub file and validate it's changes on Application UI | Deloitte |  |  | Not started | Requires root access. We are working with Exigen to sort out access issues
18 | Automated Test | Adding instance's config properties file in core velocity framework | EIS |  |  | Completed
19 |  | Confirm readiness of Jenkins(Migration of historic execution data from EIS jenkins etc.) | Deloitte |  |  | Failed | AWS jenkins02 should be a replica of Dev02 (EIS) jenkins. The Historic data of test execution is not migrated to AWS jenkins.
20 |  | Based on the timezone set on Amazon cloud, assess it's impact to nightly regression suite and execution cycle. | Deloitte |  |  | Failed | Exigen has synchronized timezones on all App servers/build servers and test executors(verified)- UTC/GMT + 11 hours. We unable to verify timezones on build servers due to access issue
21 |  | Compare execution time of automated nightly test(avg. of 3) on Amazon cloud vs EIS cloud | Deloitte |  |  | In progress
22 |  | Validate browser version installed on executors(used for automated test) especially for Browser compatibility testing | Deloitte |  |  | Not started
23 |  | Execute automated nightly regression suite on Amazon cloud, compare results with EIS cloud and analyze delta failures | Deloitte |  |  | In progress
24 |  | Perform Sonar testing on Amazon cloud | Deloitte |  |  | Not started
25 |  | Confirm readiness of various utilities used for status reporting | Deloitte |  |  | Not started
26 |  | Execute automated test script from local workspace | Deloitte |  |  | Not started
27 |  | Validate functioning of all PAS admin batch jobs used by regression test suite | Deloitte |  |  | Not started
28 |  | Validate Integration,HVT,CFT,docTest, manual executions | Deloitte |  |  | Not started

## Execution Detail
Sr. | Work Area | Task | Run Time: AWS | Run Time: EIS Cloud | Failures - First Run: AWS | Failures - First Run: EIS Cloud | Notes
Single time point (functional) tests
● Run 1
● Run 2
● Run 3
Calendar (parallel time sensitive) tests
● Run 1
● Run 2
● Run 3
Time point (sequential time sensitive) tests
● Run 1
● Run 2
● Run 3
Life Cycle (complex parallel time sensitive) tests
● Run 1
● Run 2
● Run 3
Browser tests
● Run 1
● Run 2
● Run 3
EIS regression tests
● Run 1
● Run 2
● Run 3

## Assumptions
Assumptions
Network access | DeloitteNet traffic to Amazon cloud will be routed through CSAA VPN
Sign-off pre-conditions | All activities identified as part of AWS transition plan will be performed on PAS09 Golden build #80013
AWS set-up | All equipment/configuration are expected to the same as its on EIS cloud