## Sheet1
Labels | Scenario Name | Blocked | Blocked Reason | AC's blocked | HPQC status | Anusha's comments
CA_CP | CA-CP-109 | Defect | 35017 | 6 | Triage | PAS6 Sprints
CA_CP | CA-CP-110 | Defect | 34656 | 13 | Closed/Additional defect 34918 | Unplanned
CA_CP | CA-CP-112 | Defect | 35431 | 4 | Triage | 2015-10-19
CA_CP | CA-CP-104 | Defect | 35291 | 0 | Triage | Clarification
CA_CP | CA-CP-119 | Defect | 34870 | 2 | Closed PAS7 | 2015-09-29
CA_CP | CA-CP-117 | Workflow Not Developed | CCI/CPI Validation | 9
CA_CP | CA-CP-123 | Potential Defect | Clarification Raised/Claridication Resolved Defect Needs to be raised | 1 |  | Chittranjan to close this today
CA_CP | CA-CP-103 | Out of scope | Defect for task creation/ Design Change Require/move to BCT | 9
CA_CP | CA-CP-106 | Not Blocked |  | 6 |  | Already assigned to Pavitra
CA_CP | CA-CP-107 | Manual | AC needs to be validated manually | 2 |  | Partial-Non Integration
CA_CP | CA-CP-111 | Not Blocked |  | 3 |  | this is marked blocked due to pending clarification from SME
CA_CP | CA-CP-116 | Potential Defect |  | 1 |  | 35488 has been logged
CA_CP | CA-CP-118 | Not Blocked |  | 1 |  | this is marked blocked due to pending clarification from SME
CA_CP | CA-CP-108 | Not Blocked |  | 4 |  | Ready for Review,4 Acs are CCI related which cannot be done.
pas05_pilot | F-P-Agent-CA-1485 | Manual |  | 4 |  | CMNG- Integration
pas05_pilot | F-P-Agent-1480 | Manual |  | 3 |  | CMNG- Integration
pas05_pilot | F-H-DocumentGeneration-CA-1495 | Manual |  | 2 |  | Manual-Non Integration
pas05_pilot | C-H-DocumentGeneration-CA-1494 | Manual |  | 3 |  | Manual-Non Integration
pas05_pilot | T-C-PolicyInfo-CA-911 | Manual |  | 5 |  | CEA
pas05_pilot | F-H-Premium-CA-1519 | Manual |  | 3 |  | CEA
pas05_pilot | C-H-Coverage-CA-1609 | Workflow Not Developed | CCI/CPI Validation | 1
PAS5_NBP | NBP78 | Manual |  | 5 |  | Manual-Non Integration
PAS5_NBP | NBP75 | Defect | 33692 | 8 | Closed PAS7 | 2015-10-05
PAS5_NBP | NBP16 | Defect | 33396 | 3 | Triage | In Process
PAS5_NBP | NBP51 | Defect | 30190 | 6 | Triage | Review
defect_automation | B-F-Auto-SS-Reports-CCL-45 | Out of scope | Test case covered in Exigen | 1
defect_automation | B-T-Auto-SS-AutomatedRenewal-AZ-16 | Out of scope | Invalid defect | 1
pas6_nbp | NBP142 | Manual |  | 2 |  | Manual-Non Integration
pas6_nbp | NBP138 | Manual |  | 1 |  | CEA
pas6_nbp | NBP130 | Manual |  | 8 |  | CEA
pas6_nbp | NBP131 | Manual |  | 4 |  | Integration
pas6_nbp | NBP105 | Manual |  | 5 |  | CEA
pas6_nbp | NBP110 | Not Blocked |  | 2 |  | Assigned to Bindu
pas6_nbp | NBP154 | Manual | Cannot be automated | 1 |  | Functional design issue
CP | CL-CP-102 | defect | 35429 | 1 | Triage | Unplanned
CP | CL-CP-103 | Out of scope | Defect for task creation/ Design Change Require/move to BCT | 9
CP | CL-CP-104-DE | Defect | 35048 | 1 | Rejected
CP | Cl-CP-107 | Defect | 34754 | 3 | Rejected/Additional defect 35462 | Under review
CP | CL-CP-109 | Workflow Not Developed | CCI/CPI Validation | 6
CP | CL-CP-109 | Defect | 35017 | 1 | Triage | PAS6 Sprints
CP | CL-CP-109-DE | Defect | 35017 | 1 | Triage | PAS6 Sprints
CP | CL-CP-110 | Defect | 34656 | 8 | Closed/Additional defect 34918 | Unplanned
CP | CL-CP-110-DE | Not Blocked |  | 1 |  | This cannot be assigned since CL-CP-110 is blocked due to defect

## Defects
Labels | Scenario Name | No. of Test cases | Developer | Defect# | HPQC status | Comments
PAS2,3,4 | C-HO-HO3-CA-322 | 6 | Sowjanya | 30814 | On Hold
PAS2,3,4 | C-HO-HO4-CL-312 | 3 | Monica | 35280 | Closed | Available in build #70398
PAS2,3,4 | C-AU-SS-OR-348 | 2 | Monica |  |  | Manual team to raise a defect
PAS5_NBP | NBP51 | 6 | Sheela | 30190 | Closed | Available in build #70685
CA_CP | CA-CP-103 | 8 | sbahl | 34982 | Rejected | PAS6.1
CA_CP | CA-CP-109 | 1 | kbindusree | 35017 | Triage | Unplanned
CA_CP | CA-CP-113 | 1 | kbindusree | 35166 | Rejected | PAS6.1
CA_CP | CA-CP-119 | 2 | Zoheb Ahmed Banikar | 34870 | Closed | PAS7
CA_CP | CA-CP-123 | 1 | chitranjan | 35521 | Rejected-Misunderstood requirements | PAS6.1
CP | CL-CP-109-DE | 1 | achbhatia | 35017 | Triage | Unplanned
CP | CL-CP-109 | 1 | achbhatia | 35017 | Triage | Unplanned
CP | CL-CP-103 | 9 | mtare | 34982 | Rejected-not reproducible | PAS6.1
CP | CL-CP-102 | 1 | mapendyala | 35429 |  | Available in build #71397
Labels | Scenario Name | No. of Test cases | Developer | Defect# | HPQC status | Comments | Assigned to
PAS2,3,4 | C-HO-HO4-CL-312 | 3 | Monica | 35280 | Closed | Available in build #70398 | Monica
PAS5_NBP | NBP51 | 6 | Sheela | 30190 | Closed | Available in build #70685 | Pavitra
CA_CP | CA-CP-123 | 1 | chitranjan | 35521 | Rejected-Misunderstood requirements | PAS6.1 | chitranjan
CP | CL-CP-102 | 1 | mapendyala | 35429 |  | Available in build #71397 | Madhuri
CA_CP | CA-CP-113 | 1 | kbindusree | 35166 | Rejected | PAS6.1 | Manas

## Design Tickets
Label | Scenario ID | No. of Test Cases | Developer | Design ticket | Assignee | Comments
pas6_nbp | NBP154 | 1 |  | DEMO-21905 | Shireesh | To check on how to test this scenario
PAS05_Pilot | C-H-Coverage-CA-1609 | 1 |  | DEMO-11260 | Sharique | Don’t have access to Test package in RTC
PAS2,3,4 | C-AU-SS-CL-364 | 8 | Chittranjan | DEMO-21844 | Purva
PAS2,3,4 | C-AU-SS-CL-354 | 3 | Chittranjan | DEMO-21864 | Purva
defect_automation | B-T-Auto-SS-AutomatedRenewal-AZ-16 | 1 | Rajasekhar | DEMO-16667 | Shireesh | The functionality has been descoped
defect_automation | B-F-Auto-SS-Reports-CCL-45 | 1 |  |  | Shireesh | This has already been tested by Exigen.