## CA_CP
Project | Key | Summary | Issue Type | Status | Assignee | Developer | Automation Feasibility | Blocked Reason | No. of Test Cases | TC Coded | CCI | Defect | Design | Manual | Inprogress | Boolean | Defect No/Env Issue No | Pay Plan | PayPlan1R | PayPlan2R | Payment Plan | Phase | Phase Impacted | Phase of Origin | Preconditions | Privilege | Probability | Product | Product Type | Products Pending | QC ID | Query Count | Query Description | Query Raised By | RRC ID | RTC ID | RTC Status | Raised During | Rank | Re-Open Reason | Reason for Automation Feasibility | Reason for not in Regression Scope | Recommendations | Regression Reusability | Regression Scope | Regression Thread | Related To | Related US_AC | Release | Reopen | Resolution Details | Response Plan | Review Comments | Review Stage | Review Type | Reviewer | Risk Impact | Risk Response | Risk Score | Risk Severity | Scenario Task Type | Scenario Type | Scenario Type 2 | Schedule Impact (hours/days) | Source Release | Source[CMMI] | Sprint | Sprint | Stakeholders | State | States Pending | Status | Story Point | Suggested Product | Suggested State
CSAA | DEMO-17649 | CA-CP-100 | Testing Task | Update Script | rajashekar | rajashekar | Fully Automated |  | 16 | 16 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i00zvj: | [13 empty] | Please refer the previous comments for review. | Script Review |  | dnasikkar
CSAA | DEMO-17648 | CA-CP-101 | Testing Task | Ready for Review | mapendyala | mapendyala | Fully Automated |  | 9 | 9 | [5 empty] | TRUE | 34870 | [5 empty] | Construction - Development | [15 empty] | 0¦i00zv3:
CSAA | DEMO-17647 | CA-CP-103 | Testing Task | Blocked | sbahl | sbahl |  |  | 13 | 5 |  | 8 |  |  |  | TRUE | 34982 | [5 empty] | Construction - Development | [15 empty] | 0¦i00zx3:
CSAA | DEMO-17646 | CA-CP-105 | Testing Task | Script Review | jidasgupta | pavirao | Fully Automated |  | 10 | 10 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i00zw7: | [16 empty] | jidasgupta
CSAA | DEMO-17645 | CA-CP-106 | Testing Task | Ready for Review | pavirao | pavirao | Fully Automated |  | 17 | 17 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i00zvb:
CSAA | DEMO-17644 | CA-CP-107 | Testing Task | Ready for Review | sheela | sheela | Partial - Non Integration |  | 12 | 10 |  |  |  | 2 |  | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i02dif:
CSAA | DEMO-17643 | CA-CP-109 | Testing Task | Blocked | kbindusree | kbindusree |  | Defect | 15 | 14 |  | 1 |  |  |  | TRUE | 35017 | [5 empty] | Construction - Development | [15 empty] | 0¦i00zxj:
CSAA | DEMO-17642 | CA-CP-110 | Testing Task | Ready for Review | kbindusree | sbahl |  | Defect | 18 | 18 | [5 empty] | TRUE | 34656 | [5 empty] | Construction - Development | [15 empty] | 0¦i00zvz:
CSAA | DEMO-17641 | CA-CP-111 | Testing Task | Ready for Review | Zoheb Ahmed Banikar | kbindusree |  | Design Doc CR | 8 | 8 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i010h3:
CSAA | DEMO-17640 | CA-CP-112 | Testing Task | Ready for Review | achbhatia | achbhatia |  | Design Doc CR | 14 | 14 | [5 empty] | TRUE | 35431 | [5 empty] | Construction - Development | [15 empty] | 0¦i00ycn:
CSAA | DEMO-17639 | CA-CP-113 | Testing Task | Update Script | kbindusree | kbindusree | Fully Automated |  | 10 | 9 |  | 1 |  |  |  | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i00ybb:
CSAA | DEMO-17638 | CA-CP-114 | Testing Task | Ready for Review | mtare | mtare | Fully Automated |  | 8 | 8 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i00ybz:
CSAA | DEMO-17637 | CA-CP-115 | Testing Task | Ready for Review | priyajoshi | priyajoshi | Fully Automated |  | 5 | 5 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i012tr:
CSAA | DEMO-17636 | CA-CP-116 | Testing Task | Ready for Review | akonchada | sheela | Fully Automated |  | 7 | 7 | [5 empty] | TRUE | 35488 | [5 empty] | Construction - Development | [15 empty] | 0¦i01trr:
CSAA | DEMO-17635 | CA-CP-118 | Testing Task | Blocked | mapendyala | mapendyala |  | Design Doc CR | 12 | 12 | [5 empty] | TRUE | INC0402240 | [5 empty] | Construction - Development | [15 empty] | 0¦i00zuv:
CSAA | DEMO-17634 | CA-CP-121 | Testing Task | Ready for Review | sheela | sheela | Fully Automated |  | 2 | 2 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i02dbj:
CSAA | DEMO-17633 | CA-CP-104 | Testing Task | Blocked | akonchada | achbhatia | Fully Automated | Defect | 11 | 11 | [5 empty] | TRUE | 35291 | [5 empty] | Construction - Development | [15 empty] | 0¦i02avb: | [13 empty] | Coded for 11 ACs. Need to raise defect. | Script Review |  | akonchada
CSAA | DEMO-17632 | CA-CP-108 | Testing Task | Ready for Review | chitranjan | chitranjan | Fully Automated |  | 11 | 11 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i027sf:
CSAA | DEMO-17631 | CA-CP-120 | Testing Task | Ready for Review | sbahl | sbahl |  |  | 11 | 11 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i02azz:
CSAA | DEMO-17630 | CA-CP-102 | Testing Task | Ready for Review | Ruchir Agarwal | Ruchir Agarwal |  |  | 18 | 18 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i00h5z:
CSAA | DEMO-17629 | CA-CP-119 | Testing Task | Blocked | Zoheb Ahmed Banikar | Zoheb Ahmed Banikar |  | Defect | 4 | 2 |  | 2 |  |  |  | TRUE | 34870 | [5 empty] | Construction - Development | [15 empty] | 0¦i02akn:
CSAA | DEMO-17628 | CA-CP-117 | Testing Task | Ready for Review | chitranjan | chitranjan |  | Workflow Not Developed | 14 | 14 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i01qmn:
CSAA | DEMO-17627 | CA-CP-122 | Testing Task | Ready for Review | Bhushan | mtare | Fully Automated |  | 10 | 10 | [5 empty] | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i027wf: | [13 empty] | Incorrectly turned into Ready for review status; sending it back to complete development | Script Review |  | Bhushan
CSAA | DEMO-17626 | CA-CP-123 | Testing Task | Blocked | chitranjan | chitranjan |  | Design Doc CR | 10 | 9 |  | 1 |  |  |  | TRUE | [6 empty] | Construction - Development | [15 empty] | 0¦i027yn:
[9 empty] | 265 | 250 | 0 | 13 | 0 | 2 | 0

## CL_CP
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Fix Version/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | AC Category | AC Count | AC No | AC Pattern Type | Account | Actual End Date | Actual Start Date | All Products Covered | All States Covered | Analysis Priority | Applicable States | Attribute ID / CR ID | Automation Feasibility | Blocked Reason | Business Impact | CP 1R | CP 2R | CP ID - 2R | CP1R-Old | CP2R-Old | Category | Cause | Cause - Failed in Nightly | Cause - Failed in Pilot | Closure Criteria | Code Review Checklist - Reviewer | Code review checklist - Developer | Coded on Build | Complexity | Contingency Plan | Contour URL | Date Analysis Completed | Date Analysis Started | Date Blocked | Date Design Completed | Date Design Update Complete | Date Primary Review Started | Date Query Raised | Date Query Resolved | Date Set | Date Unblocked | Date of Assignment | Date of Code Commit | Date of Completion | Date of Primary Review Completion | Date of RTC Status Update | Date of Re-Completion | Date of Script Update | Date of Secondary Review Completion | Date review comments added | Decision Reached | Decision# | Defect Category | Defect Cause Type | Developer | Defect ID | Defect No/Env Issue No | Defect Severity | Defect Status (If any) | Defect Type | Defect Type | Defect Type | Defect_Comments | Delta State | Design Author | Detected Stage and Injected Stage | Discipline/ Thread | EVD for SI Task - AN | EVD for SI Task - DP | EVD for SI Task - DV | EVD for SI Task - RQ | EVD for SI Task - SM | EVD for SI Task - TE | EVD for SI Task - TS | Epic Activity | Epic Link | Escalation Level | Estimated End Date | Estimated Start Date | Expected Detection Phase | External issue ID | External issue ID | External issue ID | Feature Area | Financial Impact ($) | Fixed By | Fixed on Date | Flagged | FormID | Functional Area | Group Ownership | Identified | Impact Summary | Iteration | Iteration | Justification/Reason | L1 | L2 | L3 | LOB | Latest RRC ID | Level 1 Capability | Level 2 Capability | Lifecycle Phase | Line of Business | Link | MTC ID - 2R | MTC2R | Manually Tested | NB1R | NBP ID | New/Updated Deliverable | No of Review Comments (External) | No of Review Comments (Internal) | No of Reviews | No. of Test Cases | Not Applicable | Objective | Old RRC ID/US ID | PAS5 Pilot | Passed Source | PatternID / ScenarioID/TestCaseID | Pay Plan | PayPlan1R | PayPlan2R | Payment Plan | Phase | Phase Impacted | Phase of Origin | Preconditions | Privilege | Probability | Product | Product Type | Products Pending | QC ID | Query Count | Query Description | Query Raised By | RRC ID | RTC ID | RTC Status | Raised During | Rank | Re-Open Reason | Reason for Automation Feasibility | Reason for not in Regression Scope | Recommendations | Regression Reusability | Regression Scope | Regression Thread | Related To | Related US_AC | Release | Reopen | Resolution Details | Response Plan | Review Comments | Review Stage | Review Type | Reviewer | Risk Impact | Risk Response | Risk Score | Risk Severity | Scenario Task Type | Scenario Type | Scenario Type 2 | Schedule Impact (hours/days) | Source Release | Source[CMMI] | Sprint | Sprint | Stakeholders | State | States Pending | Status | Story Point | Suggested Product | Suggested State | TC Coded | CCI | Defect | Design | Manual | Integration | Inprogress | Boolean | Reviewer
CSAA | DEMO-17328 | CL-CP-110-DE | Testing Task | Ready for Review | Medium | Unresolved | Monica Jettipalle | jidasgupta | jidasgupta | 2015-09-11 00:38 |  | 2015-09-25 17:07 |  |  |  | 0 | 1 |  | 32400 | 32400 |  | 0% |  |  | CL-CP-110-DE |  | 0% | 0% |  | 32400 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [15 empty] | Medium | [23 empty] | Defect |  | Monica Jettipalle |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [20 empty] | 1 | [11 empty] | Construction - Development | [15 empty] | 0¦i028s7: | [36 empty] | 1 | [6 empty] | TRUE
CSAA | DEMO-17327 | CL-CP-109-DE | Testing Task | Blocked | Medium | Unresolved | achbhatia | jidasgupta | jidasgupta | 2015-09-11 00:38 |  | 2015-09-26 15:45 |  |  |  | 0 | 1 |  | 32400 | 32400 |  | 0% |  |  | CL-CP-109-DE |  | 0% | 0% |  | 32400 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | Defect | [14 empty] | Medium |  |  |  |  | 2015-09-26 15:45 | [7 empty] | 2015-09-18 | [10 empty] | Defect |  | achbhatia |  | 35017 | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 1 | [11 empty] | Construction - Development | [15 empty] | 0¦i0251j: | [36 empty] | 0 |  | 1 |  |  |  |  | TRUE
CSAA | DEMO-17326 | CL-CP-107-DE | Testing Task | Test in Pilot | Medium | Unresolved | sheela | jidasgupta | jidasgupta | 2015-09-11 00:38 |  | 2015-10-27 17:00 |  |  |  | 0 | 1 |  | 32400 | 0 | 32400 | 100% |  |  | CL-CP-107-DE |  | 100% | 100% | 32400 | 0 | 32400 | CP |  |  |  |  | None | [7 empty] | Partial - Non Integration | Workflow Not Developed | [11 empty] | Review against Functional Design, Naming Conventions, Coding Conventions | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Defect Coded (If Any), Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium |  |  |  |  | 2015-09-23 15:15 | [6 empty] | 2015-09-26 14:43 |  | 2015-09-26 | [9 empty] | Defect |  | sheela |  | 34754 | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 2 | [11 empty] | Construction - Development | [15 empty] | 0¦i0255b: | [16 empty] | jidasgupta | [19 empty] | 2 | [6 empty] | TRUE
CSAA | DEMO-17325 | CL-CP-101-DE | Testing Task | Test in Pilot | Medium | Unresolved | kbindusree | jidasgupta | jidasgupta | 2015-09-11 00:38 |  | 2015-09-30 17:24 |  |  |  | 0 | 1 |  | 32400 | 30600 | 1800 | 5% |  |  | CL-CP-101-DE |  | 5% | 5% | 1800 | 30600 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [12 empty] | Review against Functional Design, Naming Conventions, Coding Conventions | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-09-21 | 2015-09-23 | [9 empty] | Defect |  | kbindusree |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 1 | [11 empty] | Construction - Development | [15 empty] | 0¦i024yf: | [16 empty] | jidasgupta | [19 empty] | 1 | [6 empty] | TRUE
CSAA | DEMO-17324 | CL-CP-102-DE | Testing Task | Ready for Review | Low | Unresolved | rajashekar | akonchada | akonchada | 2015-09-10 16:02 |  | 2015-09-24 15:48 |  |  |  | 0 | 1 |  | 43200 | 10800 | 32400 | 75% |  |  | CL-CP-102-DE |  | 75% | 75% | 32400 | 10800 | 43200 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [13 empty] | Naming Conventions, Coding Conventions |  | Low | [12 empty] | 2015-09-23 | 2015-09-24 | [9 empty] | Defect |  | rajashekar |  |  | Medium |  | Code Change |  |  |  |  | Shireesh | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 1 | [27 empty] | 0¦i0281b: | [36 empty] | 1 | [6 empty] | TRUE
CSAA | DEMO-17323 | CL-CP-104-DE | Testing Task | Ready for Review | Medium | Unresolved | chitranjan | akonchada | akonchada | 2015-09-10 15:59 | 2015-10-20 12:11 | 2015-09-25 13:43 |  |  |  | 0 | 1 |  | 72000 | 14400 |  | 0% |  |  | CL-CP-104-DE |  | 0% | 0% |  | 14400 | 72000 | CP |  |  |  |  | None | [7 empty] | Fully Automated | Defect | [14 empty] | Low |  |  |  |  | 2015-09-25 13:43 | [7 empty] | 2015-09-25 | [10 empty] | Defect |  | chitranjan |  | 35048 | Medium |  | Code Change |  |  |  |  | Varun Dixit | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 1 | [27 empty] | 0¦i025d3: | [36 empty] | 1 | [6 empty] | TRUE
CSAA | DEMO-17321 | CL-CP-120 | Testing Task | Ready for Review | Medium | Unresolved | chitranjan | akonchada | akonchada | 2015-09-10 15:38 | 2015-09-10 15:39 | 2015-09-21 18:46 |  |  |  | 0 | 1 |  | 288000 | 28800 |  | 0% |  |  | CL-CP-120 |  | 0% | 0% |  | 28800 | 288000 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [15 empty] | Medium | [12 empty] | 2015-09-10 | [10 empty] | Defect |  | chitranjan |  |  | Medium |  | Code Change |  |  |  |  | Varun Dixit | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 12 | [27 empty] | 0¦i025av: | [36 empty] | 12 | [6 empty] | TRUE
CSAA | DEMO-17320 | CL-CP-100-OK | Testing Task | Ready for Review | High | Unresolved | kbindusree | akonchada | akonchada | 2015-09-10 15:34 |  | 2015-09-21 13:24 |  |  |  | 0 | 1 |  | 97200 | 95400 | 1800 | 1% |  | DEMO-17322 | CL-CP-100-OK |  | 1% | 1% | 1800 | 95400 | 97200 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [13 empty] | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-09-10 | 2015-09-21 | [9 empty] | Defect |  | kbindusree |  |  | Medium |  | Code Change |  |  |  |  | Upasana | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 2 | [27 empty] | 0¦i022lz: | [36 empty] | 2 | [6 empty] | TRUE | Dipti
CSAA | DEMO-17319 | CL-CP-100-DE | Testing Task | Ready for Review | Low | Unresolved | akonchada | akonchada | akonchada | 2015-09-10 15:30 |  | 2015-09-21 18:46 |  |  |  | 0 | 1 |  | 97200 | 97200 |  | 0% |  |  | CL-CP-100-DE |  | 0% | 0% |  | 97200 | 97200 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [15 empty] | Medium | [12 empty] | 2015-09-10 | [10 empty] | Defect |  | akonchada |  |  | Medium |  | Code Change |  |  |  |  | Upasana | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 1 | [27 empty] | 0¦i02547: | [36 empty] | 1 | [6 empty] | TRUE | Dipti
CSAA | DEMO-17318 | CL-CP-119 | Testing Task | Ready for Review | High | Unresolved | mtare | sheela | sheela | 2015-09-09 17:34 |  | 2015-09-14 12:12 |  |  |  | 0 | 1 |  | 162000 | 32400 | 129600 | 80% |  |  | CL-CP-119 |  | 80% | 80% | 129600 | 32400 | 162000 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [13 empty] | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | High | [12 empty] | 2015-09-09 | 2015-09-14 | [9 empty] | Defect |  | mtare |  |  | Medium |  | Code Change |  |  |  |  | Varun Dixit | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 7 | [27 empty] | 0¦i022wf: | [22 empty] | Calendar | [13 empty] | 7 | [6 empty] | TRUE
CSAA | DEMO-17317 | CL-CP-117 | Testing Task | Ready for Review | High | Unresolved | dnasikkar | sheela | sheela | 2015-09-09 15:22 |  | 2015-10-27 13:52 |  |  |  | 0 | 1 |  | 32400 | 0 | 43200 | 133% |  |  | CL-CP-117 |  | 100% | 100% | 43200 | 0 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [12 empty] | Coding Conventions, Hardcoding Conventions, Review Comments | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Defect Coded (If Any), Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-09-11 | 2015-09-11 | [9 empty] | Defect |  | achbhatia |  |  | Medium |  | Code Change |  |  |  |  | Upasana | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 15 | [27 empty] | 0¦i0256n: | [13 empty] | 27th Oct : - Donot set today's date in the xml - TC_R_R10 - Donot use addDays while setting the dates.Use a standard timepoint present in TimePointsHelper.java - Remove hardcoded policy number on line num 97 - R-R5 - Coverage Validations as per Product type is not covered. Additional : - Line 385 - Renewal Part2 is executed twice | Script Review |  | dnasikkar | [5 empty] | Calendar | [13 empty] | 15 | [6 empty] | TRUE
CSAA | DEMO-17316 | CL-CP-106-DE | Testing Task | Ready for Review | Medium | Unresolved | pavirao | akonchada | akonchada | 2015-09-09 14:15 |  | 2015-09-24 13:25 |  |  |  | 0 | 1 |  | 129600 | 32400 | 97200 | 75% |  | DEMO-17842 | CL-CP-106-DE |  | 75% | 75% | 97200 | 32400 | 129600 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [13 empty] | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Defect Coded (If Any), Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Low | [12 empty] | 2015-09-11 | 2015-09-23 | [9 empty] | Defect |  | pavirao |  | 35032 | Medium |  | Code Change |  |  |  |  | Shireesh | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 1 | [27 empty] | 0¦i01y4n: | [36 empty] | 1 | [6 empty] | TRUE
CSAA | DEMO-17315 | CL-CP-121 | Testing Task | Test in Pilot | High | Unresolved | sheela | sheela | sheela | 2015-09-09 13:03 |  | 2015-10-13 16:58 |  |  |  | 0 | 1 |  | 162000 | 0 | 162000 | 100% |  |  | CL-CP-121 |  | 100% | 100% | 162000 | 0 | 162000 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [12 empty] | Review against Functional Design, Naming Conventions, Coding Conventions, Logging Conventions, Hardcoding Conventions, Dataset Conventions, Review Comments | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-09-09 | 2015-09-09 | [9 empty] | Defect |  | sheela |  |  | Medium |  | Code Change |  |  |  |  | Varun Dixit | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 5 | [27 empty] | 0¦i01yef: | [16 empty] | akonchada | [5 empty] | Calendar | [13 empty] | 5 | [6 empty] | TRUE
CSAA | DEMO-16611 | CL-CP-118 | Testing Task | Ready for Build | Medium | Unresolved | mapendyala | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-10-28 12:17 |  |  |  | 0 | 2 |  | 324000 | 0 | 32400 | 10% |  |  | CP118 |  | 100% | 100% | 32400 | 0 | 324000 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [12 empty] | Coding Conventions, Review Comments | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Defect Coded (If Any), Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-09-01 | 2015-09-23 | [9 empty] | Defect |  | mapendyala |  | 34754 | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 15 | [11 empty] | Construction - Development | [15 empty] | 0¦i01z8n: | [13 empty] | 28th Oct: - Replace line num 135-142 by ReportsTabEditorPanel.orderreports()(since ordering specific reports individually is not mentioned in the design doc) - New Business - Bill to at Renewal is not validated as "Insured". - DD3-20 - Billing Job to be run only if the Payment Plan is Quarterly - Replace Line num 214-221 by a common function (Adding Credit Card from the Billing tab) - DD6-20 - Billing job to be run only if Payment Plan is Quarterly/Semi-Annual, Same applies to DD6 - DD9-20 - Bill to be generated only if Payment Plan is Quarterly - Line num 279 - Remove if condition (to be discussed) - DD10-20 - to be done only if Payment plan is non-monthly -R-R1- Validations as per Product type are not covered - R-R3 - Occupancy Type validations as per Product type are not covered - Line num 406 - Replace by a standard timepoint instead of addDays - R-R10 - Verify if alert for pending renewal is displayed - Line num 513 - Replace by a standard timepoint instead of using addDays - Line num 535 - Replace by a standard timepoint instead of using addDays | Script Review |  | dnasikkar | [19 empty] | 15 | [6 empty] | TRUE
CSAA | DEMO-16610 | CL-CP-116 | Testing Task | Ready for Review | Medium | Unresolved | akonchada | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-09-09 21:34 |  |  |  | 0 | 1 |  | 162000 | 0 | 226800 | 140% |  | DEMO-16612 | CL-CP-116 |  | 100% | 100% | 226800 | 0 | 162000 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [13 empty] | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, SVN Commit |  | Medium | [12 empty] | 2015-09-07 | 2015-09-07 | [9 empty] | Defect |  | akonchada |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 10 | [11 empty] | Construction - Development | [15 empty] | 0¦i01z8v: | [36 empty] | 10 | [6 empty] | TRUE | Dipti
CSAA | DEMO-16609 | CL-CP-115 | Testing Task | Ready for Review | Medium | Unresolved | sbahl | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-09-25 11:35 |  |  |  | 0 | 1 |  | 32400 | 32400 |  | 0% |  |  | CL-CP-115 |  | 0% | 0% |  | 32400 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | Defect | [14 empty] | Medium |  |  |  |  | 2015-09-23 15:15 | [6 empty] | 2015-09-25 11:35 | 2015-09-23 | [10 empty] | Defect |  | sbahl |  | 35009 | Medium |  | Code Change |  | New |  |  |  | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 10 | [11 empty] | Construction - Development | [15 empty] | 0¦i01za7: | [36 empty] | 10 | [6 empty] | TRUE
CSAA | DEMO-16608 | CL-CP-114 | Testing Task | Ready for Review | Medium | Unresolved | jidasgupta | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-10-28 18:11 |  |  |  | 0 | 1 |  | 324000 | 0 | 34200 | 10% |  |  | CL-CP-114 |  | 100% | 100% | 34200 | 0 | 324000 | CP |  |  |  |  | None | [7 empty] | Partial - Non Integration | [9 empty] | NA | NA |  | Hardcoding Conventions, Review Comments | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium |  |  |  |  | 2015-08-26 11:24 | [6 empty] | 2015-08-26 11:25 | 2015-08-26 | 2015-08-31 | [9 empty] | Defect |  | mapendyala |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [12 empty] | 2015-10-28 | [7 empty] | None | [19 empty] | 1 | 12 | [11 empty] | Construction - Development | [15 empty] | 0¦i01tvj: | [13 empty] | 28th Oct: Line num 197 - Replace addDays with cancellationeffectiveDate. Replace the hardcoded values for "Cancellation" and "Insured Non-Payment..." - Replacing addDays will not pass as weekend logic will not work for cancellationEffDt on UI Line num 453 - Efolder part to be kept separate from the other code - Done Line num 462,463 - Replace by using Dollar class,if possible - Not possible as no function is available in Dollar class Line num 489,562,625 - Replace with a standard timepoint from TimePointHelper.java - Used utility method as the timelines are not present in TimepointHelper class Additional: Remove usused imports | Script Review |  | jidasgupta | [19 empty] | 11 |  |  |  | 1 |  |  | TRUE
CSAA | DEMO-16607 | CL-CP-113 | Testing Task | Update Script | Medium | Unresolved | mtare | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-10-28 15:37 |  |  |  | 0 | 1 |  | 32400 | 0 | 194400 | 600% |  | DEMO-16703 | CL-CP-113 |  | 100% | 100% | 194400 | 0 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [12 empty] | Review against Functional Design, Naming Conventions, Coding Conventions, Logging Conventions, Hardcoding Conventions, Dataset Conventions, Documentation Conventions | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-08-26 | 2015-09-09 | [9 empty] | Defect |  | mtare |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 11 | [11 empty] | Construction - Development | [15 empty] | 0¦i01z5b: | [13 empty] | 1) Do not mention XPATH for "lblcancelNoticeError" in the script. 2) Override only expected errors at line 156. BindTabEditorPanel.overrideAllRules 3) Replace index=1 with actual value at line 193. 4) Replace "5" with constant in LOC Dollar installmentFee = new Dollar(5); 5) Replace index=1 with actual value at line 513. | Script Review |  | vgakhar | [19 empty] | 11 | [6 empty] | TRUE
CSAA | DEMO-16606 | CL-CP-112 | Testing Task | Test in Pilot | Medium | Unresolved | pavirao | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-10-17 13:16 |  |  |  | 0 | 1 |  | 32400 | 0 | 486000 | 1500% |  |  | CP112 |  | 100% | 100% | 486000 | 0 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [12 empty] | Review against Functional Design, Naming Conventions, Coding Conventions, Logging Conventions | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-08-25 | 2015-09-11 | [9 empty] | Defect |  | pavirao |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 16 | [11 empty] | Construction - Development | [15 empty] | 0¦i01z5j: | [16 empty] | jidasgupta | [19 empty] | 16 | [6 empty] | TRUE
CSAA | DEMO-16605 | CL-CP-111 | Testing Task | Test in Pilot | Medium | Unresolved | kbindusree | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-10-27 18:29 |  |  |  | 0 | 2 |  | 32400 | 27000 | 5400 | 16% |  |  | CP111 |  | 16% | 16% | 5400 | 27000 | 32400 | CP |  |  |  |  | None | [7 empty] | Partial - Integration | [9 empty] | N/A | N/A |  | Review against Functional Design, Naming Conventions, Coding Conventions | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-09-02 | 2015-09-21 | [9 empty] | Defect |  | kbindusree |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [12 empty] | 2015-10-26 | [7 empty] | None | [19 empty] | 2 | 10 | [11 empty] | Construction - Development | [15 empty] | 0¦i022ef: | [13 empty] | Please code for different timelines at 2DD1-20. Please include if logic, For Annual, Semi-Annual, Quarterly: Validate amount left from prior term(due to endorsement) is generated in offcycle bill.-done For Eleven month pay Validate amount left from prior term+ installment amount is generated. Please take latest from svn before updating code.-done | Script Review |  | jidasgupta | [19 empty] | 9 |  |  |  |  | 1 |  | TRUE
CSAA | DEMO-16604 | CL-CP-109 | Testing Task | Blocked | Medium | Unresolved | achbhatia | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-09-25 14:02 |  |  |  | 0 | 1 |  | 288000 | 32400 |  | 0% |  |  | CL-CP-109 |  | 0% | 0% |  | 32400 | 288000 | CP |  |  |  |  | None | [7 empty] | Fully Automated | Defect | [14 empty] | Medium |  |  |  |  | 2015-09-25 14:02 | [7 empty] | 2015-09-11 | [10 empty] | Defect |  | achbhatia |  | 35017 | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 15 | [11 empty] | Construction - Development | [15 empty] | 0¦i026rz: | [36 empty] | 14 |  | 1 |  |  |  |  | TRUE
CSAA | DEMO-16603 | CL-CP-108 | Testing Task | Script Review | Medium | Unresolved | akonchada | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-10-13 17:06 |  |  |  | 0 | 2 |  | 388800 | 64800 | 324000 | 83% |  |  | CL-CP-108 |  | 83% | 83% | 324000 | 64800 | 388800 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [13 empty] | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Defect Coded (If Any), Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-09-10 | 2015-09-25 | [9 empty] | Defect |  | sheela |  | 34754 | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 16 | [11 empty] | Construction - Development | [15 empty] | 0¦i01xb3: | [16 empty] | akonchada | [19 empty] | 16 | [6 empty] | TRUE
CSAA | DEMO-16602 | CL-CP-107 | Testing Task | Test in Pilot | Medium | Unresolved | sheela | jidasgupta | jidasgupta | 2015-08-18 14:52 |  | 2015-10-27 16:29 |  |  |  | 0 | 2 |  | 180000 | 145800 | 34200 | 19% |  | DEMO-17287 | CP107 |  | 19% | 19% | 34200 | 145800 | 180000 | CP |  |  |  |  | None | [7 empty] | Partial - Non Integration | Design Doc CR | [8 empty] | N/A | N/A |  | Review against Functional Design, Naming Conventions, Coding Conventions | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Defect Coded (If Any), Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium |  |  |  |  | 2015-09-09 12:33 | [6 empty] | 2015-09-24 19:44 | 2015-09-09 | 2015-09-26 | [9 empty] | Defect |  | sheela |  | 34754 | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [12 empty] | 2015-10-20 | [7 empty] | None | [19 empty] | 2 | 13 | [11 empty] | Construction - Development | [15 empty] | 0¦i02dev: | [13 empty] | 1. TC4_SetCancelNotice: Remove hardcoding for message: done 2. Validation#10 at R+R12 is missing: N/A , this is a manual step. 3. Remove add days for date changes across functions.: done 4. Remove trailing debug code :done | Script Review |  | jidasgupta | [19 empty] | 11 |  |  |  | 2 |  |  | TRUE
CSAA | DEMO-16601 | CL-CP-110 | Testing Task | Ready for Review | Medium | Unresolved | rajashekar | jidasgupta | jidasgupta | 2015-08-18 14:42 |  | 2015-10-30 12:30 |  |  |  | 0 | 1 |  | 32400 | 32400 |  | 0% |  |  | CP110 |  | 0% | 0% |  | 32400 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | Defect | [14 empty] | Medium |  |  |  |  | 2015-09-23 17:19 | [6 empty] | 2015-10-28 19:28 | 2015-09-23 | [10 empty] | Defect |  | rajashekar |  | 34656 | Medium |  | Code Change |  | Existing |  |  |  | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 21 | [11 empty] | Construction - Development | [15 empty] | 0¦i027vj: | [36 empty] | 21 | [6 empty] | TRUE
CSAA | DEMO-16600 | CL-CP-106 | Testing Task | Update Script | Medium | Unresolved | pavirao | jidasgupta | jidasgupta | 2015-08-18 14:42 |  | 2015-10-03 19:34 |  |  |  | 0 | 2 |  | 32400 | 0 | 648000 | 2000% |  | DEMO-16691 | CP106 |  | 100% | 100% | 648000 | 0 | 32400 | CP |  |  |  |  | None | [7 empty] | Partial - Non Integration | [12 empty] | Review against Functional Design, Naming Conventions, Coding Conventions | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Defect Coded (If Any), Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-08-25 | 2015-09-11 | [9 empty] | Defect |  | pavirao |  | 34754 | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 18 | [11 empty] | Construction - Development | [15 empty] | 0¦i01yiv: |  | Step R-R9 has content validation | [11 empty] | 1. Missing validation at R-R10. Kindly take latest code from SVN and check. Validation for V15 is missing | Script Review |  | jidasgupta | [19 empty] | 17 |  |  |  | 1 |  |  | TRUE
CSAA | DEMO-16599 | CL-CP-105 | Testing Task | Test in Pilot | Medium | Unresolved | sheela | jidasgupta | jidasgupta | 2015-08-18 14:42 |  | 2015-10-27 16:10 |  |  |  | 0 | 1 |  | 162000 | 0 | 295200 | 182% |  | DEMO-16658 | CL-CP-105 |  | 100% | 100% | 295200 | 0 | 162000 | CP |  |  |  |  | None | [7 empty] | Partial - Non Integration | Design Doc CR | [8 empty] | N/A | N/A |  | Review against Functional Design, Naming Conventions, Coding Conventions | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium |  |  |  |  | 2015-08-20 09:07 | [6 empty] | 2015-08-21 16:50 | 2015-08-19 | 2015-09-04 | [9 empty] | Defect |  | sheela |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [12 empty] | 2015-10-18 | [7 empty] | None | [19 empty] | 2 | 13 | [11 empty] | Construction - Development | [15 empty] | 0¦i020kf: | [13 empty] | 1. #L validation are missing at DD6+NOC. Please include them in cancellation verification function: Done 2. R-R1 . Remove hard coding for task name: Done 3. R-R6 . Remove hard coding for "status" :Done 4. Remove hard coding at TC019_Endorsement : Done 5. Include scenario doc location in comments: Done | Script Review |  | jidasgupta | [19 empty] | 12 |  |  |  | 1 |  |  | TRUE
CSAA | DEMO-16598 | CL-CP-104 | Testing Task | Ready for Review | Medium | Unresolved | chitranjan | jidasgupta | jidasgupta | 2015-08-18 14:42 | 2015-10-08 12:01 | 2015-10-08 12:03 |  |  |  | 0 | 2 |  | 136800 | 0 | 136800 | 100% |  |  | CL-CP-104 |  | 100% | 100% | 136800 | 0 | 136800 | CP |  |  |  |  | None | [7 empty] | Fully Automated | Defect | [11 empty] | Review Comments | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium |  |  |  |  | 2015-09-10 13:25 | [7 empty] | 2015-08-21 | 2015-08-21 | [9 empty] | Defect |  | chitranjan |  | 35048 | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 14 | [11 empty] | Construction - Development | [15 empty] | 0¦i01ybz: | [13 empty] | 9th Sept- Please block this scenario due to the defect which you mentioned. | Script Review |  | akonchada | [19 empty] | 14 | [6 empty] | TRUE | Dipti
CSAA | DEMO-16597 | CL-CP-103 | Testing Task | Blocked | Medium | Unresolved | mtare | jidasgupta | jidasgupta | 2015-08-18 14:42 |  | 2015-09-23 15:12 |  |  |  | 0 | 2 |  | 32400 | 32400 |  | 0% |  |  | CP103 |  | 0% | 0% |  | 32400 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | Defect | [14 empty] | Medium |  |  |  |  | 2015-09-23 15:12 | [18 empty] | Defect |  | mtare |  | 34982 | Medium |  | Code Change |  | New |  |  |  | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [20 empty] | 18 | [11 empty] | Construction - Development | [15 empty] | 0¦i022s7: | [36 empty] | 9 |  | 9 |  |  |  |  | TRUE | Dipti
CSAA | DEMO-16596 | CL-CP-102 | Testing Task | Ready for Build | Medium | Unresolved | mapendyala | jidasgupta | jidasgupta | 2015-08-18 14:42 |  | 2015-10-15 17:26 |  |  |  | 0 | 1 |  | 324000 | 32400 |  | 0% |  | DEMO-17101 | CP102 |  | 0% | 0% |  | 32400 | 324000 | CP |  |  |  |  | None | [7 empty] | Fully Automated | Defect | [14 empty] | Medium |  |  |  |  | 2015-10-15 17:26 | [6 empty] | 2015-10-06 17:56 | 2015-08-26 | [10 empty] | Defect |  | mapendyala |  | 35429 | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 0 | 23 | [11 empty] | Construction - Development | [15 empty] | 0¦i01yaf: | [36 empty] | 23 | [6 empty] | TRUE | Dipti
CSAA | DEMO-16595 | CL-CP-101 | Testing Task | Test in Pilot | Medium | Unresolved | sbahl | jidasgupta | jidasgupta | 2015-08-18 14:42 |  | 2015-09-30 17:23 |  |  |  | 0 | 1 |  | 32400 | 0 | 216000 | 666% |  |  | CP101 |  | 100% | 100% | 216000 | 0 | 32400 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [12 empty] | Review against Functional Design, Naming Conventions, Coding Conventions | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Defect Coded (If Any), Dataset Conventions, Documentation, SVN Commit, Mini Test Param |  | Medium | [12 empty] | 2015-09-23 | 2015-09-23 | [9 empty] | Defect |  | sbahl |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 14 | [11 empty] | Construction - Development | [15 empty] | 0¦i00zhr: | [16 empty] | jidasgupta | [19 empty] | 14 | [6 empty] | TRUE | Dipti
CSAA | DEMO-16594 | CL-CP-100 | Testing Task | Script Review | Medium | Unresolved | dnasikkar | jidasgupta | jidasgupta | 2015-08-18 14:42 |  | 2015-10-27 16:14 |  |  |  | 0 | 1 |  | 162000 | 0 | 259200 | 160% |  |  | CL-CP-100 |  | 100% | 100% | 259200 | 0 | 162000 | CP |  |  |  |  | None | [7 empty] | Fully Automated | [13 empty] | Naming Conventions, Coding Conventions, Logging Conventions, Harcoding Conventions, Dataset Conventions, SVN Commit |  | Medium | [12 empty] | 2015-08-18 | 2015-09-07 | [9 empty] | Defect |  | akonchada |  |  | Medium |  | Code Change | [5 empty] | Script Development | [7 empty] | Develop Test Automation Script | [20 empty] | None | [19 empty] | 1 | 21 | [11 empty] | Construction - Development | [15 empty] | 0¦i01zsn: | [16 empty] | dnasikkar | [19 empty] | 21 | [6 empty] | TRUE | Dipti
[148 empty] | 320 | [64 empty] | 302 | 0 | 12 | 0 | 5 | 1 | 0

## Sheet3
Summary | AC
CA-CP-100 | 16
CA-CP-101 | 9
CA-CP-103 | 13
CA-CP-105 | 10
CA-CP-106 | 17
CA-CP-107 | 12
CA-CP-109 | 15
CA-CP-110 | 18
CA-CP-111 | 8
CA-CP-112 | 15
CA-CP-113 | 10
CA-CP-114 | 8
CA-CP-115 | 5
CA-CP-116 | 7
CA-CP-118 | 12
CA-CP-121 | 2
CA-CP-104 | 11
CA-CP-108 | 11
CA-CP-120 | 11
CA-CP-102 | 18
CA-CP-119 | 4
CA-CP-117 | 14
CA-CP-122 | 10
CA-CP-123 | 10
CL-CP-110-DE | 1
CL-CP-109-DE | 1
CL-CP-107-DE | 1
CL-CP-101-DE | 1
CL-CP-102-DE | 1
CL-CP-104-DE | 1
CL-CP-120 | 12
CL-CP-100-OK | 2
CL-CP-100-DE | 2
CL-CP-119 | 7
CL-CP-117 | 15
CL-CP-106-DE | 1
CL-CP-121 | 5
CL-CP-118 | 15
CL-CP-116 | 10
CL-CP-115 | 10
CL-CP-114 | 12
CL-CP-113 | 11
CL-CP-112 | 16
CL-CP-111 | 11
CL-CP-109 | 15
CL-CP-108 | 16
CL-CP-107 | 13
CL-CP-110 | 21
CL-CP-106 | 18
CL-CP-105 | 13
CL-CP-104 | 14
CL-CP-103 | 18
CL-CP-102 | 23
CL-CP-101 | 14
CL-CP-100 | 21

## Sheet5
Automation Plan
Plan | Target Acs | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
PAS 6 CP | 59 | 33 | 26 | 0
PAS 5 CP | 44 | 32 | 6 | 6
PAS5(Pilot) | 1 |  |  | 1
PAS5(NBP) | 6 |  |  | 6
PAS 2/3/4 Automation | 9 +24=33 | 4 | 3 | 28
Prod PAS 6 Defects | 2 |  |  | 2
Weekly |  | 69 | 35 | 43
Cumulative |  | 69 | 104 | 147
Resource Plan
Plan |  | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
PAS 6 CP |  | 5 | 5
PAS 5 CP |  | 5 | 1 | 1
PAS5(Pilot) |  |  |  | 1
PAS5(NBP) |  |  |  | 1
PAS 2/3/4 Automation |  | 1 | 2 | 7
Prod PAS 6 Defects |  |  |  | 1
Planned Resource Counts |  | 11 | 8 | 11 | 0
Days | Utilization factor
1 | 0.2
2 | 0.4
3 | 0.6
4 | 0.8
5 | 1
Note on F2: Author: Utilization considered for 3 days on account of Diwali
Note on B7: Konchada, Anusha: 9- pending 24- Recently handed over by PAS2,3,4 team

## Sheet1
Summary | No. of Test Cases | TC Coded | Issue Type | Status
CA-CP-100 | 16 | 16 | Testing Task | Update Script
CA-CP-101 | 9 | 9 | Testing Task | Ready for Review
CA-CP-103 | 13 | 5 | Testing Task | Develop Script
CA-CP-105 | 10 | 10 | Testing Task | Script Review
CA-CP-106 | 17 | 17 | Testing Task | Ready for Review
CA-CP-107 | 12 | 10 | Testing Task | Ready for Review
CA-CP-109 | 15 | 14 | Testing Task | Blocked
CA-CP-110 | 18 | 7 | Testing Task | Develop Script
CA-CP-111 | 8 | 8 | Testing Task | Ready for Review
CA-CP-112 | 15 | 15 | Testing Task | Develop Script
CA-CP-113 | 10 | 9 | Testing Task | Ready for Review
CA-CP-114 | 8 | 8 | Testing Task | Ready for Review
CA-CP-115 | 5 | 5 | Testing Task | Ready for Review
CA-CP-116 | 7 | 6 | Testing Task | Ready for Review
CA-CP-118 | 12 | 12 | Testing Task | Blocked
CA-CP-121 | 2 | 2 | Testing Task | Ready for Review
CA-CP-104 | 11 | 11 | Testing Task | Blocked
CA-CP-108 | 11 | 11 | Testing Task | Ready for Review
CA-CP-120 | 11 | 11 | Testing Task | Develop Script
CA-CP-102 | 18 | 18 | Testing Task | Develop Script
CA-CP-119 | 4 | 2 | Testing Task | Blocked
CA-CP-117 | 14 | 5 | Testing Task | Blocked
CA-CP-122 | 10 | 10 | Testing Task | Ready for Review
CA-CP-123 | 10 | 9 | Testing Task | Blocked
CL-CP-110-DE | 1 | 1 | Testing Task | Open
CL-CP-109-DE | 1 |  | Testing Task | Blocked
CL-CP-107-DE | 1 | 1 | Testing Task | Test in Pilot
CL-CP-101-DE | 1 | 1 | Testing Task | Test in Pilot
CL-CP-102-DE | 1 | 1 | Testing Task | Ready for Review
CL-CP-104-DE | 1 | 1 | Testing Task | Develop Script
CL-CP-120 | 12 | 12 | Testing Task | Develop Script
CL-CP-100-OK | 2 | 2 | Testing Task | Ready for Review
CL-CP-100-DE | 2 | 2 | Testing Task | Develop Script
CL-CP-119 | 7 | 7 | Testing Task | Ready for Review
CL-CP-117 | 15 | 14 | Testing Task | Ready for Review
CL-CP-106-DE | 1 | 1 | Testing Task | Ready for Review
CL-CP-121 | 5 | 5 | Testing Task | Test in Pilot
CL-CP-118 | 15 | 15 | Testing Task | Update Script
CL-CP-116 | 10 | 10 | Testing Task | Ready for Review
CL-CP-115 | 10 | 10 | Testing Task | Develop Script
CL-CP-114 | 12 | 11 | Testing Task | Ready for Review
CL-CP-113 | 11 | 11 | Testing Task | Update Script
CL-CP-112 | 16 | 16 | Testing Task | Test in Pilot
CL-CP-111 | 11 | 10 | Testing Task | Test in Pilot
CL-CP-109 | 15 | 14 | Testing Task | Blocked
CL-CP-108 | 16 | 16 | Testing Task | Script Review
CL-CP-107 | 13 | 11 | Testing Task | Test in Pilot
CL-CP-110 | 21 | 21 | Testing Task | Develop Script
CL-CP-106 | 18 | 17 | Testing Task | Update Script
CL-CP-105 | 13 | 12 | Testing Task | Test in Pilot
CL-CP-104 | 14 | 14 | Testing Task | Blocked
CL-CP-103 | 18 | 9 | Testing Task | Blocked
CL-CP-102 | 23 | 22 | Testing Task | Blocked
CL-CP-101 | 14 | 14 | Testing Task | Test in Pilot
CL-CP-100 | 21 | 21 | Testing Task | Script Review