## Catchup Inventory
Category | CR/Regular | Total ACs | Status
PAS 6 NBP(New) | Regular | 169 | In progress
PAS 6 CP | Regular | 321 | In progress
PAS 6 UBI Testing | Regular | 27 | In progress
PAS 5 CP | Regular | 930 | In progress
PAS 2/3/4 Automation | CR | 240 | In progress
Production Defects (108) | CR | 55 | In progress
PAS 6 Scenarios | Regular | 29 | Not started
PAS 5 Scenarios | Regular | 75 | Not started
PAS 7 | Regular | 300 | Not started
Back Comp Testing | CR | 282 | In progress
Controlled Finance Tests | CR | 240 | In progress
Integration Tests | CR | 149 | In progress
TPT Refactoring | CR | 45 | In progress
Conversion Automation | CR | 84 | Complete
Real Address | Unplanned | 223 | On hold
3169

## Integrated Plan
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
PAS 6 NBP(New) | 169 | 157 | 116 | 2015-09-04: 0; 2015-09-11: 19; 2015-09-18: 11; 2015-09-25: 11
PAS 6 CP | 321 | 321 | 142 | 2015-09-04: 48; 2015-09-11: 36; 2015-09-18: 21; 2015-09-25: 54; 2015-10-02: 20
PAS 6 UBI Testing | 27 | 27 | 0 | 2015-09-04: 0; 2015-09-11: 10; 2015-09-18: 7; 2015-09-25: 10
PAS 5 CP | 930 | 908 | 572 | 0 | 0 | 0 | 14 | 42 | 77 | 77 | 61 | 65 | 0 | 0
PAS 2/3/4 Automation | 240 | 240 | 59 | 0 | 10 | 9 | 13 | 24 | 27 | 27 | 24 | 47
Prod PAS 6 Defects | 55 | 55 | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 6 Scenarios(Refactor) | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14
PAS 5 Scenarios (Refactor) | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 30 | 15
PAS 7 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 60
BCT | 282 | 282 | 0 | 0 | 0 | 23 | 23 | 23 | 23 | 30 | 23 | 30 | 30 | 23 | 30 | 27
CFT | 240 | 240 | 6 | 3 | 6 | 15 | 15 | 15 | 27 | 33 | 60 | 60
TPT Refactoring | 45 | 45 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 10
Integration | 149 | 149 | 80 | 2015-09-04: 0; 2015-09-11: 0; 2015-09-18: 0; 2015-09-25: 10; 2015-10-02: 20; 2015-10-09: 20; 2015-10-16: 19
Conversion | 84 | 84 | 84
Weekly |  |  | 1098 | 67 | 86 | 91 | 155 | 149 | 179 | 191 | 173 | 212 | 90 | 82 | 90 | 102
Cumulative |  |  | 1098 | 1165 | 1251 | 1342 | 1497 | 1646 | 1825 | 2016 | 2189 | 2401 | 2491 | 2573 | 2663 | 2765
Actuals | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | Total Completed | Pending
PAS 6 NBP(New) | 177 | 166 | 116 | 0 | 12 | 8 | 17 | 1 | 0 | 0 | 2 | 0 | 0 | 10 |  |  | 166 | 0
PAS 6 CP | 321 | 315 | 142 | 49 | 36 | 43 | 19 | 0 | 0 | 0 | 1 | 3 | 10 | 0 |  |  | 303 | 12 | all blocked
PAS 6 UBI Testing | 27 | 27 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | 0
PAS 5 CP | 930 | 879 | 572 | 0 | 0 | 0 | 34 | 85 | 88 | 22 | 13 | 14 | 4 | 18 |  |  | 850 | 29 | 23 available
PAS 2/3/4 Automation | 240 | 240 | 59 | 0 | 0 | 1 | 15 | 7 | 14 | 57 | 39 | 24 | 0 | 7 |  |  | 223 | 17 | 29 available
Prod PAS 6 Defects | 55 | 53 | 39 | 4 | 6 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 53 | 0
PAS 6 Scenarios(Refactor) | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 29
PAS 5 Scenarios (Refactor) | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 75
PAS 7 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 300
BCT | 282 | 282 | 0 | 0 | 0 | 13 | 29 | 15 | 27 | 28 | 24 | 27 | 43 | 24 |  |  | 230 | 52
CFT | 240 | 240 | 6 | 3 | 15 | 24 | 15 | 15 | 39 | 39 | 60 | 24 | 0 | 0 |  |  | 240 | 0
TPT Refactoring | 45 | 45 | 0 | 0 | 5 | 6 | 11 | 11 | 7 | 3 | 2 | 0 | 0 | 0 |  |  | 45 | 0
Integration | 149 | 149 | 80 | 0 | 0 | 0 | 0 | 5 | 11 | 7 | 17 | 29 | 0 | 0 |  |  | 149 | 0
Conversion | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 84 | 0
Weekly |  |  | 1098 | 56 | 74 | 97 | 168 | 140 | 186 | 156 | 158 | 121 | 57 | 59 | 0 | 0
Cumulative | 2954 | 2884 | 1098 | 1154 | 1228 | 1325 | 1493 | 1633 | 1819 | 1975 | 2133 | 2254 | 2311 | 2370 | 2370 | 2370 | 2370 | 514

## RiskIssues
Sr. | Work stream | Summary | Severity | Mitigation Plan | Owner | Detected on | Detected by | Status | Resolution | Resolution Date
1 | PAS | PAS5 scenario refactoring(optimization) will require script updates to already completed PAS5 tests | Medium | Review the changes and identify if extensive rework is required | Bhushan | 2015-09-14 | Bhushan | Closed | Burn down revised to include this. | 2015-09-21
2 | BCT | BCT 5.1 will need resources from BCT automation. Schedule will be affected. | Medium | Burn-down to be revised. Revised ETA: 11-Dec. | Bhushan | 2015-09-25 | Swagata | Open
3 | Integration | PAS 6.1 New milestone starting today will require 2 resources from Integration Automation.As a result only 1 resource will be working on Integration Automation.Schedule will be affected | Medium | Revised the burn down. Revised ETA is Dec 11 2015 | Bhushan | 2015-09-25 | Rohan | Open
4 | Integration | Time shift URL is not same as cloud. Tushar is currently looking in to getting a Time shift URL which will be an exact replica of that in cloud, until then we will not be able to test the time shift part of the scripts that we are currently creating. | Medium | Tushar is working with Dev team to get a URL that can be utilized | Kishore | 2015-09-21 | Rohan | Open
5 | PAS | 1.The test scripts developed on PAS6 code base may require additional updates before running against PAS6.1 code | Low | Move test automation to 6.1 servers ASAP | Bhushan | 2015-09-14 | Bhushan | Closed | All the new automation is now on PAS6.1 | 2015-09-21
6 | CFT | Executing all automated tests together is currently not feasible since property and auto framework work separately | Medium | Need to work with EIS team to design a solution for this or plan 2 environments for execution | Bhushan | 2015-09-28 | Bhushan | Open
7 | BCT | BCT and Integration tests will be partially automated | Low | Manual staff will be retained | Sachin | 2015-09-14 | Swagata, Rohan, Bhushan | Open | No resolution currently. Appropriate staffing included in the steady state plan.
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Internal
Actuals | Original Target | Revised Target | Total Completed | Pending | Notes
PAS 6 NBP(New) | 177 | 156 | 154 | 2 | Total = 177 20 AC's - manual (18 int + 2 DB verifications) 1 blocked - cannot automate (requires stub value update at runtime) Can be automated - 156 11/9 10 new Acs added so total count = 156+10 = 166 NBP - 187 ¦ 21 ¦ 166 ¦ 156 ¦ 0 ¦ 10 UBI - 27 ¦ 0 ¦ 27¦ 27 ¦ 0 ¦ 0
PAS 6 CP | 321 | 312 | 289 | 23 | Total = 321, Automatable - 312 Actual complete - 290 Blocked - 22 Defects - 16, Moved to BCT - 9, CCI/CPI - 6 Shireesh count = 320 9/11 321 ¦ 6 ¦ 315 ¦ 303 ¦ 12 ¦ 0
PAS 6 UBI Testing | 27 | 27 | 27 | 0 | Covered in NBP
PAS 5 CP | 930 | 874 | 801 | 73 | 90 blocked, 14 available PAS5 Pilot Total 325 Manual - 20(int - 7; DB validations - 13) Automated - 304, Blocked - 1 (CCI/CPI) PAS5 NBP Total - 321 Manual - 5 (PUP - both auto & property policy required in same script); Descoped - 5 Automated - 294, Blocked - 17 (all defects) Not matching with Shireesh PAS5 CPs Total - 266 (Manual - 2, Moved to BCT - 6) Automated - 214 of 258 Defect - 8 , CCi/CPI - 13, In progress - 23 9/11 status Total ¦ Manual or Descope ¦ Available for automation ¦ Completed ¦ Blocked by Defect ¦ In progress Pilot - 325 ¦ 20 ¦ 305 ¦ 302 ¦ 0 ¦ 3 NBP - 320 ¦ 10 ¦ 310 ¦ 304 ¦ 6 ¦ 0 CP - 266 ¦ 2 ¦ 264 ¦ 226 ¦ 13 ¦ 25 9/16 Status CP - 266 ¦ 2 ¦ 264 ¦ 242 ¦ 13 ¦ 9 Pilot - 325 ¦ 20 ¦ 305 ¦ 304 ¦ 1 ¦ 0 | pilot nbp cp | 305 311 258
PAS 2/3/4 Automation | 240 | 240 | 153 | 87 | Provided by Design team -157 Already coded in PAS4 - 5 Provided by manual team - 86 Already coded in PAS4 - 6 Total inventory = (157-5)+(86-6) = 232 Automated = 192 Moved to Manual = 7 Blocked = 4 (defects) Available = 29
Prod PAS 6 Defects | 55 | 55 | 53 | 2
PAS 6 Scenarios(Refactor) | 29 | 29 | 0 | 29
PAS 5 Scenarios (Refactor) | 75 | 75 | 0 | 75
PAS 7 | 300 | 300 | 0 | 300
BCT | 282 | 282 | 112 | 170
CFT | 240 | 240 | 156 | 84
TPT Refactoring | 45 | 45 | 43 | 2
Integration | 149 | 149 | 103 | 46
Conversion | 84 | 84 | 84 | 0

## PAS Automation (hidden)
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
PAS 6 NBP(New) | 169 | 157 | 116 | 2015-09-04: 0; 2015-09-11: 19; 2015-09-18: 11; 2015-09-25: 11 | 157
PAS 6 CP | 321 | 321 | 142 | 2015-09-04: 48; 2015-09-11: 36; 2015-09-18: 21; 2015-09-25: 54; 2015-10-02: 20 | 321
PAS 6 UBI Testing | 27 | 27 | 0 | 2015-09-04: 0; 2015-09-11: 10; 2015-09-18: 7; 2015-09-25: 10 | 27
PAS 5 CP | 930 | 908 | 572 | 0 | 0 | 0 | 14 | 42 | 77 | 77 | 61 | 65 | 0 | 0 |  |  | 908
PAS 2/3/4 Automation | 240 | 240 | 59 | 0 | 10 | 9 | 13 | 24 | 27 | 27 | 24 | 47 | 0 | 0 |  |  | 240
Prod PAS 6 Defects | 55 | 55 | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 55
PAS 6 Scenarios(Refactor) | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 14 | 0 | 0 | 29
PAS 5 Scenarios (Refactor) | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 30 | 15 | 75
PAS 7 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 60 | 150
Actuals | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
PAS 6 NBP(New) | 169 | 157 | 116 | 2015-09-04: 0; 2015-09-11: 12; 2015-09-18: 8 | 136
PAS 6 CP | 321 | 321 | 142 | 2015-09-04: 49; 2015-09-11: 36; 2015-09-18: 43 | 270
PAS 6 UBI Testing | 27 | 27 | 0 | [13 empty] | 0
PAS 5 CP | 930 | 908 | 572 | [13 empty] | 572
PAS 2/3/4 Automation | 240 | 240 | 59 | [13 empty] | 59
Prod PAS 6 Defects | 55 | 55 | 39 | 2015-09-04: 4; 2015-09-11: 6; 2015-09-18: 2 | 51
PAS 6 Scenarios(Refactor) | 29 | 29 | 0 | [13 empty] | 0
PAS 5 Scenarios (Refactor) | 75 | 75 | 0 | [13 empty] | 0
PAS 7 | 300 | 300 | 0 | [13 empty] | 0
Burn down | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
PAS 6 NBP(New) | 169 | 157 | 116 | 2015-09-04: 0; 2015-09-11: 19; 2015-09-18: 11; 2015-09-25: 11
PAS 6 CP | 321 | 321 | 179 | 2015-09-04: 131; 2015-09-11: 95; 2015-09-18: 74; 2015-09-25: 20; 2015-10-02: 0
PAS 6 UBI Testing | 27 | 27 | 27 | 2015-09-04: 27; 2015-09-11: 17; 2015-09-18: 10; 2015-09-25: 0
PAS 5 CP | 930 | 930 | 269 | 269 | 269 | 269 | 269 | 241 | 178 | 115 | 57 | 0
PAS 2/3/4 Automation | 240 | 240 | 181 | 181 | 171 | 162 | 149 | 125 | 98 | 71 | 36 | 0
Prod PAS 6 Defects | 55 | 55 | 16 | 2015-09-04: 0
PAS 6 Scenarios(Refactor) | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 14 | 0
PAS 5 Scenarios (Refactor) | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 60 | 45 | 15 | 0
PAS 7 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 270 | 240 | 210 | 150
Resources | Total ACs | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
PAS 6 NBP(New) | 169 | 156 |  | 0 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 6 CP | 321 | 321 |  | 8 | 6 | 6 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 6 UBI Testing | 27 | 27 |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 5 CP | 930 | 930 |  | 0 | 0 | 0 | 2 | 6 | 9 | 9 | 8 | 8 | 0 | 0 | 0 | 0
PAS 2/3/4 Automation | 240 | 240 |  | 0 | 4 | 4 | 3 | 7 | 7 | 7 | 8 | 8 | 0 | 0 | 0 | 0
PAS 6 Defects | 55 | 55 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 6 Scenarios | 29 | 29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0
PAS 5 Scenarios | 75 | 75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 10 | 6
PAS 7 | 300 | 300 |  | 2015-11-06: 6; 2015-11-13: 6; 2015-11-20: 6; 2015-11-27: 10
Total |  |  |  | 14 | 15 | 15 | 16 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16

## BCT (hidden)
BCT Completion Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
Plan | 282 | 282 | 0 | 0 | 0 | 23 | 23 | 23 | 23 | 30 | 23 | 30 | 30 | 23 | 30 | 27
Actual |  |  |  | 2015-09-18: 13

## CFT (hidden)
CFT | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
CFT | 240 | 240 | 6 | 3 | 6 | 15 | 15 | 15 | 27 | 33 | 60 | 60
CFT - Actuals |  |  | 6 | 2015-09-04: 3; 2015-09-11: 15; 2015-09-18: 24

## TPT Refactor (hidden)
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
TPT Refactoring | 45 | 45 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 10
Actual | 45 | 45 | 0 | 2015-09-04: 0; 2015-09-11: 5; 2015-09-18: 6

## Integration (hidden)
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
Integration | 149 | 149 | 80 | 2015-09-04: 0; 2015-09-11: 0; 2015-09-18: 0; 2015-09-25: 10; 2015-10-02: 20; 2015-10-09: 20; 2015-10-16: 19
Actuals | 149 | 149 | 80 | 2015-09-04: 0; 2015-09-11: 0; 2015-09-18: 0

## Conversion (hidden)
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27
Conversion | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actuals | 84 | 84 | 84