## Sheet1 (3)
Automation Plan
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | Tentative Target Acs | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 1900-12-11 | 2015-12-18 | 2015-12-25 | 2015-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-22 | 2015-01-29 | 2015-02-05 | 2015-02-12 | 2015-02-19 | 2015-02-26 | 2015-03-04 | 2015-03-11 | 2015-03-18 | 2015-03-25 | 2015-04-01 | 2015-04-08
PAS 6 NBP(New) |  |  | 116 | 0 | 19 | 11 | 11
PAS 6 CP |  |  | 142 | 48 | 36 | 21 | 54 | 20
PAS 6 UBI Testing |  |  | 0 | 0 | 10 | 7 | 10
PAS 5 CP |  |  | 572 | 0 | 0 | 0 | 14 | 42 | 77 | 77 | 61 | 65
PAS 2/3/4 Automation | 240 | 240 | 59 | 0 | 10 | 9 | 13 | 24 | 27 | 27 | 24 | 47 | 451 | 32 | 48 | 24 | 14 | 12 | 12 | 12 | 7 | 7 | 12 | 9 | 12 | 9 | 8 | 8 | 8 | 8 | 40 | 40 | 40 | 40 | 40 | 12
Prod PAS 6 Defects |  |  | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 6 Scenarios(Refactor) | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21 | 9
PAS 5 Scenarios (Refactor) | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6 | 3 | 6 | 6 | 6 | 3 | 3 | 6 | 4 | 6 | 4 | 6 | 6 | 6 | 6
PAS 7 | 300 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 |  |  | 45 | 27 | 32 | 32 | 32 | 19 | 19 | 32 | 26 | 32 | 26 | 39 | 39 | 39 | 39
Weekly |  |  | 928 | 64 | 75 | 48 | 102 | 86 | 104 | 104 | 85 | 112 |  | 53 | 57 | 75 | 44 | 50 | 50 | 50 | 29 | 29 | 50 | 39 | 50 | 39 | 53 | 53 | 53 | 53 | 40 | 40 | 40 | 40 | 40 | 12
Cumulative |  |  | 928 | 992 | 1067 | 1115 | 1217 | 1303 | 1407 | 1511 | 1596 | 1708 |  | 53 | 110 | 185 | 229 | 279 | 329 | 379 | 408 | 437 | 487 | 526 | 576 | 615 | 668 | 721 | 774 | 827 | 867 | 907 | 947 | 987 | 1027 | 1039
Resource Plan
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 |  | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 1900-12-11 | 2015-12-18 | 2015-12-25 | 2015-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-22 | 2015-01-29 | 2015-02-05 | 2015-02-12 | 2015-02-19 | 2015-02-26 | 2015-03-04 | 2015-03-11 | 2015-03-18 | 2015-03-25 | 2015-04-01 | 2015-04-08
PAS 6 NBP(New)
PAS 6 CP
PAS 6 UBI Testing
PAS 5 CP
PAS 2/3/4 Automation | [13 empty] | 8 | 12 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 10 | 10 | 10 | 10 | 10 | 3
Prod PAS 6 Defects
PAS 6 Scenarios(Refactor) | [13 empty] | 7 | 3
PAS 5 Scenarios (Refactor) | [15 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
PAS 7 | [15 empty] | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6
Planned Resource Counts | [13 empty] | 15 | 15 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3
Resource assumption | [13 empty] | 15 |  |  |  | 10
Days | Utilization factor
1 | 0.2
2 | 0.4
3 | 0.6
4 | 0.8
5 | 1
Assumptions
1 | The target AC count is tentative as per the recent communcation from Design team. It is subject to change
2 | All the folks currently working on Catch up CR work will continue until 11/27
3 | Integrating Policy Lifecycle scenarios using NBP and CP will be lower priority as compared to additional automation of PAS2/3/4 and PAS7
4 | We will have seamless delivery of PAS 2/3/4 scenario design from design team (expected to receive 40 TCs each week)
5 | PAS7 scenarios will be available starting 11/16 and all scenarios would be available by 11/27
6 | Beyond 11/27, we will continue to have 12 members in the team who would continue on automation activities (including 6 from steady state)
7 | All firm holidays until Jan 2016 only have been factored in
8 | Doesn’t factor in unscheduled PTOs
9 | No major system outages/ infrastructure outages are factored in
Note on R2: Author: Utilization considered for 3 days on account of Diwali
Note on V2: Author: Utilization considered for 3 days on account of Christmas
Note on W2: Author: Utilization considered for 3 days on account of New Year
Note on Y2: Author: Utilization considered for 4 days on account of Sankranti [assuming Hyd team is on PTO]
Note on AA2: Author: Utilization considered for 4 days on account of Republic Day

## Sheet1 (2)
Automation Plan
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | Tentative Target Acs | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 1900-12-11 | 2015-12-18 | 2015-12-25 | 2015-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-22 | 2015-01-29 | 2015-02-05 | 2015-02-12 | 2015-02-19 | 2015-02-26 | 2015-03-04 | 2015-03-11 | 2015-03-18 | 2015-03-25 | 2015-04-01 | 2015-04-08
PAS 6 NBP(New) | 169 | 157 | 116 | 0 | 19 | 11 | 11
PAS 6 CP | 321 | 321 | 142 | 48 | 36 | 21 | 54 | 20
PAS 6 UBI Testing | 27 | 27 | 0 | 0 | 10 | 7 | 10
PAS 5 CP | 930 | 908 | 572 | 0 | 0 | 0 | 14 | 42 | 77 | 77 | 61 | 65
PAS 2/3/4 Automation | 240 | 240 | 59 | 0 | 10 | 9 | 13 | 24 | 27 | 27 | 24 | 47 | 451 | 32 | 48 | 24 | 14 | 12 | 12 | 12 | 7 | 7 | 12 | 9 | 12 | 9 | 8 | 8 | 8 | 8 | 40 | 40 | 40 | 40 | 40 | 12
Prod PAS 6 Defects | 55 | 55 | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 6 Scenarios(Refactor) | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21 | 9
PAS 5 Scenarios (Refactor) | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 6 | 3 | 6 | 6 | 6 | 3 | 3 | 6 | 4 | 6 | 4 | 6 | 6 | 6 | 6
PAS 7 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 |  |  | 45 | 27 | 32 | 32 | 32 | 19 | 19 | 32 | 26 | 32 | 26 | 39 | 39 | 39 | 39 |  |  | 0
Weekly |  |  | 928 | 64 | 75 | 48 | 102 | 86 | 104 | 104 | 85 | 112 |  | 53 | 57 | 75 | 44 | 50 | 50 | 50 | 29 | 29 | 50 | 39 | 50 | 39 | 53 | 53 | 53 | 53 | 40 | 40 | 40 | 40 | 40 | 12
Cumulative |  |  | 928 | 992 | 1067 | 1115 | 1217 | 1303 | 1407 | 1511 | 1596 | 1708 |  | 53 | 110 | 185 | 229 | 279 | 329 | 379 | 408 | 437 | 487 | 526 | 576 | 615 | 668 | 721 | 774 | 827 | 867 | 907 | 947 | 987 | 1027 | 1039
Resource Plan
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 |  | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 1900-12-11 | 2015-12-18 | 2015-12-25 | 2015-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-22 | 2015-01-29 | 2015-02-05 | 2015-02-12 | 2015-02-19 | 2015-02-26 | 2015-03-04 | 2015-03-11 | 2015-03-18 | 2015-03-25 | 2015-04-01 | 2015-04-08
PAS 6 NBP(New)
PAS 6 CP
PAS 6 UBI Testing
PAS 5 CP
PAS 2/3/4 Automation | [13 empty] | 8 | 12 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 10 | 10 | 10 | 10 | 10 | 3
Prod PAS 6 Defects
PAS 6 Scenarios(Refactor) | [13 empty] | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 5 Scenarios (Refactor) | [15 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
PAS 7 | [15 empty] | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6
Planned Resource Counts | [13 empty] | 15 | 15 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 3
Resource assumption | [13 empty] | 15 |  |  |  | 10
Days | Utilization factor
1 | 0.2
2 | 0.4
3 | 0.6
4 | 0.8
5 | 1
Assumptions
1 | The target AC count is tentative as per the recent communcation from Design team. It is subject to change
2 | All the folks currently working on Catch up CR work will continue until 11/27
3 | Integrating Policy Lifecycle scenarios using NBP and CP will be lower priority as compared to additional automation of PAS2/3/4 and PAS7
4 | We will have seamless delivery of PAS 2/3/4 scenario design from design team (expected to receive 40 TCs each week)
5 | PAS7 scenarios will be available starting 11/16 and all scenarios would be available by 11/27
6 | Beyond 11/27, we will continue to have 12 members in the team who would continue on automation activities (including 6 from steady state)
7 | All firm holidays until Jan 2016 only have been factored in
8 | Doesn’t factor in unscheduled PTOs
9 | No major system outages/ infrastructure outages are factored in
Note on R2: Author: Utilization considered for 3 days on account of Diwali
Note on V2: Author: Utilization considered for 3 days on account of Christmas
Note on W2: Author: Utilization considered for 3 days on account of New Year
Note on Y2: Author: Utilization considered for 4 days on account of Sankranti [assuming Hyd team is on PTO]
Note on AA2: Author: Utilization considered for 4 days on account of Republic Day

## Sheet1
Automation Plan
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | Tentative Target Acs | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 1900-12-11 | 2015-12-18 | 2015-12-25 | 2015-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-22 | 2015-01-29 | 2015-02-05 | 2015-02-12 | 2015-02-19 | 2015-02-26 | 2015-03-04 | 2015-03-11 | 2015-03-18 | 2015-03-25 | 2015-04-01 | 2015-04-08
PAS 6 NBP(New) | 169 | 157 | 116 | 0 | 19 | 11 | 11
PAS 6 CP | 321 | 321 | 142 | 48 | 36 | 21 | 54 | 20
PAS 6 UBI Testing | 27 | 27 | 0 | 0 | 10 | 7 | 10
PAS 5 CP | 930 | 908 | 572 | 0 | 0 | 0 | 14 | 42 | 77 | 77 | 61 | 65 |  | 0 | 0
PAS 2/3/4 Automation | 240 | 240 | 59 | 0 | 10 | 9 | 13 | 24 | 27 | 27 | 24 | 47 | 451 | 32 | 48 | 24 | 24 | 12 | 12 | 12 | 7 | 7 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 28 | 40 | 40 | 40 | 40 | 8
Prod PAS 6 Defects | 55 | 55 | 39 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 6 Scenarios(Refactor) | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21 | 9
PAS 5 Scenarios (Refactor) | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6 | 6 | 6 | 6 | 3 | 3 | 6 | 3
PAS 7 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 |  |  | 45 | 45 | 32 | 32 | 32 | 19 | 19 | 32 | 32 | 32 | 32 | 39 | 39 | 39 | 13 |  |  | 0
Weekly |  |  | 928 | 64 | 75 | 48 | 102 | 86 | 104 | 104 | 85 | 112 |  | 53 | 57 | 75 | 75 | 50 | 50 | 50 | 29 | 29 | 50 | 50 | 50 | 50 | 54 | 54 | 53 | 44 | 40 | 40 | 40 | 40 | 8 | 0
Cumulative |  |  | 928 | 992 | 1067 | 1115 | 1217 | 1303 | 1407 | 1511 | 1596 | 1708
Resource Plan
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 |  | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 1900-12-11 | 2015-12-18 | 2015-12-25 | 2015-01-01 | 2015-01-08 | 2015-01-15 | 2015-01-22 | 2015-01-29 | 2015-02-05 | 2015-02-12 | 2015-02-19 | 2015-02-26 | 2015-03-04 | 2015-03-11 | 2015-03-18 | 2015-03-25 | 2015-04-01 | 2015-04-08
PAS 6 NBP(New)
PAS 6 CP
PAS 6 UBI Testing
PAS 5 CP
PAS 2/3/4 Automation | [13 empty] | 8 | 12 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 7 | 10 | 10 | 10 | 10 | 2
Prod PAS 6 Defects
PAS 6 Scenarios(Refactor) | [13 empty] | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PAS 5 Scenarios (Refactor) | [15 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1
PAS 7 | [15 empty] | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 2
Weekly
Cumulative | [13 empty] | 15 | 15 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 2 | 0
Resource assumption | [13 empty] | 15 |  |  |  | 10
Days | Utilisation factor
1 | 1
2 | 0.8
3 | 0.6
4 | 0.4
5 | 0.2
Note on R2: Author: Utilization considered for 3 days on account of Diwali
Note on V2: Author: Utilization considered low
Note on W2: Author: Utilization considered low
Note on Y2: Author: Utilization considered low

## Sheet2
Plan | Original Target | Revised Target | Till - 8/28 | 2015-09-04
PAS 6 NBP(New) | 169 | 157 | 116 | 0
PAS 6 CP | 321 | 321 | 142 | 48
PAS 6 UBI Testing | 27 | 27 | 0 | 0
PAS 5 CP | 930 | 908 | 572 | 0