## Summary
PAS6 CP
Automation | Total TC | TC coded | Blocked | Manual/Integration | CCI/CPI | InProgress | *blocked due to defect only
As per JIRA | 321 | 271
As per Inventory | 321 | 271 | 12 | 6 | 19 | 13
From design | 321
PAS6 NBP
Automation | Total TC | Completed | Blocked | Manual/Integration
As per JIRA | 204 | 183 | 1 | 20 |  |  | *183 includes UBI[27]
As per Inventory | 204 | 183 | 1 | 20 |  |  | *Completed includes ones that are in pilot+Ready for build
From design | 214
Discrepancy | 10 | [5 empty] | *Scenario ID tickets in JIRA have not been created
Defect Automation
Automation | Total TC | Completed | Blocked
As per JIRA | 55 | 53 | 2
As per Inventory | 55 | 53 | 2 |  |  |  | *Completed includes ones that are in pilot+Ready for build
From design | 55

## BlockedScenarios
Label | Scenario Name | AC/TC count | Status | Reason
pas6_nbp | NBP154 | 1 | Blocked | It requires a CLUE report value to change within a year, which cannot be handled through stub as well.
pas6_nbp | NBP156 [ T-HO-HO3-CA-200] | 2 | Open | Design team did not communicate us after design completition. Yet to create JIRA ticket in Automation
pas6_nbp | NBP157 [ T-HO-HO3-CL-201 ] | 8 | Open | Design team did not communicate us after design completition. Yet to create JIRA ticket in Automation
defect_automation | B-F-Auto-SS-Reports-CCL-45 | 1 | Blocked | Already tested by Exigen- Can we descope it?
defect_automation | B-T-Auto-SS-AutomatedRenewal-AZ-16 | 1 | Blocked | This functionality is not available as per user story 180 CL i.e. the functionality is no longer in place and cannot be tested. Can we descope it?
PAS6_CP | CL-CPs | 6 | Blocked | There are 6 Acs altogether which fall in Manual/ Integration bucket