## Sheet1
Category | JIRA Key | Summary | Scenario Name | Assignee | No of Test Cases | Status | Automation Feasibility | Completed on Week Ending | RCA SCN Name | RCA FLAG | RCA Hand over date
pas6_nbp | DEMO-17261 | NBP153 | C-HO-HO6-CL-197 | Nikhil Save | 2 | Closed | Fully Automated | 2015-10-05 | C-HO-HO6-CL-197 | TRUE
pas6_nbp | DEMO-17260 | NBP152 | C-HO-HO3-CL-196 | Nikhil Save | 2 | Update Script | Fully Automated | 2015-10-05 | C-HO-HO3-CL-196 | TRUE
pas6_nbp | DEMO-17259 | NBP150 | C-PU-PUP-CL-194 | Rohan Soni | 1 | Closed | Fully Automated | 2015-10-05 | C-PU-PUP-CL-194 | TRUE
pas6_nbp | DEMO-17258 | NBP151 | T-HO-HO3-CL-195 | Ruchir Agarwal | 1 | Ready for Build | Fully Automated | 2015-10-05 | T-HO-HO3-CL-195 | TRUE
pas6_nbp | DEMO-17257 | NBP149 | C-PU-PUP-CL-193 | sbahl | 10 | Update Script | Fully Automated | 2015-10-05 | C-PU-PUP-CL-193 | TRUE
pas6_nbp | DEMO-17256 | NBP140 | C-HO-HO3-NJ-190 | sbahl | 1 | Update Script | Fully Automated | 2015-09-14 | C-HO-HO3-NJ-190 | TRUE
pas6_nbp | DEMO-17255 | NBP148 UBI | C-AU-SS-SCL-192 | priyajoshi | 5 | Closed | Partial - Non Integration | 2015-10-05 | C-AU-SS-AZ-192 | TRUE
pas6_nbp | DEMO-17254 | NBP147 UBI | C-AU-SS-SCL-191 | priyajoshi | 5 | Closed | Partial - Non Integration | 2015-10-05 | C-AU-SS-AZ-191 | TRUE
pas6_nbp | DEMO-17253 | NBP146 | T-HO-HO3-CL-189 | G, Sowjanya | 1 | Closed | Fully Automated | 2015-09-14 | T-HO-HO3-CL-189 | TRUE | 2015-11-06
pas6_nbp | DEMO-17252 | NBP145 | T-HO-HO4-CL-188 | G, Sowjanya | 2 | Closed | Fully Automated | 2015-09-14 | T-HO-HO4-CL-188 | TRUE | 2015-11-06
pas6_nbp | DEMO-17251 | NBP144 | T-PU-PUP-CL-187 | mtare | 1 | Ready for Build | Fully Automated | 2015-09-14 | #N/A | FALSE
pas6_nbp | DEMO-17250 | NBP143 | T-PU-PUP-CL-186 | mtare | 1 | Ready for Build | Fully Automated | 2015-09-14 | #N/A | FALSE
pas6_nbp | DEMO-17249 | NBP142 | T-HO-HO4-DE-185 | Monica Jettipalle | 2 | Deferred | Manual - Non Integration |  | #N/A | FALSE
pas6_nbp | DEMO-17248 | NBP141 | T-HO-HO3-SCL-184 | Monica Jettipalle | 1 | Closed | Fully Automated | 2015-09-14 | T-HO-HO3-SCL-184 | TRUE | 2015-11-06
pas6_nbp | DEMO-17247 | NBP139 UBI | C-AU-SS-SCL-183 | Monica Jettipalle | 4 | Passed w/defect | Fully Automated | 2015-10-05 | C-AU-SS-AZ-183 | TRUE
pas6_nbp | DEMO-17246 | NBP138 | F-CEA-CA-182 | Unassigned | 1 | Deferred | Manual - Integration |  | #N/A | FALSE
pas6_nbp | DEMO-17245 | NBP130 | F-CEA-CA-179 | Unassigned | 8 | Deferred | Manual - Integration |  | #N/A | FALSE
pas6_nbp | DEMO-17244 | NBP131 | F-CEA-CA-178 | Unassigned | 4 | Deferred | Manual - Integration |  | #N/A | FALSE
pas6_nbp | DEMO-17243 | NBP125 UBI | C-AU-SS-CL-170 | G, Sowjanya | 8 | Update Script | Fully Automated | 2015-10-05 | C-AU-SS-AZ-170 | TRUE
pas6_nbp | DEMO-17242 | NBP124 UBI | C-AU-SS-CL-169 | priyajoshi | 5 | Update Script | Fully Automated | 2015-10-05 | C-AU-SS-AZ-169 | TRUE
pas6_nbp | DEMO-15142 | NBP121 | C-HO-HO4-CA-166 | chitranjan | 3 | Closed | Fully Automated | 2015-09-14 | C-HO-HO4-CA-166 | TRUE
pas6_nbp | DEMO-15141 | NBP133 | C-HO-DP3-CL-174 | sbahl | 5 | Closed | Fully Automated | 2015-09-14 | C-HO-DP3-CL-174 | TRUE
pas6_nbp | DEMO-15137 | NBP132 | T-HP-HO4-NJ-177 | achbhatia | 3 | Update Script | Partial - Non Integration | 2015-09-14 | T-HP-HO4-NJ-177 | TRUE
pas6_nbp | DEMO-15097 | NBP134 | C-PU-PUP-CL-175 | mtare | 4 | Closed | Fully Automated | 2015-09-14 | C-PU-PUP-CL-175 | TRUE
pas6_nbp | DEMO-14933 | NBP102 | C-HO-HO3-CL-156 | achbhatia | 2 | Closed | Fully Automated | 2015-09-14 | C-HO-HO3-CL-156 | TRUE
pas6_nbp | DEMO-14930 | NBP128 | C-HO-HO6-CA-173 | pavirao | 2 | Closed | Fully Automated | 2015-09-14 | C-HO-HO6-CA-173 | TRUE
pas6_nbp | DEMO-14929 | NBP129 | C-HO-HO3-CA-159 | mapendyala | 3 | Closed | Fully Automated | 2015-09-14 | C-HO-HO3-CA-159 | TRUE
pas6_nbp | DEMO-14928 | NBP137 | F-HO-HO3-CA-181 | sbahl | 1 | Closed | Fully Automated | 2015-09-14 | F-HO-HO3-CA-181 | TRUE
pas6_nbp | DEMO-14927 | NBP135 | C-HO-HO6-CL-176 | mtare | 3 | Closed | Fully Automated | 2015-09-14 | C-HO-HO6-CL-176 | TRUE
pas6_nbp | DEMO-14925 | NBP107 | C-HO-HO4-PA-168 | chitranjan | 3 | Closed | Fully Automated | 2015-09-14 | C-HO-HO4-PA-168 | TRUE
pas6_nbp | DEMO-14924 | NBP136 | C-HO-HO4-CL-180 | sheela | 3 | Closed | Fully Automated | 2015-09-14 | C-HO-HO4-CL-180 | TRUE
pas6_nbp | DEMO-14882 | NBP123 | C-PU-PUP-CL-163 | kbindusree | 2 | Closed | Fully Automated | 2015-09-14 | C-PU-PUP-CL-163 | TRUE
pas6_nbp | DEMO-14881 | NBP94 | C-HO-HO4-CL-152 | kbindusree | 9 | Passed w/defect | Fully Automated | 2015-09-14 | C-HO-HO4-CL-152 | TRUE
pas6_nbp | DEMO-14780 | NBP110 | C-HO-HO3-OK-162 | kbindusree | 2 | Update Script | Fully Automated | 2015-10-23 | #N/A | FALSE
pas6_nbp | DEMO-14745 | NBP122 | C-HP-HO6-CL-167 | rajashekar | 4 | Closed | Fully Automated | 2015-09-14 | C-HP-HO6-CL-167 | TRUE
pas6_nbp | DEMO-14744 | NBP120 | C-HO-DP3-CA-165 | rajashekar | 3 | Closed | Fully Automated | 2015-09-14 | C-HO-DP3-CA-165 | TRUE
pas6_nbp | DEMO-14743 | NBP112 | C-PU-PUP-CCL-164 | chitranjan | 2 | Closed | Fully Automated | 2015-09-14 | C-PU-PUP-CCL-164 | TRUE
pas6_nbp | DEMO-14742 | NBP119 | C-HO-HO3-CA-161 | chitranjan | 4 | Closed | Fully Automated | 2015-09-14 | C-HO-HO3-CA-161 | TRUE
pas6_nbp | DEMO-14741 | NBP118 | T-PU-PUP-CA-160 | sheela | 2 | Closed | Fully Automated | 2015-09-14 | T-PU-PUP-CA-160 | TRUE | 2015-11-06
pas6_nbp | DEMO-14740 | NBP103 | C-PU-PUP-CL-158 | sheela | 2 | Closed | Fully Automated | 2015-09-14 | C-PU-PUP-CL-158 | TRUE
pas6_nbp | DEMO-14739 | NBP105 | C-HO-HO6-CA-157 | Unassigned | 5 | Deferred | Manual - Integration |  | #N/A | FALSE
pas6_nbp | DEMO-14738 | NBP101 | C-HO-HO6-CA-155 | pavirao | 2 | Closed | Fully Automated | 2015-09-14 | C-HO-HO6-CA-155 | TRUE
pas6_nbp | DEMO-14737 | NBP100 | C-HO-HO6-CCL-154 | pavirao | 5 | Closed | Partial - Non Integration | 2015-09-14 | C-HO-HO6-CCL-154 | TRUE | 2015-11-06
pas6_nbp | DEMO-14736 | NBP97 | C-HO-HO4-CA-153 | achbhatia | 2 | Closed | Fully Automated | 2015-10-05 | C-HO-HO4-CA-153 | TRUE
pas6_nbp | DEMO-14735 | NBP117 | C-HO-HO4-CCL-151 | kbindusree | 7 | Closed | Fully Automated | 2015-09-14 | C-HO-HO4-CCL-151 | TRUE
pas6_nbp | DEMO-14734 | NBP106 | C-HO-HO3-OK-150 | mtare | 3 | Closed | Fully Automated | 2015-09-21 | C-HO-HO3-OK-150 | TRUE
pas6_nbp | DEMO-14733 | NBP116 | C-HO-DP3-OK-149 | sbahl | 5 | Closed | Fully Automated | 2015-09-14 | C-HO-DP3-OK-149 | TRUE
pas6_nbp | DEMO-14732 | NBP115 | C-HO-HO3-OK-148 | chitranjan | 6 | Closed | Partial - Non Integration | 2015-09-14 | C-HO-HO3-OK-148 | TRUE
pas6_nbp | DEMO-14731 | NBP108 | C-HO-HO3-SCL-147 | chitranjan | 2 | Closed | Fully Automated | 2015-09-14 | C-HO-HO3-SCL-147 | TRUE
pas6_nbp | DEMO-14730 | NBP104 | C-HO-DP3-SCL-146 | sheela | 3 | Closed | Fully Automated | 2015-09-14 | C-HO-DP3-SCL-146 | TRUE
pas6_nbp | DEMO-14729 | NBP99 | C-HO-HO3-SCL-144 | sheela | 6 | Closed | Partial - Non Integration | 2015-09-14 | C-HO-HO3-SCL-144 | TRUE
pas6_nbp | DEMO-14728 | NBP98 | C-HO-HO6-SCL-143 | pavirao | 3 | Closed | Fully Automated | 2015-09-14 | C-HO-HO6-SCL-143 | TRUE
pas6_nbp | DEMO-14727 | NBP96 | C-HO-HO4-SCL-142 | pavirao | 6 | Closed | Partial - Non Integration | 2015-09-14 | C-HO-HO4-SCL-142 | TRUE
pas6_nbp | DEMO-14726 | NBP95 | C-HO-HO3-DE-141 | mapendyala | 5 | Passed w/defect | Partial - Non Integration | 2015-09-14 | C-HO-HO3-DE-141 | TRUE | 2015-11-06
pas6_nbp | DEMO-14725 | NBP93 | C-HO-HO3-DE-140 | mapendyala | 7 | Closed | Partial - Non Integration | 2015-09-14 | C-HO-HO3-DE-140 | TRUE
pas6_nbp | DEMO-14724 | NBP92 | C-HO-DP3-DE-139 | akonchada | 3 | Closed | Partial - Non Integration | 2015-09-14 | C-HO-DP3-DE-139 | TRUE
pas6_nbp | DEMO-14723 | NBP91 | C-HO-HO3-DE-138 | akonchada | 6 | Closed | Partial - Non Integration | 2015-09-14 | C-HO-HO3-DE-138 | TRUE
pas6_nbp | DEMO-17441 | NBP154 | T-HO-HO3-CL-198 | Unassigned | 1 | Blocked | Fully Automated |  | #N/A | FALSE
defect_automation | DEMO-16702 | B-F-HO-HO3-InsuranceScore-AZ-65 |  | rajashekar | 1 | Closed | Fully Automated | 2015-09-14 | B-F-HO-HO3-InsuranceScore-AZ-65 | TRUE | 2015-11-06
defect_automation | DEMO-16701 | B-C-HO-HO6-Endorsement-SCL-63 |  | achbhatia | 1 | Closed | Fully Automated | 2015-09-14 | B-C-HO-HO6-Endorsement-SCL-63 | TRUE
defect_automation | DEMO-16700 | B-T-HO-HO6-MidtermEndorsement-SCL-62 |  | achbhatia | 1 | Update Script | Fully Automated | 2015-09-14 | B-T-HO-HO6-MidtermEndorsement-SCL-62 | TRUE
defect_automation | DEMO-16699 | B-T-PU-PUP-MidtermEndorsement-SCL-61 |  | rajashekar | 1 | Update Script | Fully Automated | 2015-09-14 | B-T-PU-PUP-MidtermEndorsement-SCL-61 | TRUE
defect_automation | DEMO-16698 | B-C-AU-SS-Rewrite-UT-064 |  | Monica Jettipalle | 1 | Closed | Fully Automated | 2015-09-14 | B-C-AU-SS-Rewrite-UT-064 | TRUE
defect_automation | DEMO-16697 | B-T-HO-HO3-Endorsement-AZ-72 |  | Nikhil Save | 1 | Closed | Fully Automated | 2015-09-14 | B-T-HO-HO3-Endorsement-AZ-72 | TRUE | 2015-11-06
defect_automation | DEMO-16696 | B-T-HO-PUP-Endorsement-AZ-71 |  | Rohan Soni | 1 | Closed | Fully Automated | 2015-09-14 | B-T-HO-PUP-Endorsement-AZ-71 | TRUE | 2015-11-06
defect_automation | DEMO-16695 | B-C-HO-HO3-DefineQuotePolicy-PA-70 |  | G, Sowjanya | 1 | Closed | Fully Automated | 2015-09-21 | B-C-HO-HO3-DefineQuotePolicy-PA-70 | TRUE
defect_automation | DEMO-16694 | B-T-HO-PUP-GenerateDocument-VA-69 |  | akonchada | 1 | Closed | Partial - Non Integration | 2015-09-14 | B-T-HO-PUP-GenerateDocument-VA-69 | TRUE
defect_automation | DEMO-16693 | B-F-HO-HO3-CancellationNotice -UT-67 |  | kbindusree | 1 | Closed | Fully Automated | 2015-09-14 | B-F-HO-HO3-CancellationNotice -UT-67 | TRUE | 2015-11-06
defect_automation | DEMO-16692 | B-T-HO-HO3-CancellationNotice-NJ-66 |  | kbindusree | 1 | Ready for Build | Fully Automated | 2015-09-14 | #N/A | FALSE
defect_automation | DEMO-16683 | B-F-AU-SS-Determine Rate-AZ-041 |  | achbhatia | 1 | Closed | Fully Automated | 2015-09-14 | B-F-AU-SS-Determine Rate-AZ-041 | TRUE | 2015-11-06
defect_automation | DEMO-15793 | B-C-HO-HO3-Automated Renewal-SCL-60 |  | rajashekar | 1 | Closed | Fully Automated | 2015-09-14 | B-C-HO-HO3-Automated Renewal-SCL-60 | TRUE
defect_automation | DEMO-15792 | B-C-PU-PUP-ManageAgentTasks-CCL-59 |  | kbindusree | 1 | Closed | Fully Automated | 2015-10-21 | B-C-PU-PUP-ManageAgentTasks-CCL-59 | TRUE
defect_automation | DEMO-15791 | B-F-AU-SS-GeneralCapability-NY-57 |  | kbindusree | 1 | Closed | Fully Automated | 2015-09-14 | B-F-AU-SS-GeneralCapability-NY-57 | TRUE | 2015-11-06
defect_automation | DEMO-15790 | B-T-HO-HO6-Reports-CA-56 |  | mtare | 1 | Closed | Fully Automated | 2015-09-14 | B-T-HO-HO6-Reports-CA-56 | TRUE
defect_automation | DEMO-15789 | B-T-HO-DP3-DetermineDiscount-AZ-55 |  | rajashekar | 1 | Closed | Fully Automated | 2015-09-14 | B-T-HO-DP3-DetermineDiscount-AZ-55 | TRUE
defect_automation | DEMO-15788 | B-T-HO-HO3-Endorsement-UT-054 |  | Nikhil Save | 1 | Passed w/defect | Fully Automated | 2015-09-21 | B-T-HO-HO3-Endorsement-UT-054 | TRUE | 2015-11-06
defect_automation | DEMO-15787 | B-F-HO-DP3-Endorsement-CCL-53 |  | rajashekar | 1 | Closed | Fully Automated | 2015-09-14 | B-F-HO-DP3-Endorsement-CCL-53 | TRUE
defect_automation | DEMO-15786 | B-C-HO-HO3-Endorsement-UT-51 |  | sheela | 1 | Ready for Build | Fully Automated | 2015-09-14 | B-C-HO-HO3-Endorsement-UT-51 | TRUE
defect_automation | DEMO-15785 | B-F-AU-SS-GenerateDocument-MD-50 |  | achbhatia | 1 | Closed | Fully Automated | 2015-09-14 | B-F-AU-SS-GenerateDocument-MD-50 | TRUE | 2015-11-06
defect_automation | DEMO-15784 | B-T-Auto-SS-DefineQuotePolicy-CL-48 |  | achbhatia | 1 | Closed | Fully Automated | 2015-09-14 | B-T-Auto-SS-DefineQuotePolicy-CL-48 | TRUE | 2015-11-06
defect_automation | DEMO-15783 | B-C-HP-HO4-GenerateDocument-CL-47 |  | rajashekar | 1 | Update Script | Fully Automated | 2015-09-14 | B-C-HP-HO4-GenerateDocument-CL-47 | TRUE
defect_automation | DEMO-15782 | B-F-Auto-SS-Reports-CCL-45 |  | priyajoshi | 1 | Blocked |  |  | #N/A | FALSE
defect_automation | DEMO-15781 | B-F-HO-HO3-Claims-CCL-44 |  | chitranjan | 1 | Closed | Fully Automated | 2015-09-14 | B-F-HO-HO3-Claims-CCL-44 | TRUE
defect_automation | DEMO-15780 | B-T-PU-PUP-Endorsement-CA-43 |  | kbindusree | 1 | Closed | Fully Automated | 2015-09-14 | B-T-PU-PUP-Endorsement-CA-43 | TRUE
defect_automation | DEMO-15779 | B-F-Auto-SS-DefineCoverages-NJ-42 |  | kbindusree | 1 | Closed | Fully Automated | 2015-09-14 | B-F-Auto-SS-DefineCoverages-NJ-42 | TRUE
defect_automation | DEMO-15778 | B-F-Auto-SS-DetermineRate-CL-39 |  | sbahl | 1 | Closed | Fully Automated | 2015-09-14 | B-F-Auto-SS-DetermineRate-CL-39 | TRUE | 2015-11-06
defect_automation | DEMO-15777 | B-T-HP-HO4-Endorsement-UT-38 |  | kbindusree | 1 | Closed | Fully Automated | 2015-09-14 | B-T-HP-HO4-Endorsement-UT-38 | TRUE
defect_automation | DEMO-15776 | B-F-AU-SS-Reports-CL-037 |  | sbahl | 1 | Closed | Fully Automated | 2015-09-14 | B-F-AU-SS-Reports-CL-037 | TRUE
defect_automation | DEMO-15775 | B-T-PU-PUP-DefineNamedInsured-CA-33 |  | pavirao | 1 | Closed | Fully Automated | 2015-09-14 | B-T-PU-PUP-DefineNamedInsured-CA-33 | TRUE
defect_automation | DEMO-15774 | B-T-PU-PUP-Endorsement-CL-32 |  | pavirao | 1 | Closed | Fully Automated | 2015-09-14 | B-T-PU-PUP-Endorsement-CL-32 | TRUE
defect_automation | DEMO-15773 | B-F-PU-PUP-Eligibility-CL-31 |  | achbhatia | 1 | Closed | Fully Automated | 2015-09-14 | B-F-PU-PUP-Eligibility-CL-31 | TRUE
defect_automation | DEMO-15772 | B-T-HO-HO3-Endorsement-CO-30 |  | sheela | 1 | Update Script | Fully Automated | 2015-09-14 | #N/A | FALSE
defect_automation | DEMO-15771 | B-F-PU-PUP-Eligibility-UT-29 |  | sheela | 1 | Closed | Fully Automated | 2015-09-14 | B-F-PU-PUP-Eligibility-UT-29 | TRUE | 2015-11-06
defect_automation | DEMO-15770 | B-C-HP-HO3-Automated Renewal-CO-26 |  | rajashekar | 1 | Closed | Fully Automated | 2015-09-14 | B-C-HP-HO3-Automated Renewal-CO-26 | TRUE
defect_automation | DEMO-15769 | B-T-Auto-SS-Reinstate Policy-AZ-25 |  | pavirao | 1 | Update Script | Fully Automated | 2015-09-14 | #N/A | FALSE
defect_automation | DEMO-15768 | B-F-AU-SS-DefineCoverages-DC-24 |  | pavirao | 1 | Closed | Fully Automated | 2015-09-14 | B-F-AU-SS-DefineCoverages-DC-24 | TRUE
defect_automation | DEMO-15767 | B-C-HO-HO3-Reports-SCL-23 |  | achbhatia | 1 | Closed | Fully Automated | 2015-09-14 | B-C-HO-HO3-Reports-SCL-23 | TRUE
defect_automation | DEMO-15766 | B-F-HO-HO3-ModifyPaymentMethod-SCL-22 |  | achbhatia | 1 | Closed | Fully Automated | 2015-09-14 | B-F-HO-HO3-ModifyPaymentMethod-SCL-22 | TRUE
defect_automation | DEMO-15765 | B-T-Auto-SS-DefinePayment-AZ-21 |  | achbhatia | 1 | Update Script | Fully Automated | 2015-09-14 | #N/A | FALSE
defect_automation | DEMO-15764 | B-C-HP-PUP-ReinstatePolicy-AZ-19 |  | achbhatia | 1 | Closed | Fully Automated | 2015-09-14 | B-C-HP-PUP-ReinstatePolicy-AZ-19 | TRUE
defect_automation | DEMO-15763 | B-F-Auto-SS-VerifyDocumentspriortoBind-UT-18 |  | sbahl | 1 | Closed | Fully Automated | 2015-09-14 | B-F-Auto-SS-VerifyDocumentspriortoBind-UT-18 | TRUE
defect_automation | DEMO-15762 | B-C-HO-HO3-Rewrite-SCL-17 |  | chitranjan | 1 | Closed | Fully Automated | 2015-09-14 | B-C-HO-HO3-Rewrite-SCL-17 | TRUE
defect_automation | DEMO-15761 | B-T-Auto-SS-AutomatedRenewal-AZ-16 |  | rajashekar | 1 | Blocked | Fully Automated |  | #N/A | FALSE
defect_automation | DEMO-15760 | B-T-HO-HO3-DefinePayment-UT-14 |  | sheela | 1 | Closed | Fully Automated | 2015-09-14 | B-T-HO-HO3-DefinePayment-UT-14 | TRUE
defect_automation | DEMO-15759 | B-C-HP-HO3-DefineMortgagee-AZ-13 |  | sbahl | 1 | Closed | Fully Automated | 2015-09-14 | B-C-HP-HO3-DefineMortgagee-AZ-13 | TRUE
defect_automation | DEMO-15758 | B-F-Auto-CSA-DefineDriver-CA-12 |  | mapendyala | 1 | Closed | Fully Automated | 2015-09-14 | B-F-Auto-CSA-DefineDriver-CA-12 | TRUE
defect_automation | DEMO-15757 | B-F-Auto-SS-DefineCoverages-OK-11 |  | sbahl | 1 | Closed | Fully Automated | 2015-09-14 | B-F-Auto-SS-DefineCoverages-OK-11 | TRUE
defect_automation | DEMO-15756 | B-C-HO-HO3-Endorsement-CA-10 |  | chitranjan | 1 | Closed | Fully Automated | 2015-09-14 | B-C-HO-HO3-Endorsement-CA-10 | TRUE
defect_automation | DEMO-15755 | B-F-PU-PUP-GenerateDocumentsTriggers-CO-7 |  | chitranjan | 1 | Closed | Fully Automated | 2015-09-14 | B-F-PU-PUP-GenerateDocumentsTriggers-CO-7 | TRUE
defect_automation | DEMO-15754 | B-F-HO-HO3-Reports-CCL-6 |  | rajashekar | 1 | Passed w/defect | Fully Automated | 2015-09-14 | B-F-HO-HO3-Reports-CCL-6 | TRUE | 2015-11-06
defect_automation | DEMO-15753 | B-F-HO-HO3-Reports-CCL-4 |  | rajashekar | 1 | Closed | Fully Automated | 2015-09-14 | B-F-HO-HO3-Reports-CCL-4 | TRUE
defect_automation | DEMO-15752 | B-F-PU-PUP-MailingAddress-CL-2 |  | kbindusree | 1 | Closed | Fully Automated | 2015-09-14 | B-F-PU-PUP-MailingAddress-CL-2 | TRUE
defect_automation | DEMO-15751 | B-T-HO-HO3-GenerateBill-CL-1 |  | kbindusree | 1 | Closed | Fully Automated | 2015-09-14 | B-T-HO-HO3-GenerateBill-CL-1 | TRUE
CP | DEMO-16594 | CL-CP-100 |  | dnasikkar | 21 | Script Review | Fully Automated |  | #N/A | FALSE
CP | DEMO-17319 | CL-CP-100-DE |  | akonchada | 2 | Develop Script | Fully Automated |  | #N/A | FALSE
CP | DEMO-17320 | CL-CP-100-OK |  | kbindusree | 2 | Ready for Review | Fully Automated |  | #N/A | FALSE
CP | DEMO-16595 | CL-CP-101 |  | sbahl | 14 | Test in Pilot | Fully Automated |  | #N/A | FALSE
CP | DEMO-17325 | CL-CP-101-DE |  | kbindusree | 1 | Test in Pilot | Fully Automated |  | #N/A | FALSE
CP | DEMO-16596 | CL-CP-102 |  | mapendyala | 23 | Blocked | Fully Automated |  | #N/A | FALSE
CP | DEMO-17324 | CL-CP-102-DE |  | rajashekar | 1 | Ready for Review | Fully Automated |  | #N/A | FALSE
CP | DEMO-16597 | CL-CP-103 |  | mtare | 18 | Blocked | Fully Automated |  | #N/A | FALSE
CP | DEMO-16598 | CL-CP-104 |  | chitranjan | 14 | Blocked | Fully Automated |  | #N/A | FALSE
CP | DEMO-17323 | CL-CP-104-DE |  | chitranjan | 1 | Develop Script | Fully Automated |  | #N/A | FALSE
CP | DEMO-16599 | CL-CP-105 |  | sheela | 13 | Test in Pilot | Partial - Non Integration |  | #N/A | FALSE
CP | DEMO-16600 | CL-CP-106 |  | pavirao | 18 | Update Script | Partial - Non Integration |  | #N/A | FALSE
CP | DEMO-17316 | CL-CP-106-DE |  | pavirao | 1 | Ready for Review | Fully Automated |  | #N/A | FALSE
CP | DEMO-16602 | CL-CP-107 |  | sheela | 13 | Test in Pilot | Partial - Non Integration |  | #N/A | FALSE
CP | DEMO-17326 | CL-CP-107-DE |  | sheela | 1 | Test in Pilot | Partial - Non Integration |  | #N/A | FALSE
CP | DEMO-16603 | CL-CP-108 |  | akonchada | 16 | Script Review | Fully Automated |  | #N/A | FALSE
CP | DEMO-16604 | CL-CP-109 |  | achbhatia | 15 | Blocked | Fully Automated |  | #N/A | FALSE
CP | DEMO-17327 | CL-CP-109-DE |  | achbhatia | 1 | Blocked | Fully Automated |  | #N/A | FALSE
CP | DEMO-16601 | CL-CP-110 |  | rajashekar | 21 | Develop Script | Fully Automated |  | #N/A | FALSE
CP | DEMO-17328 | CL-CP-110-DE |  | Unassigned | 1 | Open | Fully Automated |  | #N/A | FALSE
CP | DEMO-16605 | CL-CP-111 |  | kbindusree | 11 | Test in Pilot | Partial - Integration |  | #N/A | FALSE
CP | DEMO-16606 | CL-CP-112 |  | pavirao | 16 | Test in Pilot | Fully Automated |  | #N/A | FALSE
CP | DEMO-16607 | CL-CP-113 |  | mtare | 11 | Update Script | Fully Automated |  | #N/A | FALSE
CP | DEMO-16608 | CL-CP-114 |  | jidasgupta | 12 | Ready for Review | Partial - Non Integration |  | #N/A | FALSE
CP | DEMO-16609 | CL-CP-115 |  | sbahl | 10 | Develop Script | Fully Automated |  | #N/A | FALSE
CP | DEMO-16610 | CL-CP-116 |  | akonchada | 10 | Ready for Review | Fully Automated |  | #N/A | FALSE
CP | DEMO-17317 | CL-CP-117 |  | dnasikkar | 15 | Ready for Review | Fully Automated |  | #N/A | FALSE
CP | DEMO-16611 | CL-CP-118 |  | mapendyala | 15 | Update Script | Fully Automated |  | #N/A | FALSE
CP | DEMO-17318 | CL-CP-119 |  | mtare | 7 | Ready for Review | Fully Automated |  | #N/A | FALSE
CP | DEMO-17321 | CL-CP-120 |  | chitranjan | 12 | Develop Script | Fully Automated |  | #N/A | FALSE
CP | DEMO-17315 | CL-CP-121 |  | sheela | 5 | Test in Pilot | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-16148 | T-H-Endorsement-CA-916 |  | sheela | 2 | Closed | Fully Automated | 2015-10-05 | T-H-Endorsement-CA-916 | TRUE
PAS2,3,4 | DEMO-16147 | T-H-Cancellation-CA-940 |  | rajashekar | 2 | Update Script | Partial - Non Integration | 2015-10-05 | #N/A | FALSE
PAS2,3,4 | DEMO-16146 | F-P-PolicyInfo-CA-912 |  | achbhatia | 2 | Closed | Fully Automated | 2015-10-05 | F-P-PolicyInfo-CA-912 | TRUE
PAS2,3,4 | DEMO-16145 | F-H-TollFree-IN-953 |  | Bhushan | 1 | Deferred | Manual - Integration |  | #N/A | FALSE
PAS2,3,4 | DEMO-16142 | F-H-PolicyInfo-CA-945 |  | kbindusree | 3 | Closed | Fully Automated | 2015-10-05 | F-H-PolicyInfo-CA-945 | TRUE
PAS2,3,4 | DEMO-16141 | F-H-PolicyInfo-CA-1502 |  | achbhatia | 4 | Passed w/defect | Fully Automated | 2015-10-05 | F-H-PolicyInfo-CA-1502 | TRUE
PAS2,3,4 | DEMO-16139 | F-H-NewBusiness-CA-937 |  | kbindusree | 4 | Passed w/defect | Partial - Integration | 2015-10-05 | F-H-NewBusiness-CA-937 | TRUE
PAS2,3,4 | DEMO-16138 | F-H-Document-CA-943 |  | rajashekar | 2 | Closed | Partial - Non Integration | 2015-10-05 | F-H-Document-CA-943 | TRUE
PAS2,3,4 | DEMO-16136 | C-P-Rewrite-CA-932 |  | chitranjan | 5 | Passed w/defect | Partial - Non Integration | 2015-10-05 | C-P-Rewrite-CA-932 | TRUE
PAS2,3,4 | DEMO-16135 | C-P-Renewal-CA-903 |  | sheela | 4 | Closed | Fully Automated | 2015-10-05 | C-P-Renewal-CA-903 | TRUE
PAS2,3,4 | DEMO-16132 | C-H-Endorsement-CA-929 |  | chitranjan | 3 | Closed | Fully Automated | 2015-10-05 | C-H-Endorsement-CA-929 | TRUE
PAS2,3,4 | DEMO-16131 | C-H-Cancellation-CA-908 |  | Rohan Soni | 2 | Passed w/defect | Fully Automated | 2015-10-05 | C-H-Cancellation-CA-908 | TRUE
PAS2,3,4 | DEMO-16130 | T-A-Renewal-CL-1811 |  | Bhushan | 3 | Deferred | Manual - Non Integration |  | #N/A | FALSE
PAS2,3,4 | DEMO-16129 | C-P-Renewals-NJ-1874 |  | rajashekar | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-P-Renewals-NJ-1874 | TRUE
PAS2,3,4 | DEMO-16128 | C-A-New Business-CA-1917 |  | Bhushan | 2 | Deferred | Manual - Non Integration |  | #N/A | FALSE
PAS2,3,4 | DEMO-15643 | T-H-Renewals-NJ-1882 |  | Rohan Soni | 2 | Ready for Build | Partial - Non Integration | 2015-11-02 | #N/A | FALSE
PAS2,3,4 | DEMO-15642 | T-A-Renewal-MT-1812 |  | pavirao | 2 | Closed | Partial - Non Integration | 2015-10-05 | T-A-Renewal-MT-1812 | TRUE
PAS2,3,4 | DEMO-15641 | F-A-NewBusiness-MT-1813 |  | sbahl | 2 | Closed | Fully Automated | 2015-10-05 | F-A-NewBusiness-MT-1813 | TRUE
PAS2,3,4 | DEMO-15640 | C-H-Renewal-CL-1919 |  | rajashekar | 2 | Update Script | Partial - Non Integration | 2015-10-05 | C-H-Renewal-CL-1919 | TRUE
PAS2,3,4 | DEMO-15639 | C-H-Cancellation-CL-1877 |  | chitranjan | 6 | Closed | Partial - Integration | 2015-10-05 | C-H-Cancellation-CL-1877 | TRUE
PAS2,3,4 | DEMO-15638 | C-A-Renewal-UT-1887 |  | chitranjan | 3 | Passed w/defect | Partial - Integration | 2015-10-05 | C-A-Renewal-UT-1887 | TRUE
PAS2,3,4 | DEMO-15637 | C-A-Renewal-AZ-1886 |  | mtare | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-A-Renewal-AZ-1886 | TRUE
PAS2,3,4 | DEMO-15636 | C-A-Cancellation-MD-1775 |  | sbahl | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-A-Cancellation-MD-1775 | TRUE | 2015-11-06
PAS2,3,4 | DEMO-15591 | C-P-Renewal-PA-1902 |  | rajashekar | 1 | Passed w/defect | Fully Automated | 2015-10-05 | C-P-Renewal-PA-1902 | TRUE
PAS2,3,4 | DEMO-15339 | T-H-NewBusiness-UT-1859 |  | akonchada | 2 | Closed | Partial - Non Integration | 2015-10-05 | T-H-NewBusiness-UT-1859 | TRUE
PAS2,3,4 | DEMO-15338 | C-A-Renewal-CA-1885 |  | priyajoshi | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-A-Renewal-CA-1885 | TRUE
PAS2,3,4 | DEMO-15136 | C-A-Renewal-AZ-1916 |  | chitranjan | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-A-Renewal-AZ-1916 | TRUE
PAS2,3,4 | DEMO-15135 | I-T-H-Rewrite-UT-1746 |  | pavirao | 1 | Closed | Fully Automated | 2015-10-05 | I-T-H-Rewrite-UT-1746 | TRUE
PAS2,3,4 | DEMO-15120 | T-H-Reinstatepolicy-UT-1742 |  | mapendyala | 2 | Ready for Build | Fully Automated | 2015-10-05 | #N/A | FALSE
PAS2,3,4 | DEMO-15105 | C-P-Rewrite-PA-1903 |  | mapendyala | 1 | Test in Pilot | Fully Automated | 2015-10-12 | C-P-Rewrite-PA-1903 | TRUE
PAS2,3,4 | DEMO-14936 | F-H-Endorsement-PA-1901 |  | akonchada | 2 | Closed | Fully Automated | 2015-10-05 | F-H-Endorsement-PA-1901 | TRUE
PAS2,3,4 | DEMO-14935 | C-H-Renewal-UT-1842 |  | akonchada | 2 | Closed | Fully Automated | 2015-10-05 | C-H-Renewal-UT-1842 | TRUE
PAS2,3,4 | DEMO-14934 | C-P-Rewrite-PA-1816 |  | pavirao | 1 | Closed | Fully Automated | 2015-10-05 | C-P-Rewrite-PA-1816 | TRUE
PAS05_Pilot | DEMO-4970 | C-H-Endorsement-CA-1611 |  | priyajoshi | 3 | Passed w/defect | Fully Automated | 2015-10-05 | C-H-Endorsement-CA-1611 | TRUE
PAS05_Pilot | DEMO-4969 | C-H-Amendment Form-CA-1608 |  | sbahl | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Amendment Form-CA-1608 | TRUE
PAS05_Pilot | DEMO-4968 | C-H-Endorsement-CA-1602 |  | sheela | 3 | Passed w/defect | Fully Automated | 2015-10-05 | C-H-Endorsement-CA-1602 | TRUE
PAS05_Pilot | DEMO-4967 | F-H-Endorsement-CA-1601 |  | chitranjan | 3 | Closed | Fully Automated | 2015-10-05 | F-H-Endorsement-CA-1601 | TRUE
PAS05_Pilot | DEMO-4966 | F-H-Endorsement-CA-1600 |  | Abhinav Sinha | 2 | Closed | Partial - Non Integration | 2015-10-05 | F-H-Endorsement-CA-1600 | TRUE
PAS05_Pilot | DEMO-4965 | F-H-Endorsement-CA-1467 |  | sheela | 2 | Closed | Fully Automated | 2015-10-05 | F-H-Endorsement-CA-1467 | TRUE
PAS05_Pilot | DEMO-4964 | F-H-Endorsement-CA-1449 |  | pdalwani | 2 | Closed | Partial - Non Integration | 2015-10-05 | F-H-Endorsement-CA-1449 | TRUE
PAS05_Pilot | DEMO-4963 | C-H-Endorsement-CA-1448 |  | priyajoshi | 1 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Endorsement-CA-1448 | TRUE
PAS05_Pilot | DEMO-4962 | C-H-RenewalForm-CA-1424 |  | sheela | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-H-RenewalForm-CA-1424 | TRUE
PAS05_Pilot | DEMO-4960 | C-H-Renewal-CA-1618 |  | chitranjan | 1 | Closed | Partial - Integration | 2015-10-05 | C-H-Renewal-CA-1618 | TRUE
PAS05_Pilot | DEMO-4959 | C-H-Renewal-CA-1617 |  | yeshah | 1 | Closed | Partial - Integration | 2015-10-05 | C-H-Renewal-CA-1617 | TRUE
PAS05_Pilot | DEMO-4958 | I-F-H-AAASearch-CA-1616 |  | sbahl | 1 | Closed | Fully Automated | 2015-10-05 | I-F-H-AAASearch-CA-1616 | TRUE
PAS05_Pilot | DEMO-4957 | I-F-H-DocumentGeneration-CA-1615 |  | mtare | 1 | Closed | Partial - Non Integration | 2015-10-05 | I-F-H-DocumentGeneration-CA-1615 | TRUE
PAS05_Pilot | DEMO-4956 | C-H-Coverage-CA-1609 |  | priyajoshi | 1 | Blocked | Fully Automated |  | #N/A | FALSE
PAS05_Pilot | DEMO-4955 | C-H-Endorsement-CA-1605 |  | priyajoshi | 1 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Endorsement-CA-1605 | TRUE
PAS05_Pilot | DEMO-4954 | C-H-Endorsement-CA-1604 |  | chitranjan | 1 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Endorsement-CA-1604 | TRUE
PAS05_Pilot | DEMO-4953 | C-H-Endorsement-CA-1603 |  | priyajoshi | 1 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Endorsement-CA-1603 | TRUE
PAS05_Pilot | DEMO-4952 | C-H-Renewal-CA-1438 |  | sbahl | 1 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Renewal-CA-1438 | TRUE
PAS05_Pilot | DEMO-4948 | T-P-DocumentGeneration-CA-1413 |  | mtare | 9 | Closed | Partial - Non Integration | 2015-10-05 | T-P-DocumentGeneration-CA-1413 | TRUE
PAS05_Pilot | DEMO-4947 | T-H-Endorsement-CA-1434 |  | sbahl | 4 | Closed | Fully Automated | 2015-10-05 | T-H-Endorsement-CA-1434 | TRUE
PAS05_Pilot | DEMO-4946 | T-H-DocumentGeneration-CA-1412 |  | sbahl | 9 | Closed | Partial - Non Integration | 2015-10-05 | T-H-DocumentGeneration-CA-1412 | TRUE
PAS05_Pilot | DEMO-4945 | T-H-DocumentGeneration-CA-1411 |  | sbahl | 4 | Closed | Fully Automated | 2015-10-05 | T-H-DocumentGeneration-CA-1411 | TRUE
PAS05_Pilot | DEMO-4944 | I-T-H-Rewrite-CA-1416 |  | rajashekar | 1 | Closed | Fully Automated | 2015-10-05 | I-T-H-Rewrite-CA-1416 | TRUE
PAS05_Pilot | DEMO-4943 | I-F-H-Endorsement-CA-1455 |  | kbindusree | 1 | Closed | Fully Automated | 2015-10-05 | I-F-H-Endorsement-CA-1455 | TRUE
PAS05_Pilot | DEMO-4942 | I-F-H-DocumentGeneratio-CA-1419 |  | rajashekar | 1 | Closed | Fully Automated | 2015-10-05 | I-F-H-DocumentGeneratio-CA-1419 | TRUE
PAS05_Pilot | DEMO-4941 | I-F-H-DocumentGeneratio-CA-1418 |  | sbahl | 1 | Closed | Partial - Non Integration | 2015-10-05 | I-F-H-DocumentGeneratio-CA-1418 | TRUE
PAS05_Pilot | DEMO-4940 | I-F-H-DocumentGeneration-CA-1417 |  | Abhinav Sinha | 1 | Closed | Partial - Non Integration | 2015-10-05 | I-F-H-DocumentGeneration-CA-1417 | TRUE
PAS05_Pilot | DEMO-4939 | F-P-NewBusiness-CA-1408 |  | Anitha Doniparthi | 3 | Closed | Fully Automated | 2015-10-05 | F-P-NewBusiness-CA-1408 | TRUE
PAS05_Pilot | DEMO-4938 | F-P-NewBusiness-CA-1407 |  | sbahl | 14 | Closed | Fully Automated | 2015-10-05 | F-P-NewBusiness-CA-1407 | TRUE
PAS05_Pilot | DEMO-4937 | F-P-NewBusiness-CA-1406 |  | Abhinav Sinha | 7 | Closed | Fully Automated | 2015-10-05 | F-P-NewBusiness-CA-1406 | TRUE
PAS05_Pilot | DEMO-4936 | F-P-NewBusiness-CA-1405 |  | pavirao | 9 | Closed | Fully Automated | 2015-10-05 | F-P-NewBusiness-CA-1405 | TRUE
PAS05_Pilot | DEMO-4935 | F-P-NewBusiness-CA-1404 |  | rajashekar | 2 | Closed | Partial - Non Integration | 2015-10-05 | F-P-NewBusiness-CA-1404 | TRUE
PAS05_Pilot | DEMO-4934 | F-P-NewBusiness-CA-1403 |  | yeshah | 2 | Closed | Fully Automated | 2015-10-05 | F-P-NewBusiness-CA-1403 | TRUE
PAS05_Pilot | DEMO-4933 | F-P-NewBusiness-CA-1402 |  | pavirao | 2 | Closed | Fully Automated | 2015-10-05 | F-P-NewBusiness-CA-1402 | TRUE
PAS05_Pilot | DEMO-4932 | F-P-NewBusiness-CA-1401 |  | akonchada | 2 | Closed | Fully Automated | 2015-10-05 | F-P-NewBusiness-CA-1401 | TRUE
PAS05_Pilot | DEMO-4931 | F-P-NewBusiness-CA-1400 |  | pavirao | 6 | Closed | Fully Automated | 2015-10-05 | F-P-NewBusiness-CA-1400 | TRUE
PAS05_Pilot | DEMO-4930 | F-P-Motorcycle-CA-1484 |  | mtare | 3 | Closed | Fully Automated | 2015-10-05 | F-P-Motorcycle-CA-1484 | TRUE
PAS05_Pilot | DEMO-4929 | F-P-Agent-CA-1485 |  | Bhushan | 4 | Deferred | Manual - Integration |  | #N/A | FALSE
PAS05_Pilot | DEMO-4928 | F-P-Agent-CA-1481 |  | sheela | 3 | Closed | Partial - Integration | 2015-10-05 | F-P-Agent-CA-1481 | TRUE
PAS05_Pilot | DEMO-4927 | F-P-Agent-1480 |  | Bhushan | 3 | Deferred | Manual - Integration |  | #N/A | FALSE
PAS05_Pilot | DEMO-4926 | F-H-UnderwritingRuleOverride-CA-1498 |  | chitranjan | 2 | Closed | Fully Automated | 2015-10-05 | F-H-UnderwritingRuleOverride-CA-1498 | TRUE
PAS05_Pilot | DEMO-4925 | F-H-Premium-CA-1463 |  | rajashekar | 2 | Closed | Fully Automated | 2015-10-05 | F-H-Premium-CA-1463 | TRUE
PAS05_Pilot | DEMO-4924 | F-H-Premium-CA-1462 |  | Anitha Doniparthi | 2 | Closed | Fully Automated | 2015-10-05 | F-H-Premium-CA-1462 | TRUE
PAS05_Pilot | DEMO-4923 | F-H-Premium-CA-1461 |  | yeshah | 2 | Closed | Fully Automated | 2015-10-05 | F-H-Premium-CA-1461 | TRUE
PAS05_Pilot | DEMO-4922 | F-H-Premium-CA-1459 |  | mtare | 3 | Closed | Fully Automated | 2015-10-05 | F-H-Premium-CA-1459 | TRUE
PAS05_Pilot | DEMO-4921 | F-H-PaymentPlan-CA-1456 |  | kbindusree | 2 | Closed | Fully Automated | 2015-10-05 | F-H-PaymentPlan-CA-1456 | TRUE
PAS05_Pilot | DEMO-4920 | F-H-NewBusinessForm-CA-1436 |  | priyajoshi | 2 | Closed | Partial - Non Integration | 2015-10-05 | F-H-NewBusinessForm-CA-1436 | TRUE
PAS05_Pilot | DEMO-4919 | F-P-License-CA-1447 |  | sbahl | 3 | Closed | Fully Automated | 2015-10-05 | F-P-License-CA-1447 | TRUE
PAS05_Pilot | DEMO-4918 | F-H-Endorsement-CA-1457 |  | sbahl | 3 | Closed | Fully Automated | 2015-10-05 | F-H-Endorsement-CA-1457 | TRUE
PAS05_Pilot | DEMO-4917 | F-H-Endorsement-CA-1432 |  | Abhinav Sinha | 4 | Closed | Fully Automated | 2015-10-05 | F-H-Endorsement-CA-1432 | TRUE
PAS05_Pilot | DEMO-4916 | F-H-DetachedStructure-CA-1452 |  | Rohan Soni | 4 | Passed w/defect | Fully Automated | 2015-10-05 | F-H-DetachedStructure-CA-1452 | TRUE
PAS05_Pilot | DEMO-4915 | F-H-Amendment-CA-1410 |  | Abhinav Sinha | 2 | Closed | Fully Automated | 2015-10-05 | F-H-Amendment-CA-1410 | TRUE
PAS05_Pilot | DEMO-4914 | C-P-Rewrite-CA-1483 |  | pavirao | 2 | Closed | Fully Automated | 2015-10-05 | C-P-Rewrite-CA-1483 | TRUE
PAS05_Pilot | DEMO-4913 | T-P-Rewrite-CA-1482 |  | sheela | 3 | Closed | Fully Automated | 2015-10-05 | T-P-Rewrite-CA-1482 | TRUE
PAS05_Pilot | DEMO-4911 | C-P-Endorsement-CA-1431 |  | sbahl | 2 | Closed | Fully Automated | 2015-10-05 | C-P-Endorsement-CA-1431 | TRUE
PAS05_Pilot | DEMO-4910 | C-P-Endorsement-CA-1430 |  | mtare | 2 | Passed w/defect | Partial - Non Integration | 2015-10-05 | C-P-Endorsement-CA-1430 | TRUE
PAS05_Pilot | DEMO-4909 | C-P-Cancellation-CA-1469 |  | kbindusree | 1 | Closed | Fully Automated | 2015-10-05 | C-P-Cancellation-CA-1469 | TRUE
PAS05_Pilot | DEMO-4908 | C-P-Cancellation-CA-1468 |  | sheela | 4 | Closed | Fully Automated | 2015-10-05 | C-P-Cancellation-CA-1468 | TRUE
PAS05_Pilot | DEMO-4907 | C-H-Rewrite-CA-1471 |  | kbindusree | 2 | Closed | Fully Automated | 2015-10-05 | C-H-Rewrite-CA-1471 | TRUE | 2015-11-06
PAS05_Pilot | DEMO-4906 | C-H-Rewrite-CA-1437 |  | kbindusree | 3 | Closed | Fully Automated | 2015-10-05 | C-H-Rewrite-CA-1437 | TRUE
PAS05_Pilot | DEMO-4905 | C-H-Rewrite-CA-1415 |  | kbindusree | 5 | Closed | Fully Automated | 2015-10-05 | C-H-Rewrite-CA-1415 | TRUE
PAS05_Pilot | DEMO-4904 | C-H-Rewrite-CA-1414 |  | sbahl | 5 | Passed w/defect | Fully Automated | 2015-10-05 | C-H-Rewrite-CA-1414 | TRUE
PAS05_Pilot | DEMO-4903 | C-H-Premium-CA-1464 |  | rajashekar | 4 | Closed | Fully Automated | 2015-10-05 | C-H-Premium-CA-1464 | TRUE
PAS05_Pilot | DEMO-4902 | C-H-Membership-CA-1451 |  | rajashekar | 5 | Closed | Fully Automated | 2015-10-05 | C-H-Membership-CA-1451 | TRUE
PAS05_Pilot | DEMO-4901 | C-H-Membership-CA-1450 |  | pavirao | 3 | Closed | Fully Automated | 2015-10-05 | C-H-Membership-CA-1450 | TRUE
PAS05_Pilot | DEMO-4900 | C-H-Endorsement-CA-1474 |  | pavirao | 3 | Closed | Fully Automated | 2015-10-05 | C-H-Endorsement-CA-1474 | TRUE
PAS05_Pilot | DEMO-4899 | T-H-Endorsement-CA-1458 |  | mapendyala | 6 | Closed | Fully Automated | 2015-10-05 | T-H-Endorsement-CA-1458 | TRUE
PAS05_Pilot | DEMO-4898 | C-H-Endorsement-CA-1454 |  | priyajoshi | 2 | Closed | Fully Automated | 2015-10-05 | C-H-Endorsement-CA-1454 | TRUE
PAS05_Pilot | DEMO-4897 | C-H-Endorsement-CA-1433 |  | yeshah | 4 | Closed | Fully Automated | 2015-10-05 | C-H-Endorsement-CA-1433 | TRUE
PAS05_Pilot | DEMO-4896 | C-H-DetachedStructure-CA-1453 |  | jidasgupta | 4 | Closed | Fully Automated | 2015-10-05 | C-H-DetachedStructure-CA-1453 | TRUE
PAS05_Pilot | DEMO-4895 | C-H-Cancellation-CA-1478 |  | sheela | 2 | Closed | Fully Automated | 2015-10-05 | C-H-Cancellation-CA-1478 | TRUE
PAS05_Pilot | DEMO-4894 | C-H-Cancellation-CA-1477 |  | yeshah | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Cancellation-CA-1477 | TRUE
PAS05_Pilot | DEMO-4893 | C-H-Cancellation-CA-1476 |  | pavirao | 2 | Closed | Fully Automated | 2015-10-05 | C-H-Cancellation-CA-1476 | TRUE
PAS05_Pilot | DEMO-4892 | C-H-Cancellation-CA-1470 |  | pdalwani | 4 | Closed | Fully Automated | 2015-10-05 | C-H-Cancellation-CA-1470 | TRUE
PAS05_Pilot | DEMO-3712 | F-H-OnDemandForm-CA-1444 |  | kbindusree | 2 | Closed | Partial - Integration | 2015-10-05 | F-H-OnDemandForm-CA-1444 | TRUE
PAS05_Pilot | DEMO-3711 | F-H-NewBusiness-CA-1613 |  | pavirao | 2 | Closed | Partial - Non Integration | 2015-10-05 | F-H-NewBusiness-CA-1613 | TRUE
PAS05_Pilot | DEMO-3710 | F-H-NewBusiness-CA-1612 |  | kbindusree | 2 | Closed | Partial - Integration | 2015-10-05 | F-H-NewBusiness-CA-1612 | TRUE
PAS05_Pilot | DEMO-3709 | F-H-DocumentGeneration-CA-1495 |  | Bhushan | 2 | Deferred | Manual - Non Integration |  | #N/A | FALSE
PAS05_Pilot | DEMO-3708 | F-H-DocumentGenerartion-CA-1492 |  | akonchada | 2 | Closed | Partial - Non Integration | 2015-10-05 | F-H-DocumentGenerartion-CA-1492 | TRUE
PAS05_Pilot | DEMO-3707 | C-P-Other Form-CA-1426 |  | akonchada | 1 | Closed | Partial - Non Integration | 2015-10-05 | C-P-Other Form-CA-1426 | TRUE
PAS05_Pilot | DEMO-3706 | C-P-Endorsement-CA-1425 |  | pdalwani | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-P-Endorsement-CA-1425 | TRUE
PAS05_Pilot | DEMO-3705 | C-H-Renewal-CA-1423 |  | Anitha Doniparthi | 4 | Closed | Fully Automated | 2015-10-05 | C-H-Renewal-CA-1423 | TRUE
PAS05_Pilot | DEMO-3704 | C-H-Renewal-CA-1422 |  | pdalwani | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Renewal-CA-1422 | TRUE
PAS05_Pilot | DEMO-3703 | C-H-Renewal-CA-1421 |  | chitranjan | 3 | Closed | Fully Automated | 2015-10-05 | C-H-Renewal-CA-1421 | TRUE
PAS05_Pilot | DEMO-3701 | C-H-Pet-Animal-CA-1491 |  | mtare | 3 | Closed | Fully Automated | 2015-10-05 | C-H-Pet-Animal-CA-1491 | TRUE
PAS05_Pilot | DEMO-3700 | C-H-On-Demand Form-CA-1446 |  | Monica Jettipalle | 2 | Test in Pilot | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS05_Pilot | DEMO-3699 | C-P-OnDemandForm-CA-1445 |  | mtare | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-P-OnDemandForm-CA-1445 | TRUE
PAS05_Pilot | DEMO-3698 | C-H-OnDemandForm-CA-1443 |  | rajashekar | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-H-OnDemandForm-CA-1443 | TRUE
PAS05_Pilot | DEMO-3697 | C-H-On-Demand Form-CA-1442 |  | sbahl | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-H-On-Demand Form-CA-1442 | TRUE
PAS05_Pilot | DEMO-3696 | C-H-On-Demand Form-CA-1441 |  | mtare | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-H-On-Demand Form-CA-1441 | TRUE
PAS05_Pilot | DEMO-3695 | C-H-Inspection-CA-1429 |  | mtare | 2 | Passed w/defect | Fully Automated | 2015-10-05 | C-H-Inspection-CA-1429 | TRUE
PAS05_Pilot | DEMO-3694 | C-H-Inspection-CA-1428 |  | G, Sowjanya | 2 | Closed | Fully Automated | 2015-10-05 | C-H-Inspection-CA-1428 | TRUE
PAS05_Pilot | DEMO-3693 | C-H-Downpayment-CA-1488 |  | sbahl | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Downpayment-CA-1488 | TRUE
PAS05_Pilot | DEMO-3692 | C-H-Downpayment-CA-1486 |  | yeshah | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Downpayment-CA-1486 | TRUE
PAS05_Pilot | DEMO-3691 | C-H-DocumentGeneration-CA-1496 |  | pavirao | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-H-DocumentGeneration-CA-1496 | TRUE
PAS05_Pilot | DEMO-3690 | C-H-DocumentGeneration-CA-1494 |  | Bhushan | 3 | Deferred | Manual - Non Integration |  | #N/A | FALSE
PAS05_Pilot | DEMO-3689 | C-H-DocumentGeneration-CA-1493 |  | pavirao | 5 | Closed | Partial - Non Integration | 2015-10-05 | C-H-DocumentGeneration-CA-1493 | TRUE
PAS05_Pilot | DEMO-3688 | C-H-Amendment Form-CA-1606 |  | rajashekar | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-H-Amendment Form-CA-1606 | TRUE
PAS05_Pilot | DEMO-3679 | F-P-Endorsement-CA-1473 |  | Anitha Doniparthi | 4 | Closed | Fully Automated | 2015-10-05 | F-P-Endorsement-CA-1473 | TRUE
PAS05_Pilot | DEMO-3671 | C-H-Endorsement-CA-1475 |  | Anitha Doniparthi | 4 | Closed | Fully Automated | 2015-10-05 | C-H-Endorsement-CA-1475 | TRUE
PAS05_Pilot | DEMO-2755 | C-H-Premium-CA-1489 |  | dvarada | 3 | Closed | Fully Automated | 2015-10-05 | C-H-Premium-CA-1489 | TRUE
PAS05_Pilot | DEMO-2754 | F-P-AAASearch-CA-1497 |  | achbhatia | 3 | Closed | Fully Automated | 2015-10-05 | F-P-AAASearch-CA-1497 | TRUE
PAS05_Pilot | DEMO-2740 | F-P-Payment-CA-1620 |  | dvarada | 2 | Closed | Fully Automated | 2015-10-05 | F-P-Payment-CA-1620 | TRUE
PAS05_Pilot | DEMO-2739 | F-H-Downpayment-CA-1607 |  | Anitha Doniparthi | 3 | Closed | Partial - Non Integration | 2015-10-05 | F-H-Downpayment-CA-1607 | TRUE
PAS05_Pilot | DEMO-2738 | C-H-NewBusinessForm-CA-1435 |  | Anitha Doniparthi | 4 | Closed | Partial - Non Integration | 2015-10-05 | C-H-NewBusinessForm-CA-1435 | TRUE
PAS05_Pilot | DEMO-2737 | C-H-Downpayment-CA-1487 |  | sheela | 3 | Closed | Fully Automated | 2015-10-05 | C-H-Downpayment-CA-1487 | TRUE | 2015-11-06
PAS05_Pilot | DEMO-2736 | F-H-Downpayment-CA-1490 |  | chitranjan | 2 | Closed | Fully Automated | 2015-10-05 | F-H-Downpayment-CA-1490 | TRUE
PAS05_Pilot | DEMO-2735 | F-H-Endorsement-CA-1472 |  | Anitha Doniparthi | 3 | Closed | Fully Automated | 2015-10-05 | F-H-Endorsement-CA-1472 | TRUE
PAS05_Pilot | DEMO-551 | T-C-PolicyInfo-CA-911 |  | Bhushan | 5 | Deferred | Manual - Non Integration |  | #N/A | FALSE
PAS05_Pilot | DEMO-518 | F-H-Premium-CA-1519 |  | Bhushan | 3 | Deferred | Manual - Non Integration |  | #N/A | FALSE
PAS5_NBP | DEMO-11600 | NBP86 | C-P-CA-137 | chitranjan | 4 | Closed | Fully Automated | 2015-10-05 | C-P-CA-137 | TRUE
PAS5_NBP | DEMO-11599 | NBP90 | C-P-CA-136 | rajashekar | 8 | Closed | Fully Automated | 2015-10-05 | C-P-CA-136 | TRUE
PAS5_NBP | DEMO-11598 | NBP87 | C-P-CA-135 | kbindusree | 3 | Closed | Fully Automated | 2015-10-05 | C-P-CA-135 | TRUE
PAS5_NBP | DEMO-11597 | NBP89 | C-H-CA-134 | sbahl | 6 | Closed | Fully Automated | 2015-10-05 | C-H-CA-134 | TRUE
PAS5_NBP | DEMO-11596 | NBP78 |  | Bhushan | 5 | Deferred | Manual - Non Integration |  | #N/A | FALSE
PAS5_NBP | DEMO-11595 | NBP85 | C-P-CA-132 | pavirao | 5 | Closed | Fully Automated | 2015-10-05 | C-P-CA-132 | TRUE
PAS5_NBP | DEMO-11594 | NBP84 | C-P-CA-130 | mtare | 7 | Closed | Fully Automated | 2015-10-05 | C-P-CA-130 | TRUE
PAS5_NBP | DEMO-11593 | NBP83 | C-P-CA-125 | pavirao | 6 | Closed | Fully Automated | 2015-10-05 | C-P-CA-125 | TRUE
PAS5_NBP | DEMO-11592 | NBP80 | C-H-CA-124 | sheela | 4 | Closed | Fully Automated | 2015-10-05 | C-H-CA-124 | TRUE
PAS5_NBP | DEMO-11591 | NBP82 | C-P-CA-123 | rajashekar | 7 | Closed | Fully Automated | 2015-10-05 | C-P-CA-123 | TRUE
PAS5_NBP | DEMO-11590 | NBP77 | C-H-CA-122 | chitranjan | 5 | Closed | Fully Automated | 2015-10-05 | C-H-CA-122 | TRUE
PAS5_NBP | DEMO-11589 | NBP81 | C-P-CA-121 | priyajoshi | 10 | Closed | Fully Automated | 2015-10-05 | C-P-CA-121 | TRUE
PAS5_NBP | DEMO-11588 | NBP79 | C-P-CA-120 | akonchada | 8 | Closed | Fully Automated | 2015-10-05 | C-P-CA-120 | TRUE
PAS5_NBP | DEMO-11587 | NBP75 | C-H-CA-119 | mapendyala | 8 | Test in Pilot | Fully Automated | 2015-11-02 | #N/A | FALSE
PAS5_NBP | DEMO-11586 | NBP73 | C-H-CA-118 | pavirao | 2 | Closed | Fully Automated | 2015-10-05 | C-H-CA-118 | TRUE
PAS5_NBP | DEMO-11585 | NBP72 | C-H-CA-117 | sbahl | 4 | Closed | Fully Automated | 2015-10-05 | C-H-CA-117 | TRUE
PAS5_NBP | DEMO-11584 | NBP66 | C-H-CA-116 | priyajoshi | 5 | Closed | Fully Automated | 2015-10-05 | C-H-CA-116 | TRUE
PAS5_NBP | DEMO-11583 | NBP64 | C-H-CA-115 | sheela | 5 | Closed | Fully Automated | 2015-10-05 | C-H-CA-115 | TRUE
PAS5_NBP | DEMO-11582 | NBP40 | C-H-CA-114 | pavirao | 2 | Closed | Fully Automated | 2015-10-05 | C-H-CA-114 | TRUE
PAS5_NBP | DEMO-11581 | NBP16 | C-H-CA-113 | dnasikkar | 3 | Script Review | Fully Automated | 2015-11-02 | #N/A | FALSE
PAS5_NBP | DEMO-11580 | NBP53 | C-H-CA-112 | sbahl | 1 | Closed | Fully Automated | 2015-10-05 | C-H-CA-112 | TRUE
PAS5_NBP | DEMO-11579 | NBP50 | C-H-CA-111 | chitranjan | 4 | Closed | Fully Automated | 2015-10-05 | C-H-CA-111 | TRUE
PAS5_NBP | DEMO-11578 | NBP34 | C-H-CA-110 | mapendyala | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-110 | TRUE
PAS5_NBP | DEMO-11577 | NBP28 | C-H-CA-109 | sheela | 2 | Closed | Fully Automated | 2015-10-05 | C-H-CA-109 | TRUE
PAS5_NBP | DEMO-11576 | NBP29 | C-H-CA-108 | kbindusree | 4 | Closed | Fully Automated | 2015-10-05 | C-H-CA-108 | TRUE
PAS5_NBP | DEMO-11575 | NBP39 | C-H-CA-107 | kbindusree | 2 | Closed | Fully Automated | 2015-10-05 | C-H-CA-107 | TRUE
PAS5_NBP | DEMO-11574 | NBP42 | C-H-CA-106 | chitranjan | 2 | Closed | Fully Automated | 2015-10-05 | C-H-CA-106 | TRUE
PAS5_NBP | DEMO-11573 | NBP41 | C-H-CA-105 | sheela | 2 | Closed | Fully Automated | 2015-10-05 | C-H-CA-105 | TRUE
PAS5_NBP | DEMO-11572 | NBP35 | C-H-CA-104 | sheela | 1 | Closed | Fully Automated | 2015-10-05 | C-H-CA-104 | TRUE
PAS5_NBP | DEMO-11571 | NBP15 | C-H-CA-103 | sheela | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-103 | TRUE
PAS5_NBP | DEMO-11570 | NBP44 | C-H-CA-102 | chitranjan | 5 | Closed | Fully Automated | 2015-10-05 | C-H-CA-102 | TRUE
PAS5_NBP | DEMO-11569 | NBP37 | C-P-CA-100 | akonchada | 5 | Closed | Partial - Non Integration | 2015-10-05 | C-P-CA-100 | TRUE
PAS5_NBP | DEMO-11568 | NBP46 | C-H-CA-099 | mtare | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-099 | TRUE
PAS5_NBP | DEMO-11567 | NBP30 | C-H-CA-098 | kbindusree | 4 | Passed w/defect | Partial - Non Integration | 2015-10-05 | C-H-CA-098 | TRUE
PAS5_NBP | DEMO-11566 | NBP51 | C-H-CA-097 | sheela | 6 | Blocked |  |  | #N/A | FALSE
PAS5_NBP | DEMO-11565 | NBP38 | C-H-CA-096 | chitranjan | 1 | Closed | Fully Automated | 2015-10-05 | C-H-CA-096 | TRUE
PAS5_NBP | DEMO-11564 | NBP14 | C-H-CA-095 | pavirao | 6 | Closed | Fully Automated | 2015-10-05 | C-H-CA-095 | TRUE
PAS5_NBP | DEMO-11563 | NBP70 | C-H-CA-094 | chitranjan | 7 | Closed | Fully Automated | 2015-10-05 | C-HO-HO6-CA-094 | TRUE
PAS5_NBP | DEMO-11562 | NBP69 | C-H-CA-093 | sheela | 11 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-093 | TRUE
PAS5_NBP | DEMO-11561 | NBP67 | C-H-CA-092 | pavirao | 5 | Closed | Fully Automated | 2015-10-05 | C-H-CA-092 | TRUE
PAS5_NBP | DEMO-11560 | NBP24 | C-H-CA-091 | chitranjan | 6 | Closed | Fully Automated | 2015-10-05 | C-H-CA-091 | TRUE
PAS5_NBP | DEMO-11559 | NBP12 | C-H-CA-090 | rajashekar | 3 | Closed | Fully Automated | 2015-10-05 | C-H-CA-090 | TRUE
PAS5_NBP | DEMO-11558 | NBP48 | C-H-CA-089 | mtare | 9 | Passed w/defect | Partial - Non Integration | 2015-10-05 | C-H-CA-089 | TRUE
PAS5_NBP | DEMO-11557 | NBP68 | C-H-CA-088 | mtare | 7 | Passed w/defect | Fully Automated | 2015-10-05 | C-H-CA-088 | TRUE
PAS5_NBP | DEMO-11556 | NBP58 | C-H-CA-087 | priyajoshi | 6 | Passed w/defect | Fully Automated | 2015-10-05 | C-H-CA-087 | TRUE
PAS5_NBP | DEMO-11555 | NBP63 | C-H-CA-086 | mapendyala | 1 | Closed | Fully Automated | 2015-10-05 | C-H-CA-086 | TRUE
PAS5_NBP | DEMO-11554 | NBP62 | C-H-CA-085 | priyajoshi | 1 | Closed | Fully Automated | 2015-10-05 | C-H-CA-085 | TRUE | 2015-11-06
PAS5_NBP | DEMO-11553 | NBP61 | C-H-CA-084 | sbahl | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-084 | TRUE
PAS5_NBP | DEMO-11552 | NBP59 | C-H-CA-083 | sbahl | 6 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-083 | TRUE
PAS5_NBP | DEMO-11551 | NBP56 | C-H-CA-082 | priyajoshi | 3 | Closed | Fully Automated | 2015-10-05 | C-H-CA-082 | TRUE
PAS5_NBP | DEMO-11549 | NBP52 | C-H-CA-080 | priyajoshi | 2 | Closed | Fully Automated | 2015-10-05 | C-H-CA-080 | TRUE
PAS5_NBP | DEMO-11548 | NBP57 | C-H-CA-079 | jidasgupta | 2 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-079 | TRUE
PAS5_NBP | DEMO-11547 | NBP47 | C-H-CA-078 | mtare | 5 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-078 | TRUE
PAS5_NBP | DEMO-11546 | NBP13 | C-H-CA-077 | jidasgupta | 4 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-077 | TRUE
PAS5_NBP | DEMO-11545 | NBP3 | C-H-CA-076 | mtare | 4 | Closed | Fully Automated | 2015-10-05 | C-H-CA-076 | TRUE
PAS5_NBP | DEMO-11544 | NBP11 | C-H-CA-074 | jidasgupta | 5 | Closed | Fully Automated | 2015-10-05 | C-H-CA-074 | TRUE
PAS5_NBP | DEMO-11543 | NBP10 | C-H-CA-075 | mtare | 3 | Closed | Fully Automated | 2015-10-05 | C-H-CA-075 | TRUE
PAS5_NBP | DEMO-11542 | NBP8 | C-H-CA-073 | sbahl | 4 | Closed | Fully Automated | 2015-10-05 | C-H-CA-073 | TRUE
PAS5_NBP | DEMO-11541 | NBP7 | C-H-CA-072 | pavirao | 4 | Closed | Fully Automated | 2015-10-05 | C-H-CA-072 | TRUE
PAS5_NBP | DEMO-11540 | NBP65 | C-H-CA-071 | chitranjan | 1 | Closed | Fully Automated | 2015-10-05 | C-H-CA-071 | TRUE
PAS5_NBP | DEMO-11539 | NBP60 | C-H-CA-070 | pavirao | 7 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-070 | TRUE
PAS5_NBP | DEMO-11538 | NBP18 | C-H-CA-069 | priyajoshi | 3 | Closed | Fully Automated | 2015-10-05 | C-H-CA-069 | TRUE
PAS5_NBP | DEMO-11537 | NBP36 | C-H-CA-068 | akonchada | 5 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-068 | TRUE
PAS5_NBP | DEMO-11536 | NBP33 | C-H-CA-067 | mapendyala | 6 | Passed w/defect | Partial - Non Integration | 2015-10-05 | C-H-CA-067 | TRUE
PAS5_NBP | DEMO-11535 | NBP32 | C-H-CA-066 | rajashekar | 1 | Closed | Fully Automated | 2015-10-05 | C-H-CA-066 | TRUE
PAS5_NBP | DEMO-11534 | NBP31 | C-H-CA-065 | chitranjan | 3 | Closed | Fully Automated | 2015-10-05 | C-H-CA-065 | TRUE
PAS5_NBP | DEMO-11533 | NBP27 | C-H-CA-064 | rajashekar | 5 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-064 | TRUE
PAS5_NBP | DEMO-11532 | NBP26 | C-P-CA-063 | mtare | 4 | Passed w/defect | Fully Automated | 2015-10-05 | C-P-CA-063 | TRUE
PAS5_NBP | DEMO-11531 | NBP25 | C-H-CA-062 | sbahl | 4 | Closed | Fully Automated | 2015-10-05 | C-H-CA-062 | TRUE
PAS5_NBP | DEMO-11530 | NBP23 | C-H-CA-061 | sheela | 3 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-061 | TRUE
PAS5_NBP | DEMO-11529 | NBP22 | C-H-CA-060 | sbahl | 1 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-060 | TRUE
PAS5_NBP | DEMO-11528 | NBP21 | C-H-CA-059 | akonchada | 5 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-059 | TRUE
PAS5_NBP | DEMO-11527 | NBP20 | C-H-CA-058 | pavirao | 4 | Closed | Fully Automated | 2015-10-05 | C-H-CA-058 | TRUE
PAS5_NBP | DEMO-11526 | NBP19 | C-H-CA-057 | mtare | 4 | Closed | Partial - Non Integration | 2015-10-05 | C-H-CA-057 | TRUE
PAS5_NBP | DEMO-13300 | NBP9 | #REF! | chitranjan | 2 | Closed | Fully Automated |  | #N/A | FALSE
PAS5_NBP | DEMO-11550 | NBP55 | #REF! | akonchada | 3 | Closed | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17649 | CA-CP-100 |  | rajashekar | 16 | Update Script | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17648 | CA-CP-101 |  | mapendyala | 9 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17647 | CA-CP-103 |  | sbahl | 13 | Blocked |  |  | #N/A | FALSE
CA_CP | DEMO-17646 | CA-CP-105 |  | jidasgupta | 10 | Script Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17645 | CA-CP-106 |  | pavirao | 17 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17644 | CA-CP-107 |  | sheela | 12 | Ready for Review | Partial - Non Integration |  | #N/A | FALSE
CA_CP | DEMO-17643 | CA-CP-109 |  | kbindusree | 15 | Blocked |  |  | #N/A | FALSE
CA_CP | DEMO-17642 | CA-CP-110 |  | kbindusree | 18 | Develop Script |  |  | #N/A | FALSE
CA_CP | DEMO-17641 | CA-CP-111 |  | Zoheb Ahmed Banikar | 8 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17640 | CA-CP-112 |  | achbhatia | 15 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17639 | CA-CP-113 |  | kbindusree | 10 | Update Script | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17638 | CA-CP-114 |  | mtare | 8 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17637 | CA-CP-115 |  | priyajoshi | 5 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17636 | CA-CP-116 |  | sheela | 7 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17635 | CA-CP-118 |  | mapendyala | 12 | Blocked |  |  | #N/A | FALSE
CA_CP | DEMO-17634 | CA-CP-121 |  | sheela | 2 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17633 | CA-CP-104 |  | akonchada | 11 | Blocked | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17632 | CA-CP-108 |  | chitranjan | 11 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17631 | CA-CP-120 |  | sbahl | 11 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17630 | CA-CP-102 |  | Ruchir Agarwal | 18 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17629 | CA-CP-119 |  | Zoheb Ahmed Banikar | 4 | Blocked |  |  | #N/A | FALSE
CA_CP | DEMO-17628 | CA-CP-117 |  | chitranjan | 14 | Blocked |  |  | #N/A | FALSE
CA_CP | DEMO-17627 | CA-CP-122 |  | Bhushan | 10 | Ready for Review | Fully Automated |  | #N/A | FALSE
CA_CP | DEMO-17626 | CA-CP-123 |  | chitranjan | 10 | Blocked |  |  | #N/A | FALSE
PAS2,3,4 | DEMO-18044 | T-AU-SS-CL-301 |  | priyajoshi | 1 | Closed | Partial - Non Integration | 2015-10-05 | T-AU-SS-CL-301 | TRUE | 2015-11-06
PAS2,3,4 | DEMO-18043 | F-AU-SS-CL-300 |  | priyajoshi | 4 | Closed | Fully Automated | 2015-10-05 | F-AU-SS-CL-300 | TRUE | 2015-11-06
PAS2,3,4 | DEMO-17876 | F-HO-SS-CL-303 |  | Bhushan | 1 | Deferred | Manual - Integration |  | #N/A | FALSE
PAS2,3,4 | DEMO-17875 | F-HO-SS-CL-302 |  | Bhushan | 1 | Deferred | Manual - Integration |  | #N/A | FALSE
PAS2,3,4 | DEMO-17874 | F-HO-SS-CO-306 |  | Rohan Soni | 1 | Closed | Fully Automated | 2015-10-05 | F-HO-SS-CO-306 | TRUE
PAS2,3,4 | DEMO-17873 | T-PU-SS-CCL-311 |  | G, Sowjanya | 1 | Closed | Fully Automated | 2015-10-05 | T-PU-SS-CCL-311 | TRUE
PAS2,3,4 | DEMO-17872 | T-HO-SS-CL-309 |  | Nikhil Save | 6 | Ready for Build | Partial - Non Integration | 2015-10-12 | #N/A | FALSE
PAS2,3,4 | DEMO-17871 | T-HO-SS-VA-308 |  | Monica Jettipalle | 1 | Closed | Fully Automated | 2015-10-05 | T-HO-SS-VA-308 | TRUE
PAS2,3,4 | DEMO-17870 | T-HO-SS-PA-307 |  | sheela | 1 | Closed | Fully Automated | 2015-10-05 | T-HO-SS-PA-307 | TRUE
PAS2,3,4 | DEMO-19323 | C-P-NewBusiness-CA-933 |  | G, Sowjanya | 4 | Ready for Build | Fully Automated | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-19322 | T-PU-SS-CL-305 |  | Monica Jettipalle | 2 | Closed | Fully Automated | 2015-10-05 | T-PU-SS-CL-305 | TRUE
PAS05_Pilot | DEMO-18485 | C-H-Inspection-CA-1619 |  | G, Sowjanya | 2 | Closed | Fully Automated | 2015-10-05 | C-H-Inspection-CA-1619 | TRUE
PAS2,3,4 | DEMO-19856 | C-HO-HO3-CA-322 |  | G, Sowjanya | 6 | Update Script | Fully Automated | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-19855 | C-HO-HO3-CA-321 |  | Nikhil Save | 6 | Ready for Build | Fully Automated | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-19854 | C-HO-SS-VA-314 |  | Zoheb Ahmed Banikar | 4 | Test in Pilot | Fully Automated | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-19830 | C-HO-SS-NJ-316 |  | Monica Jettipalle | 4 | Ready for Build | Partial - Non Integration | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-19829 | C-HO-HO4-CL-312 |  | Monica Jettipalle | 3 | Blocked | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-19828 | C-PU-PUP-CL-313 |  | Rohan Soni | 3 | Ready for Build | Fully Automated | 2015-10-12 | C-PU-PUP-CL-313 | TRUE
PAS2,3,4 | DEMO-19827 | C-P-Endorsement-CA-904 |  | Nikhil Save | 4 | Ready for Build | Fully Automated | 2015-10-12 | C-P-Endorsement-CA-904 | TRUE
PAS2,3,4 | DEMO-19568 | C-PU-PUP-CA-326 |  | Zoheb Ahmed Banikar | 4 | Ready for Build | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-19857 | C-HO-HO3-CA-323 |  | Rohan Soni | 5 | Develop Script | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-20374 | T-HO-HO3-CL-310 |  | Nikhil Save | 1 | Ready for Build | Partial - Non Integration | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20256 | C-HO-HO3-CL-324 |  | achbhatia | 6 | Update Script | Partial - Non Integration | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-20255 | C-HO-HO6-CL-330 |  | sheela | 3 | Closed | Partial - Non Integration | 2015-10-18 | C-HO-HO6-CL-330 | TRUE | 2015-11-06
PAS2,3,4 | DEMO-20249 | C-HO-SS-PA-319 |  | sbahl | 2 | Update Script | Fully Automated | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-20247 | C-HO-SS-NJ-317 |  | rajashekar | 2 | Update Script | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20246 | C-PU-SS-PA-318 |  | mapendyala | 2 | Test in Pilot | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20464 | F-HO-DP3-CO-330 |  | Nikhil Save | 2 | Ready for Build | Fully Automated | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-20373 | C-PU-PUP-AZ-336 |  | Rohan Soni | 5 | Closed | Partial - Non Integration | 2015-10-18 | C-PU-PUP-AZ-336 | TRUE | 2015-11-06
PAS2,3,4 | DEMO-20372 | C-HO-DP3-AZ-334 |  | sbahl | 4 | Closed | Partial - Non Integration | 2015-11-02 | C-HO-DP3-AZ-334 | TRUE | 2015-11-06
PAS2,3,4 | DEMO-20371 | C-PU-PUP-CL-331 |  | Ruchir Agarwal | 3 | Closed | Partial - Non Integration | 2015-10-23 | C-PU-PUP-CL-331 | TRUE | 2015-11-06
PAS2,3,4 | DEMO-20369 | C-HO-HO6-AZ-335 |  | achbhatia | 5 | Test in Pilot | Partial - Non Integration | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20368 | C-HO-HO4-CL-325 |  | Monica Jettipalle | 5 | Closed | Partial - Non Integration | 2015-10-18 | C-HO-HO4-CL-325 | TRUE | 2015-11-06
PAS2,3,4 | DEMO-20367 | C-HO-HO4-AZ-333 |  | kbindusree | 4 | Update Script | Partial - Non Integration | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-20366 | C-HO-HO3-AZ-332 |  | sheela | 4 | Update Script | Partial - Non Integration | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20363 | C-HO-DP3-CL-325 |  | chitranjan | 5 | Update Script | Partial - Non Integration | 2015-10-18 | #N/A | FALSE
PAS2,3,4 | DEMO-20341 | C-HO-HO3-CO-328 |  | mtare | 3 | Test in Pilot | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20336 | C-PU-SS-VA-315 |  | achbhatia | 2 | Test in Pilot | Partial - Non Integration | 2015-11-02 | #N/A | FALSE
PAS2,3,4 | DEMO-20496 | C-HO-HO3-CO-329 |  | mapendyala | 4 | Ready for Build | Partial - Non Integration | 2015-11-02 | #N/A | FALSE
PAS2,3,4 | DEMO-20493 | C-HO-HO3-UT-341 |  | Rohan Soni | 1 | Ready for Build | Fully Automated | 2015-11-02 | #N/A | FALSE
PAS2,3,4 | DEMO-20492 | F-HO-SS-CO-363 |  | Rohan Soni | 3 | Closed | Fully Automated | 2015-11-02 | F-HO-SS-CO-363 | TRUE | 2015-11-18
PAS2,3,4 | DEMO-20491 | C-HO-SS-NJ-320 |  | sbahl | 2 | Test in Pilot | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20490 | C-HO-SS-NJ-360 |  | Ruchir Agarwal | 1 | Ready for Build | Fully Automated | 2015-11-02 | #N/A | FALSE
PAS2,3,4 | DEMO-20489 | C-HO-HO3-CA-345 |  | Monica Jettipalle | 2 | Ready for Build | Fully Automated | 2015-11-02 | #N/A | FALSE
PAS2,3,4 | DEMO-20488 | C-HO-HO3-UT-344 |  | G, Sowjanya | 1 | Ready for Build | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20487 | C-HO-HO3-UT-343 |  | Monica Jettipalle | 1 | Ready for Build | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20486 | C-HO-HO3-UT-342 |  | kbindusree | 1 | Update Script | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20485 | C-HO-HO3-UT-340 |  | achbhatia | 1 | Update Script | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20484 | C-HO-SS-NJ-362 |  | Nikhil Save | 2 | Closed | Fully Automated | 2015-10-23 | C-HO-SS-NJ-362 | TRUE | 2015-11-06
PAS2,3,4 | DEMO-20483 | C-HO-HO3-UT-339 |  | rajashekar | 1 | Ready for Build | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20482 | C-HO-HO3-UT-338 |  | chitranjan | 1 | Ready for Build | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20481 | C-HO-HO3-UT-337 |  | sheela | 1 | Ready for Build | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20896 | T-HO-SS-CL-350 |  | G, Sowjanya | 3 | Ready for Build | Fully Automated | 2015-10-23 | #N/A | FALSE
PAS2,3,4 | DEMO-20975 | F-HO-HO3-CO-352 |  | Zoheb Ahmed Banikar | 3 | Closed | Fully Automated | 2015-10-23 | F-HO-HO3-CO-352 | TRUE | 2015-11-18
PAS2,3,4 | DEMO-21043 | C-PU-PUP-CO-353 |  | Monica Jettipalle | 2 | Test in Pilot | Fully Automated | 2015-11-02 | #N/A | FALSE
PAS2,3,4 | DEMO-21042 | T-PU-SS-CL-351 |  | G, Sowjanya | 2 | Update Script | Partial - Non Integration | 2015-11-02 | #N/A | FALSE
pas6_nbp | DEMO-21538 | NBP156 | C-HO-HO3-CA-200 | Monica Jettipalle | 2 | Ready for Review | Fully Automated |  | #N/A | FALSE
pas6_nbp | DEMO-21537 | NBP157 | C-HO-HO3-CL-201 | mapendyala | 8 | Ready for Review | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-21417 | F-PU-SS-CL-355 |  | Unassigned | 1 | Open | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-21416 | F-AU-SS-CL-347 |  | dnasikkar | 2 | Ready for Review | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-21415 | C-HO-HO3-CO-327 |  | rajashekar | 5 | Ready for Review | Partial - Non Integration |  | #N/A | FALSE
PAS2,3,4 | DEMO-21414 | C-AU-SS-OR-366 |  | G, Sowjanya | 2 | Develop Script | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-21413 | C-AU-SS-OR-348 |  | Monica Jettipalle | 2 | Develop Script | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-21412 | C-AU-SS-NV-365 |  | Monica Jettipalle | 2 | Ready for Review | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-21411 | C-AU-SS-CL-364 |  | chitranjan | 8 | Develop Script | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-21410 | C-AU-SS-CL-354 |  | chitranjan | 3 | Develop Script | Fully Automated |  | #N/A | FALSE
PAS2,3,4 | DEMO-21409 | C-AU-CAS-CA-346 |  | Zoheb Ahmed Banikar | 4 | Develop Script | Fully Automated |  | #N/A | FALSE