## Hybrid Conversion Status
| Legend for Development Status |  |  |  | RCA | Executed scripts that require RCA effort
| Pending | Scripts either blocked by defects or lagging in development |  |  | In Progress | Scripts due this week
| Complete | Scripts developed |  |  | Not Started | Target date is TBD
[5 empty] | Passed with Defect | Script failed only due to the defect
[5 empty] | Failed due to DocGen | Script failed only due to DCS latency
# | Track | State | Scenario/Pattern ID | Test ID | AC count | Developer | States | Completion | Blocking Defects | AC's Blocked | Nightly Execution Status - 18-Apr | Nightly Execution Status - 19-Apr | Nightly Execution Status - 20-Apr | RCA Status | Date | Failure Reason
1 | Capping | DE | C-AU-SS-HCCAP-CL-001 | C-AU-SS-HCCAP-DE-001 | 6 | Anusha | 1 | 6 | 37494 |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
2 | Capping | MD | C-AU-SS-HCCAP-CL-001 | C-AU-SS-HCCAP-MD-001 | 6 | Anusha | 1 | 6 |  |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
3 | Capping | NJ | C-AU-SS-HCCAP-CL-001 | C-AU-SS-HCCAP-NJ-001 | 6 | Anusha | 1 | 6 |  |  | Failed | Failed | Passed | Closed | 2016-04-20 | Cascading effect due to previous script fix
4 | Capping | PA | C-AU-SS-HCCAP-CL-001 | C-AU-SS-HCCAP-PA-001 | 6 | Anusha | 1 | 6 |  |  | Failed | Failed | Passed | Closed | 2016-04-20 | Cascading effect due to previous script fix
5 | Capping | VA | C-AU-SS-HCCAP-CL-001 | C-AU-SS-HCCAP-VA-001 | 6 | Anusha | 1 | 6 |  |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
6 | Capping | DE | C-AU-SS-HCCAP-CL-006 | C-AU-SS-HCCAP-DE-006 | 2 | Anusha | 1 | 2 |  |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
7 | Capping | MD | C-AU-SS-HCCAP-CL-006 | C-AU-SS-HCCAP-MD-006 | 2 | Anusha | 1 | 2 |  |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
8 | Capping | NJ | C-AU-SS-HCCAP-CL-006 | C-AU-SS-HCCAP-NJ-006 | 2 | Anusha | 1 | 2 |  |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
9 | Capping | PA | C-AU-SS-HCCAP-CL-006 | C-AU-SS-HCCAP-PA-006 | 2 | Anusha | 1 | 2 |  |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
10 | Capping | VA | C-AU-SS-HCCAP-CL-006 | C-AU-SS-HCCAP-VA-006 | 2 | Anusha | 1 | 2 |  |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
11 | Capping | DE | C-AU-SS-HCCAP-CL-010 | C-AU-SS-HCCAP-DE-010 | 14 | Anusha | 1 | 14 | 38349 38113 |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
12 | Capping | MD | C-AU-SS-HCCAP-CL-010 | C-AU-SS-HCCAP-MD-010 | 14 | Anusha | 1 | 14 | 38349 38113 |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
13 | Capping | NJ | C-AU-SS-HCCAP-CL-010 | C-AU-SS-HCCAP-NJ-010 | 14 | Anusha | 1 | 14 | 38349 38113 |  | Failed | Failed | Passed | Closed | 2016-04-20 | Removed auto pay. Need to re-run
14 | Capping | PA | C-AU-SS-HCCAP-CL-010 | C-AU-SS-HCCAP-PA-010 | 14 | Anusha | 1 | 14 | 38349 38113 38115 38117 |  | Failed | Passed | Passed | Closed | 2016-04-19
15 | Capping | VA | C-AU-SS-HCCAP-CL-010 | C-AU-SS-HCCAP-VA-010 | 14 | Anusha | 1 | 14 | 38349 38113 |  | Passed | Passed | Passed | Closed | 2016-04-18 | Closed
16 | Conversions | PA | C-AU-SS-HC-PA-001 |  | 12 | Vaibhav | 1 | 12 |  |  | Failed | Failed | Passed | Closed | 2016-04-20 | Removed auto pay. Need to re-run
17 | Conversions | PA | C-AU-SS-HC-PA-002 |  | 14 | Vaibhav | 1 | 14 | 38736 37837 |  | Failed | Failed | Passed with Defect | Closed | 2016-04-20 | internal error 500
18 | Conversions | PA | C-AU-SS-HC-PA-003 |  | 8 | Vaibhav | 1 | 8 | 38736 |  | Failed | Failed | Passed with Defect | Closed | 2016-04-20 | internal error 500
19 | Conversions | NJ | C-AU-SS-HC-NJ-01 |  | 8 | Anusha | 1 | 8 |  |  | Failed | Failed | Passed | Closed | 2016-04-20 | Removed payment at R+5 as policy is on Auto pay. Has commented code. Later added code to pay bill at R thru recurring job.Removed commented code
20 | Conversions | VA | C-AU-SS-HC-VA-001 |  | 12 | Anusha | 1 | 12 |  |  | Failed | Failed | Failed due to DocGen | Closed | 2016-04-20 | DocGen failure/files not found
21 | Conversions | VA | C-AU-SS-HC-VA-002 |  | 20 | Anusha | 1 | 20 | 37809 |  | Failed | Failed | Passed | Closed | 2016-04-20 | RCA
22 | Conversions | VA | C-AU-SS-HC-VA-003 |  | 12 | Keerthi | 1 | 12 | 37749 |  | Failed | Failed | Failed due to DocGen | Closed | 2016-04-20 | decline link is not coming.Has commented code. Later removed Auto pay
23 | Conversions | CL | C-AU-SS-HC-CL-001 |  | 18 | Anusha | 1 | 18 |  |  | Failed due to DocGen only | Passed | Passed | Closed | 2016-04-19
24 | Conversions | CL | C-AU-SS-HC-CL-002 |  | 7 | Anusha | 1 | 7 |  |  | Failed | Failed | Passed | Closed | 2016-04-20 | Environment issue-RenewalImageRatingAsyncTaskJob not found
25 | Conversions | MD | C-AU-SS-HC-MD-001 |  | 10 | Vaibhav | 1 | 10 |  |  | Failed due to DocGen only | Passed | Passed | Closed | 2016-04-19 | Closed
26 | Conversions | MD | C-AU-SS-HC-MD-002 |  | 15 | Keerthi | 1 | 15 | 38736 37809 |  | Failed | Failed | Passed with Defect | Closed | 2016-04-20 | internal error 500
28 | Conversions | DE | C-AU-SS-HC-DE-001 |  | 11 | Keerthi | 1 | 11 | 37810 |  | Failed | Failed | Passed | Closed | 2016-04-20 | RCA
29 | Conversions | DE | C-AU-SS-HC-DE-002 |  | 3 | Keerthi | 1 | 3 |  |  | Failed | Failed | Passed | Closed | 2016-04-20 | RCA
Milestone#3
2016-04-18 | http://dev2aaa3jnk301.eqxdev.exigengroup.com:8080/job/AAA-Deloitte_Calendar_ConversionCapping_PEF/80/HTML_Report/
2016-04-19 | http://dev2aaa3jnk301.eqxdev.exigengroup.com:8080/job/AAA-Deloitte_Calendar_ConversionCapping_PEF/82/HTML_Report/
http://dev2aaa3jnk301.eqxdev.exigengroup.com:8080/job/AAA-Deloitte_Calendar_ConversionCapping_PEF/84/HTML_Report/
2016-04-20 | http://dev2aaa3jnk301.eqxdev.exigengroup.com:8080/job/AAA-Deloitte_Calendar_ConversionCapping_PEF/85/HTML_Report/
http://dev2aaa3jnk301.eqxdev.exigengroup.com:8080/job/AAA-Deloitte_Calendar_ConversionCapping_PEF/86/HTML_Report/
http://dev2aaa3jnk301.eqxdev.exigengroup.com:8080/job/AAA-Deloitte_Calendar_ConversionCapping_PEF/87/HTML_Report/
http://dev2aaa3jnk301.eqxdev.exigengroup.com:8080/job/AAA-Deloitte_Calendar_ConversionCapping_PEF/90/HTML_Report/
2016-04-26 | http://dev2aaa3jnk301.eqxdev.exigengroup.com:8080/job/AAA-Deloitte_Calendar_ConversionCapping_PEF/94/HTML_Report/
Note on F31: Konchada, Anusha: Count has deecreased from 11 to 9. design underwent changes Making the count 7 as home baning indicator is out of scope