## Burndown
Automation Plan
Milestones |  |  | Revised Target (if any) | 2016-01-25 | 2016-02-01 | 2016-02-08 | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-04-01
|  |  |  | 2016-01-29 | 2016-02-05 | 2016-02-12 | 2016-02-19 | 2016-02-26 | 2016-03-04 | 2016-03-11 | 2016-03-18 | 2016-03-25 | 2016-04-01
PAS 8 Capping | NJ,PA,MD,DE,VA | 15 | 22 | 2016-01-29: 0; 2016-02-05: 2; 2016-02-12: 3; 2016-02-19: 5; 2016-02-26: 5
Conversions | NJ [1] | 8 | 158 | 2016-02-19: 30; 2016-02-26: 30; 2016-03-04: 45; 2016-03-11: 30; 2016-03-18: 23
| PA [3] | 34
| MD [3] | 29
| VA [3] | 44
| DE [2] | 14
| CL [2] | 29
Weekly |  |  |  | 0 | 2 | 3 | 35 | 35 | 45 | 30 | 23 | 0 | 0
Cumulative |  | 173 |  | 0 | 2 | 5 | 40 | 75 | 120 | 150 | 173 | 173 | 173
Resource Plan
Plan |  |  |  | 2016-01-29 | 2016-02-05 | 2016-02-12 | 2016-02-19 | 2016-02-26 | 2016-03-04 | 2016-03-11 | 2016-03-18 | 2016-03-25 | 2016-04-01
PAS 8 Capping | bar: 2016-01-29 to 2016-02-26
Conversions |  |  |  | 2016-02-19: 2; 2016-02-26: 2; 2016-03-04: 3; 2016-03-11: 3; 2016-03-18: 1
Planned Resource Counts |  |  |  | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 1 | 0 | 0
Actual Numbers
Milestones |  |  | Revised Target (if any) | 2016-01-25 | 2016-02-01 | 2016-02-08 | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-04-01
|  |  |  | 2016-01-29 | 2016-02-05 | 2016-02-12 | 2016-02-19 | 2016-02-26 | 2016-03-04 | 2016-03-11 | 2016-03-18 | 2016-03-25 | 2016-04-01
PAS 8 Capping | NJ,PA,MD,DE,VA | 15 |  | 2016-01-29: 0; 2016-02-05: 2; 2016-02-12: 3; 2016-02-19: 5; 2016-02-26: 5
Conversions (180 Acs or ) | NJ | 1 |  | 2016-02-19: 5; 2016-02-26: 12; 2016-03-04: 58
| PA | 3
| MD | TBD
| DE | TBD
| VA | TBD
Weekly |  |  |  | 0 | 2 | 3 | 10 | 17 | 58 | 0 | 0 | 0 | 0
Cumulative |  | 19 |  | 0 | 2 | 5 | 15 | 32 | 90 | 90 | 90 | 90 | 90
Assumptions
1 |  | The target VC count is tentative as per the recent communication from Design team. It is subject to change
2 |  | The no. of resources starting 3/4 (the week ending 4th March) doesn’t include me (Anusha), I might have other operational activities to handle
3 |  | Only AZ state under CL has been considered for conversions(PAS7 design + PAS8 design). Yet to know if the CL tests are to run for other states as well.
4 |  | The efforts per VC doesn’t account for handling script failures during pilot/ Nightly or any situation where the scripting might take additional time than expected
5 |  | The effort per VC estimated is such that it goes per tight deadlines per the scheduled end dates.
6 |  | For Conversions, the total VC count for CL has bee approximated based on PAS7 VC count. Refer tab VC_Count
7 |  | All the folks currently working on Capping and Conversions will continue until 4/1
8 |  | This plan doesn’t consider any design/ technical issues that might be encountered during Automation
9 |  | We will have seamless delivery of PAS8 scenario design from design team
10 |  | All firm holidays until 1st,April 2016 only have been factored in
11 |  | Doesn’t factor in unscheduled PTOs.
12 |  | No major system outages/ infrastructure outages are factored in
13 |  | Each person to have 1 dedicated environment/ instance throughout the execution duration.

## WeeklyCounts
[5 empty] | 2016-02-19 | 2016-02-26 | 2016-03-04 |  | 2016-03-11 | 2016-03-18
Track | State | Scenario ID | AC count | Developer | 30 | 30 | 45 | defects | 45
Capping | PA,VA, NJ, DE , MD | C-AU-SS-HCCAP-CL-001 | 6 | Anusha
Capping | PA,VA, NJ, DE , MD | C-AU-SS-HCCAP-CL-006 | 2 | Anusha
Capping | PA,VA, NJ, DE , MD | C-AU-SS-HCCAP-CL-010 | 14 | Anusha
Conversions | PA | C-AU-SS-HC-PA-001 | 12 | Vaibhav |  |  | 12
Conversions | PA | C-AU-SS-HC-PA-002 | 14 | Vaibhav | 3 | 9 |  |  | 1 | 1
Conversions | PA | C-AU-SS-HC-PA-003 | 8 | Vaibhav |  |  |  |  | 5 | 3
Conversions | NJ | C-AU-SS-HC-NJ-01 | 8 | Kshitij | 2 | 3
Conversions | VA | C-AU-SS-HC-VA-001 | 12 | Anusha |  |  | 12
Conversions | VA | C-AU-SS-HC-VA-002 | 20 | Anusha |  |  | 20 | 37809
Conversions | VA | C-AU-SS-HC-VA-003 | 12 | Keerthi |  |  | 12 | 37749
Conversions | CL | C-AU-SS-HC-CL-001 | 18 | Anusha |  |  |  |  | 14 | 4
Conversions | CL | C-AU-SS-HC-CL-002 | 11 | Anusha | [5 empty] | 5
Conversions | MD | C-AU-SS-HC-MD-001 | 10 | Vaibhav | [5 empty] | 7
Conversions | MD | C-AU-SS-HC-MD-002 | 15 | Keerthi |  |  |  | 37809 | 12
Conversions | DE | C-AU-SS-HC-DE-001 | 11 | Keerthi |  |  |  | 37810 | 2 | 9
Conversions | DE | C-AU-SS-HC-DE-002 | 3 | Keerthi | [5 empty] | 3

## Jenkins_results
2016-03-11 |  |  | total | passed | failed
Capping | C-AU-SS-HCCAP-CL-001 | 6 | 30 | 30 | 0
| C-AU-SS-HCCAP-CL-006 | 2 | 10 | 8 | -2
| C-AU-SS-HCCAP-PA-010 | 14 | 14 | 6 | -3
-5
| C-AU-SS-HCCAP-NJ-010 | 14 | 14 | 6 | -3
-5

## QA_status
Build | Date | Target | Complete | Complete % | Passed | Defects | Not yet Run | Failed Total | Failed: Environment | Failed: Script Error | Failed: Analysis in Progress | Defects found on this Build | New Defects on this Build
|  | A = B + G + H | B = D + E | C = B / A | D | E | G | H = J + K + L | J | K | L | M | N
74714 | 2016-03-11 | 68 | 50 | 73.53% | 50 | 0 | 0 | 18 | 8 | 10 | 0 | 0 | 0

## WeeklyTargets
Scenario ID | AC count | Developer | Target- 19th Mar
C-AU-SS-HC-PA-003 | 3 | Vaibhav | 3
C-AU-SS-HC-NJ-01 | 3 | Vaibhav
C-AU-SS-HC-MD-001 | 10 | Vaibhav
C-AU-SS-HC-DE-001 | 9 | keerthi | 9
C-AU-SS-HC-CL-001 | 4 | Anusha | 4
C-AU-SS-HC-CL-002 | 11 | Anusha | 4

## ConversionCounts
Track | State | Scenario ID | AC count | Developer | States | Completion | defects | Blocked
Capping | PA,VA, NJ, DE , MD | C-AU-SS-HCCAP-CL-001 | 6 | Anusha | 5 | 30
Capping | PA,VA, NJ, DE , MD | C-AU-SS-HCCAP-CL-006 | 2 | Anusha | 5 | 10
Capping | PA,NJ | C-AU-SS-HCCAP-CL-010 | 14 | Anusha | 2 | 28
Conversions | PA | C-AU-SS-HC-PA-001 | 12 | Vaibhav |  | 12
Conversions | PA | C-AU-SS-HC-PA-002 | 14 | Vaibhav |  | 13
Conversions | PA | C-AU-SS-HC-PA-003 | 8 | Vaibhav |  | 5
Conversions | NJ | C-AU-SS-HC-NJ-01 | 8 | Kshitij |  | 5
Conversions | VA | C-AU-SS-HC-VA-001 | 12 | Anusha |  | 12
Conversions | VA | C-AU-SS-HC-VA-002 | 20 | Anusha |  | 20 | 37809 | 2
Conversions | VA | C-AU-SS-HC-VA-003 | 12 | Keerthi |  | 12 | 37749
Conversions | CL | C-AU-SS-HC-CL-001 | 18 | Anusha |  | 14
Conversions | CL | C-AU-SS-HC-CL-002 | 11 | Anusha
Conversions | MD | C-AU-SS-HC-MD-001 | 10 | Vaibhav
Conversions | MD | C-AU-SS-HC-MD-002 | 15 | Keerthi |  | 12 | 37809 | 3
Conversions | MD | C-AU-SS-HC-MD-003 | 4 | Keerthi
Conversions | DE | C-AU-SS-HC-DE-001 | 11 | Keerthi |  | 2 | 37810
Conversions | DE | C-AU-SS-HC-DE-002 | 3
Pending
Capping | VA,DE , MD | C-AU-SS-HCCAP-CL-010 | 14 | Anusha | 3 | 42