## REG SCOPE
US ID (RRC ID) | AC/VC ID | State | Regression Scope Y/N | Feature Area | Dev Timeline
MC880-820PA | MC880-820- 01PA | PA | yes | PAS/Forms
MC880-820PA | MC880-820- 02PA | PA | yes | PAS/Forms
MC880-720PA | MC880-720-1PA | PA | No | PAS/Forms
MC880-584PA | MC880-101-01PA | PA | yes | PAS/Forms
MC880-720PA | MC880-720-2PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-3PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-4PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-5PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-6PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-7PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-8PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-9PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-10PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-11PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-12PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-13PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-14PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-15PA | PA | No | PAS/Forms
MC880-720PA | MC880-720-16PA | PA | No | PAS/Forms
MC880-584PA | MC880-584-02PA | PA | No | PAS/Forms
MC880-723PA | MC880-723-01PA | PA | Yes | PAS/Forms
MC880-723PA | MC880-723-02PA | PA | Yes | PAS/Forms
MC880-115PA | MC880-115-01PA | PA | No | PAS/Forms
MC880-115PA | MC880-115-02PA | PA | No | PAS/Forms
MC880-115PA | MC880-115-03PA | PA | No | PAS/Forms
MC880-721PA | MC880-721-01PA | PA | Yes | PAS/Forms
MC880-721PA | MC880-721-02PA | PA | Yes | PAS/Forms
MC880-716PA | MC880-716-01PA | PA | Yes | PAS/Forms
MC880-716PA | MC880-716-02PA | PA | Yes | PAS/Forms
MC880-714PA | MC880-714-01PA | PA | Yes | PAS/Forms
MC880-714PA | MC880-714-02PA | PA | Yes | PAS/Forms
MC880-253PA | MC880-253-01PA | PA | Yes | PAS/Forms
MC880-253PA | MC880-253-02PA | PA | Yes | PAS/Forms
MC880-253PA | MC880-253-03PA | PA | Yes | PAS/Forms
MC880-253DE | MC880-253-01DE | DE | Yes | PAS/Forms
MC880-253DE | MC880-253-02DE | DE | Yes | PAS/Forms
MC880-253DE | MC880-210-03DE | DE | No | PAS/Forms
MC880-253DE | MC880-253-04DE | DE | Yes | PAS/Forms
MC880-253DE | MC880-253-05DE | DE | No | PAS/Forms
MC880-740DE | MC880-740-01DE | DE | Yes | PAS/Forms
MC880-740DE | MC880-740-02DE | DE | Yes | PAS/Forms
MC880-763NY | MC880-763-01NY | NY | Yes | PAS/Forms
MC880-763NY | MC880-763-02NY | NY | Yes | PAS/Forms
MC880-740NY | MC880-740-01NY | NY | Yes | PAS/Forms
MC880-740NY | MC880-740-02NY | NY | Yes | PAS/Forms
MC880-749NY | MC880-749-01NY | NY | Yes | PAS/Forms
MC880-749NY | MC880-749-02NY | NY | Yes | PAS/Forms
MC880-757NY | MC880-757-01NY | NY | Yes | PAS/Forms
MC880-757NY | MC880-757-02NY | NY | Yes | PAS/Forms
090-116CL | 090-116-3CL | CL | Yes | Capping
090-116CL | 090-116-6CL | CL | Yes | Capping
090-116CL | 090-116-7CL | CL | Yes | Capping
090-116CL | 090-116-9CL | CL | Yes | Capping
090-116CL | 090-116-11CL | CL | Yes | Capping
090-116CL | 090-116-12CL | CL | Yes | Capping
090-116CL | 090-116-13CL | CL | Yes | Capping
090-116CL | 090-116-14CL | CL | Yes | Capping
090-116CL | 090-116-16CL | CL | Yes | Capping
090-116CL | 090-116-18CL | CL | Yes | Capping
090-116CL | 090-116-19CL | CL | Yes | Capping
090-116CL | 090-116-20CL | CL | Yes | Capping
090-116CL | 090-116-21CL | CL | Yes | Capping
090-116CL | 090-116-22CL | CL | Yes | Capping
090-116CL | 090-116-23CL | CL | Yes | Capping
090-116CL | 090-116-24CL | CL | Yes | Capping
090-116CL | 090-116-25CL | CL | Yes | Capping
090-116CL | 090-116-26CL | CL | Yes | Capping
090-116CL | 090-116-27CL | CL | Yes | Capping
090-117CL | 090-117-1CL | CL | Yes | Capping
090-117CL | 090-117-2CL | CL | No | Capping
090-600CL | 090-600-1CL | CL | Yes | Capping
090-600CL | 090-600-4CL | CL | Yes | Capping
090-600CL | 090-600-5CL | CL | Yes | Capping
090-600CL | 090-600-6CL | CL | Yes | Capping
090-600CL | 090-600-7CL | CL | Yes | Capping
090-600CL | 090-600-8CL | CL | Yes | Capping
090-600CL | 090-600-9CL | CL | Yes | Capping
090-600CL | 090-600-10CL | CL | Yes | Capping
090-600CL | 090-600-13CL | CL | Yes | Capping
090-600CL | 090-600-14CL | CL | Yes | Capping
090-600CL | 090-600-15CL | CL | Yes | Capping
090-600CL | 090-600-16CL | CL | Yes | Capping
090-600CL | 090-600-17CL | CL | Yes | Capping
090-600CL | 090-600-18CL | CL | Yes | Capping
090-600CL | 090-600-19CL | CL | Yes | Capping
090-600CL | 090-600-20CL | CL | Yes | Capping
090-600CL | 090-600-21CL | CL | Yes | Capping
090-600CL | 090-600-22CL | CL | Yes | Capping
090-601CL | 090-601-1CL | CL | Yes | Capping
090-601CL | 090-601-2CL | CL | Yes | Capping
090-601CL | 090-601-3CL | CL | Yes | Capping
090-601CL | 090-601-4CL | CL | Yes | Capping
090-601CL | 090-601-5CL | CL | Yes | Capping
090-601CL | 090-601-7CL | CL | Yes | Capping
090-601CL | 090-601-8CL | CL | Yes | Capping
090-601CL | 090-601-9CL | CL | Yes | Capping
090-601CL | 090-601-10CL | CL | Yes | Capping
020-240CL | No VC's | CL | No | Capping
MC170-082CL-01 | MC170-082-1CL | CL | No | Manual Conversion
MC170-082CL-01 | MC170-082-2CL | CL | No | Manual Conversion
MC170-082CL-01 | MC170-082-3CL | CL | No | Manual Conversion
MC170-082CL-01 | MC170-082-4CL | CL | No | Manual Conversion
MC080-005CL-01 | MC080-005-1CL | CL | Yes | Manual Conversion
MC080-005CL-01 | MC080-005-2CL | CL | Yes | Manual Conversion
MC080-005CL-01 | MC080-005-3CL | CL | Yes | Manual Conversion
MC080-005CL-01 | MC080-005-4CL | CL | Yes | Manual Conversion
MC020-008CL-01 | MC020-008-01CL | CL | Yes | Manual Conversion
MC020-008CL-01 | MC020-008-02CL | CL | Yes | Manual Conversion
MC020-008CL-01 | MC020-008-03CL | CL | Yes | Manual Conversion
MC020-008CL-01 | MC020-008-04CL | CL | Yes | Manual Conversion
MC130-383CL-01 | MC130-383-1CL | CL | Yes | Manual Conversion
MC130-383CL-01 | MC130-383-2CL | CL | Yes | Manual Conversion
MC130-383CL-01 | MC130-383-3CL | CL | Yes | Manual Conversion
MC100-125CL-01 | MC100-125-1 CL | CL | No | Manual Conversion
MC880-254NY | MC880-254-01NY | NY | Yes | PAS/Forms
MC880-254NY | MC880-254-02NY | NY | Yes | PAS/Forms
MC880-254NY | MC880-254-03NY | NY | Yes | PAS/Forms
MC880-254NY | MC880-254-04NY | NY | Yes
MC880-254NY | MC880-254-05NY | NY | Yes
MC880-756NY | MC880-756-01NY | NY | Yes | PAS/Forms
MC880-756NY | MC880-756-02NY | NY | Yes | PAS/Forms
MC880-881PA | MC880-881-01PA | PA | Yes | PAS/Forms
MC880-881PA | MC880-881-02PA | PA | Yes | PAS/Forms
MC880-881PA | MC880-881-03PA | PA | No | PAS/Forms
MC880-881PA | MC880-881-04PA | PA | Yes | PAS/Forms
MC880-881PA | MC880-881-05PA | PA | Yes | PAS/Forms
MC880-881PA | MC880-881-06PA | PA | No | PAS/Forms
MC880-881PA | MC880-881-07PA | PA | No | PAS/Forms
MC880-881PA | MC880-881-08PA | PA | No | PAS/Forms
MC880-882DE | MC880-882-01DE | DE | Yes | PAS/Forms
MC880-882DE | MC880-882-02DE | DE | Yes | PAS/Forms
MC880-882DE | MC880-882-03DE | DE | No | PAS/Forms
MC880-882DE | MC880-882-04DE | DE | Yes | PAS/Forms
MC880-882DE | MC880-882-05DE | DE | Yes | PAS/Forms
MC880-882DE | MC880-882-06DE | DE | No | PAS/Forms
MC880-882DE | MC880-882-07DE | DE | No | PAS/Forms
MC880-882DE | MC880-882-08DE | DE | No | PAS/Forms
MC700-803CL-01 | MC700-803-1CL | CL | No | Import Tool/PAS
MC700-803CL-01 | MC700-803-2CL | CL | No | Import Tool/PAS
MC700-803CL-01 | MC700-803-3CL | CL | No | Import Tool/PAS
MC700-803CL-01 | MC700-803-4CL | CL | No | Import Tool/PAS
MC080-010CL-01 | 080-010CL-01 | CL | Yes | Import Tool/PAS
MC700-802CL-01 | MC700-802-01CL | CL | No | Import Tool/PAS
MC700-802CL-01 | MC700-802-02CL | CL | No | Import Tool/PAS
MC660-122CL-01 | MC660-001CL | CL | Yes | Import Tool/PAS
MC660-122CL-01 | MC660-002CL | CL | No | PAS
700-130PA-06 | No VC's | PA | No | PAS
700-130OR-03 | No VC's | CL | No | PAS
700-130DE-04 | No VC's | CL | No | PAS
700-130ID-04 | No VC's | CL | No | PAS
700-130NY-06 | No VC's | CL | No | PAS
700-130NJ-05 | No VC's | NJ | No | PAS
700-130AZ-05 | No VC's | CL | No | PAS
090-010NJ-16 | No VC's | NJ | No | Capping
090-010ID-10 | No VC's | CL | No | Capping
090-010AZ-17 | No VC's | CL | No | Capping
090-010NY | No VC's | CL | No | Capping
090-010DE-05 | No VC's | CL | No | Capping
090-010PA-24 | No VC's | CL | No | Capping
090-010OR-13 | No VC's | CL | No | Capping
090-010PA-23 | No VC's | CL | No | Capping
090-010DE-04 | No VC's | CL | No | Capping
MC880-505CL | MC880-505-1CL | CL | Yes | PAS/Forms
MC880-505CL | MC880-505-2CL | CL | No | PAS/Forms
MC880-505CL | MC880-505-3CL | CL | Yes | PAS/Forms
MC880-505CL | MC880-505-4CL | CL | Yes | PAS/Forms
MC880-888CL | MC880-888-01CL | CL | Yes | PAS/Forms
MC880-888CL | MC880-888-02CL | CL | Yes | PAS/Forms
MC880-888CL | MC880-888-03CL | CL | Yes | PAS/Forms
MC880-888CL | MC880-888-04CL | CL | Yes | PAS/Forms
MC880-888CL | MC880-888-05CL | CL | Yes | PAS/Forms
MC880-888CL | MC880-888-06CL | CL | Yes | PAS/Forms
MC880-888CL | MC880-888-07CL | CL | No | PAS/Forms
MC880-888CL | MC880-888 08CL | CL | Yes | PAS/Forms
MC880-888CL | MC880-888-09CL | CL | Yes | PAS/Forms
MC880-402AZ | MC880-402-01AZ | CL | Yes | PAS/Forms
MC880-402AZ | MC880-402-02AZ | CL | Yes | PAS/Forms
MC880-402AZ | MC880-402-03AZ | CL | Yes | PAS/Forms
MC880-402AZ | MC880-402-04AZ | CL | Yes | PAS/Forms
MC880-402AZ | MC880-402-05AZ | CL | Yes | PAS/Forms
MC880-405AZ | MC880-402-03AZ | CL | Yes | PAS/Forms
MC880-405AZ | MC880-402-04AZ | CL | Yes | PAS/Forms
MC880-086AZ | MC880-402-05AZ | CL | Yes | PAS/Forms
MC880-086AZ | MC880-086-2AZ | CL | Yes | PAS/Forms
MC880-083AZ | MC880-083-01AZ | AZ | Yes | PAS/Forms
MC880-083AZ | MC880-083-02AZ | AZ | Yes | PAS/Forms
MC880-083AZ | MC880-083-03AZ | AZ | Yes | PAS/Forms
MC880-083AZ | MC880-253-04AZ | AZ | No | PAS/Forms
MC880-086NJ | MC880-086-02NJ | NJ | No | Renewal Triggers - Named Non-Owner Coverage Endorsement Form
MC880-253NJ | MC880-253-01NJ | NJ | Yes | Renewal Triggers - Named Non-Owner Coverage Endorsement Form
MC880-253NJ | MC880-253-02NJ | NJ | Yes | Renewal Triggers - Named Non-Owner Coverage Endorsement Form
MC880-253NJ | MC880-253-03NJ | NJ | No | Renewal Triggers - Named Non-Owner Coverage Endorsement Form
MC880-253NJ | MC880-253-04NJ | NJ | Yes | Renewal Triggers - Named Non-Owner Coverage Endorsement Form
MC880-253NJ | MC880-253-05NJ | NJ | No | Renewal Triggers - Named Non-Owner Coverage Endorsement Form
MC880-253NJ | MC880-210-03NJ | NJ | Yes | Renewal Triggers - Named Non-Owner Coverage Endorsement Form
MC880-888NJ | MC880-888-01NJ | NJ | Yes | Renewal Cover Notice - Document content and Trigger
MC880-888NJ | MC880-888-02NJ | NJ | Yes | Renewal Cover Notice - Document content and Trigger
MC880-888NJ | MC880-888-03NJ | NJ | Yes | Renewal Cover Notice - Document content and Trigger
MC880-888NJ | MC880-888-04NJ | NJ | Yes | Renewal Cover Notice - Document content and Trigger
MC880-888NJ | MC880-888-05NJ | NJ | Yes | Renewal Cover Notice - Document content and Trigger
MC880-888NJ | MC880-888-06NJ | NJ | Yes | Renewal Cover Notice - Document content and Trigger
MC880-888NJ | MC880-888-07NJ | NJ | No | Renewal Cover Notice - Document content and Trigger
MC880-888NJ | MC880-888 08NJ | NJ | Yes | Renewal Cover Notice - Document content and Trigger
MC880-888NJ | MC880-888-09NJ | NJ | Yes | Renewal Cover Notice - Document content and Trigger
MC880-253OR | MC880-253-01OR | OR | Yes | PAS/Forms
MC880-253OR | MC880-253-02OR | OR | Yes | PAS/Forms
MC880-253OR | MC880-253-03OR | OR | No | PAS/Forms
MC880-253OR | MC880-253-04OR | OR | Yes | PAS/Forms
MC880-253OR | MC880-253-05OR | OR | No | PAS/Forms
MC080-143PA | MC080-143-01PA | PA | Yes | Manual Conversion
MC080-143PA | MC080-143-02PA | PA | Yes | Manual Conversion
MC080-143PA | MC080-143-03PA | PA | Yes | PAS
MC080-143PA | MC080-143-04PA | PA | No | PAS
MC080-143PA | MC080-143-05PA | PA | No | PAS
MC080-143PA | MC080-143-06PA | PA | No | PAS
MC080-143PA | MC080-143-07PA | PA | No | PAS
MC080-143PA | MC080-143-08PA | PA | No | PAS
MC080-143PA | MC080-143-09A | PA | Yes | PAS
MC080-143PA | MC080-143-10PA | PA | No | PAS
MC080-143PA | MC080-143-11PA | PA | Yes | PAS
MC080-143PA | MC080-143-12PA | PA | Yes | PAS
MC080-143PA | MC080-143-13PA | PA | Yes | PAS
MC080-143PA | MC080-143-14PA | PA | No | PAS
MC080-143PA | MC080-143-15PA | PA | Yes | PAS
MC080-143PA | MC080-143-16PA | PA | No | PAS
MC080-143PA | MC080-143-17PA | PA | Yes | PAS
MC080-143DE | MC080-143-01DE | DE | Yes | PAS
MC080-143DE | MC080-143-02DE | DE | No | PAS
MC080-143DE | MC080-143-03DE | DE | Yes | PAS
MC080-143DE | MC080-143-04DE | DE | Yes | PAS
MC080-143DE | MC080-143-05DE | DE | Yes | PAS
MC080-143DE | MC080-143-06DE | DE | No | PAS
MC080-143DE | MC080-143-07DE | DE | Yes | PAS
MC080-143DE | MC080-143-08DE | DE | Yes | PAS
MC080-143DE | MC080-143-09DE | DE | Yes | PAS
MC040-030CL | MC040-030-1 CL | CL | Yes | PAS/Forms
MC040-030CL | MC040-030-2 CL | CL | No | PAS/Forms
MC040-030CL | MC040-030-3CL | CL | Yes | PAS/Forms
MC040-030CL | MC040-030-4CL | CL | Yes | PAS/Forms
MC040-030CL | MC040-030-5CL | CL | Yes | PAS/Forms
MC040-030CL | MC040-030-6CL | CL | Yes | PAS/Forms
MC040-030CL | MC040-030-7CL | CL | Yes | PAS/Forms
MC040-030CL | MC040-030-8CL | CL | Yes | PAS/Forms
MC190-010 | MC190-010-1 CL | CL | Yes | PAS
MC190-010 | MC190-010-2 CL | CL | No | PAS
MC040-035CL | MC040-035-1CL | CL | Yes | PAS/Forms
MC040-035CL | MC040-035-2CL | CL | Yes | PAS/Forms
MC040-035CL | MC040-035-3CL | CL | No | PAS/Forms
MC040-035CL | MC040-035-4CL | CL | Yes | PAS/Forms
MC090-117CL | MC090-117-1 CL | CL | Yes | Capping
MC700-091CL | MC700-091-1CL | CL | Yes | PAS
20309 | 1 | CL | Yes | PAS
20309 | 2 | CL | Yes | PAS
20309 | 3 | CL | Yes | PAS
20309 | 4 | CL | Yes | PAS
20309 | 5 | CL | Yes | PAS
20309 | 6 | CL | Yes | PAS
20309 | 7 | CL | Yes | PAS
20309 | 8 | CL | Yes | PAS
MC500-010CL | MC500-010-1CL | CL | Yes | PAS
MC880-885PA | MC880-885 01PA | PA | Yes | PAS/Forms
MC880-885PA | MC880-885 02PA | PA | No | PAS/Forms
MC880-885PA | MC880-885 03PA | PA | Yes | PAS/Forms
MC880-885PA | MC880-885 04PA | PA | Yes | PAS/Forms
MC880-885PA | MC880-885 05PA | PA | No | PAS/Forms
MC880-885PA | MC880-885 06PA | PA | Yes | PAS/Forms
MC880-885PA | MC880-885 07PA | PA | Yes | PAS/Forms
MC880-885PA | MC880-885 08PA | PA | No | PAS/Forms
MC880-882PA | MC880-882-01PA | PA | Yes | PAS/Forms
MC880-882PA | MC880-882-02PA | PA | Yes | PAS/Forms
MC880-882PA | MC880-882-03PA | PA | Yes | PAS/Forms
MC880-882PA | MC880-882-04PA | PA | Yes | PAS/Forms
MC880-882PA | MC880-882-05PA | PA | Yes | PAS/Forms
MC880-882PA | MC880-882-06PA | PA | Yes | PAS/Forms
MC880-882PA | MC880-882-07PA | PA | Yes | PAS/Forms
MC880-882PA | MC880-882-08PA | PA | Yes | PAS/Forms
MC880-718PA | MC880-718-01PA | PA | No | PAS/Forms
MC880-718PA | MC880-718-02PA | PA | No | PAS/Forms
MC880-718PA | MC880-718-03PA | PA | No | PAS/Forms
MC880-718PA | MC880-718-04PA | PA | No | PAS/Forms
MC880-718PA | MC880-718-05PA | PA | No | PAS/Forms
MC880-718PA | MC880-718-06PA | PA | No | PAS/Forms
MC880-718PA | MC880-718-07PA | PA | No | PAS/Forms
MC880-718PA | MC880-718-08PA | PA | No | PAS/Forms
MC880-889PA | MC880-889-1PA | PA | Yes | PAS/Forms
MC880-889PA | MC880-889-2PA | PA | Yes | PAS/Forms
MC880-889PA | MC880-889-3PA | PA | Yes | PAS/Forms
MC880-889PA | MC880-889-4PA | PA | No | PAS/Forms
MC880-889PA | MC880-889-5PA | PA | No | PAS/Forms
MC880-889PA | MC880-889-6PA | PA | No | PAS/Forms
MC880-889PA | MC880-889-7PA | PA | Yes | PAS/Forms
MC880-889PA | MC880-889-8PA | PA | Yes | PAS/Forms
MC880-889PA | MC880-889-9PA | PA | Yes | PAS/Forms
MC880-889PA | MC880-889-9BPA | PA | No | PAS/Forms
MC880-889PA | MC880-889-10PA | PA | No | PAS/Forms
MC880-889PA | MC880-889-11PA | PA | Yes | PAS/Forms
MC880-889PA | MC880-889-12PA | PA | No | PAS/Forms
MC880-889PA | MC880-889-13PA | PA | No | PAS/Forms
MC880-889PA | MC880-889-14PA | PA | Yes | PAS/Forms
MC880-889PA | MC880-889-15PA | PA | No | PAS/Forms
MC880-889PA | MC880-889-16PA | PA | No | PAS/Forms
MC880-889PA | MC880-889-17PA | PA | Yes | PAS/Forms
MC880-717PA | MC880-717-01PA | PA | Yes | PAS/Forms
MC880-717PA | MC880-717-02PA | PA | Yes | PAS/Forms
MC880-888PA | MC880-888-01PA | PA | Yes | PAS/Forms
MC880-888PA | MC880-888-02PA | PA | Yes | PAS/Forms
MC880-888PA | MC880-888-03PA | PA | Yes | PAS/Forms
MC880-888PA | MC880-888-04PA | PA | Yes | PAS/Forms
MC880-888PA | MC880-888-05PA | PA | Yes | PAS/Forms
MC880-888PA | MC880-888-06PA | PA | Yes | PAS/Forms
MC880-888PA | MC880-888-07PA | PA | No | PAS/Forms
MC880-888PA | MC880-888 08PA | PA | Yes | PAS/Forms
MC880-888PA | MC880-888-09PA | PA | Yes | PAS/Forms
MC880-715PA | MC880-715-01PA | PA | Yes | PAS/Forms
MC880-715PA | MC880-715-02PA | PA | Yes | PAS/Forms
MC880-101PA | MC880-101-01PA | PA | No | PAS/Forms
MC880-101PA | MC880-101-02PA | PA | No | PAS/Forms
MC880-101PA | MC880-101-03PA | PA | No | PAS/Forms
MC880-820DE | MC880-820- 01DE | DE | Yes | PAS/Forms
MC880-820DE | MC880-820- 02DE | DE | Yes | PAS/Forms
MC880-888DE | MC880-888-01DE | DE | Yes | PAS/Forms
MC880-888DE | MC880-888-02DE | DE | Yes | PAS/Forms
MC880-888DE | MC880-888-03DE | DE | Yes | PAS/Forms
MC880-888DE | MC880-888-04DE | DE | Yes | PAS/Forms
MC880-888DE | MC880-888-05DE | DE | Yes | PAS/Forms
MC880-888DE | MC880-888-06DE | DE | Yes | PAS/Forms
MC880-888DE | MC880-888-07DE | DE | No | PAS/Forms
MC880-888DE | MC880-888-08DE | DE | Yes | PAS/Forms
MC880-888DE | MC880-888-09DE | DE | Yes | PAS/Forms
MC880-881DE | MC880-881-01DE | DE | Yes | PAS/Forms
MC880-881DE | MC880-881-02DE | DE | Yes | PAS/Forms
MC880-881DE | MC880-881-03DE | DE | No | PAS/Forms
MC880-881DE | MC880-881-04DE | DE | Yes | PAS/Forms
MC880-881DE | MC880-881-05DE | DE | Yes | PAS/Forms
MC880-881DE | MC880-881-06DE | DE | No | PAS/Forms
MC880-881DE | MC880-881-07DE | DE | Yes | PAS/Forms
MC880-881DE | MC880-881-08DE | DE | No | PAS/Forms
MC880-086ID | MC880-086-01ID | ID | Yes | PAS/Forms
MC880-086ID | MC880-086-02ID | ID | Yes | PAS/Forms
MC880-254ID | MC880-254-01ID | ID | Yes | PAS/Forms
MC880-254ID | MC880-254-02ID | ID | Yes | PAS/Forms
MC880-254ID | MC880-254-03ID | ID | Yes | PAS/Forms
MC880-254ID | MC880-254-4ID | ID | Yes | PAS/Forms
MC880-880AZ | MC880-880-C-1AZ | AZ | Yes | PAS/Forms
MC880-880AZ | MC880-880-C-2AZ | AZ | Yes | PAS/Forms
MC880-880DE | MC880-880-C-1DE | DE | Yes | PAS/Forms
MC880-880DE | MC880-880-C-2DE | DE | Yes | PAS/Forms
MC880-880ID | MC880-880-C-1ID | ID | Yes | PAS/Forms
MC880-880ID | MC880-880-C-2ID | ID | Yes | PAS/Forms
MC880-880NY | MC880-880-C-1NY | NY | Yes | PAS/Forms
MC880-880NY | MC880-880-C-2NY | NY | Yes | PAS/Forms
MC880-880OR | MC880-880-C-1OR | OR | Yes | PAS/Forms
MC880-880OR | MC880-880-C-2OR | OR | Yes | PAS/Forms
MC880-880PA | MC880-880-B-1PA | PA | Yes | PAS/Forms
MC880-880PA | MC880-880-C-1PA | PA | Yes | PAS/Forms
MC880-880PA | MC880-880-C-2PA | PA | Yes | PAS/Forms
MC880-840PA | MC880-840-D-1PA | PA | Yes | PAS/Forms
MC880-840PA | MC880-840-D-2PA | PA | Yes | PAS/Forms
MC880-840PA | MC880-840-D-3PA | PA | Yes | PAS/Forms
MC880-840PA | MC880-840-D-4PA | PA | Yes | PAS/Forms
MC880-082AZ | MC880-082-01AZ | AZ | Yes | PAS/Forms
MC880-082AZ | MC880-082-02AZ | AZ | Yes | PAS/Forms
MC880-082AZ | MC880-082-03AZ | AZ | Yes | PAS/Forms
MC880-082AZ | MC880-082-04AZ | AZ | No | PAS/Forms
MC880-733NJ | MC880-733-01NJ | NJ | No | PAS/Forms
MC880-733NJ | MC880-733-02NJ | NJ | No | PAS/Forms
MC880-733NJ | MC880-733-03NJ | NJ | No | PAS/Forms
MC880-733NJ | MC880-733-04NJ | NJ | Yes | PAS/Forms
MC880-733NJ | MC880-733-05NJ | NJ | Yes | PAS/Forms
MC880-733NJ | MC880-733-06NJ | NJ | Yes | PAS/Forms
MC880-733NJ | MC880-733-07NJ | NJ | No | PAS/Forms
MC880-733NJ | MC880-733-08NJ | NJ | Yes | PAS/Forms
MC880-880NJ | MC880-880-C-1NJ | NJ | Yes | PAS/Forms
MC880-880NJ | MC880-880-C-2NJ | NJ | Yes | PAS/Forms
MC880-253ID | MC880-253-01ID | ID | Yes | PAS/Forms
MC880-253ID | MC880-253-02ID | ID | Yes | PAS/Forms
MC880-253ID | MC880-253-03ID | ID | No | PAS/Forms
MC880-253ID | MC880-253-04ID | ID | Yes | PAS/Forms
MC880-253ID | MC880-253-05ID | ID | No | PAS/Forms
MC130-320 | MC130-320-2CL | CL | No | PAS
MC030-222CL | MC030-222-1CL | CL | Yes | PAS
MC030-222CL | MC030-222-2CL | CL | No | PAS
MC410-015 | MC410-015-1CL | CL | Yes | PAS
MC410-015 | MC410-015-2CL | CL | No | PAS
21331 | 1 | CL | Yes | PAS
21331 | 2 | CL | No | PAS
21331 | 3 | CL | Yes | PAS
21331 | 4 | CL | No | PAS
21331 | 5 | CL | No | PAS
21331 | 6 | CL | No | PAS
21331 | 7 | CL | No | PAS
21189 | 1 | CL | Yes | PAS
21189 | 2 | CL | Yes | PAS
21189 | 3 | CL | Yes | PAS
21189 | 4 | CL | Yes | PAS
21189 | 5 | CL | Yes | PAS
21189 | 6 | CL | Yes | PAS
21189 | 7 | CL | Yes | PAS
21189 | 8 | CL | Yes | PAS
MC880-115OR | MC880-115-01OR | OR | Yes | PAS
MC880-115OR | MC880-115-02OR | OR | Yes | PAS
MC880-115OR | MC880-115-03OR | OR | Yes | PAS
MC880-086OR | MC880-086-01OR | OR | Yes | PAS
MC880-086OR | MC880-086-02OR | OR | Yes | PAS
MC880-887PA | MC880-887-01PA | PA | Yes | PAS/Forms
MC880-887PA | MC880-887-02PA | PA | Yes | PAS/Forms
MC880-887PA | MC880-887-03PA | PA | No | PAS/Forms
MC880-887PA | MC880-887-04PA | PA | Yes | PAS/Forms
MC880-887PA | MC880-887-05PA | PA | No | PAS/Forms
MC880-887PA | MC880-887-06PA | PA | No | PAS/Forms
MC880-887PA | MC880-882-07PA | PA | No | PAS/Forms
MC880-887PA | MC880-887-07BPA | PA | Yes | PAS/Forms
MC880-887PA | MC880-887-08PA | PA | Yes | PAS/Forms
MC880-887PA | MC880-887-09PA | PA | No | PAS/Forms
MC880-887PA | MC880-887-10PA | PA | Yes | PAS/Forms

## NEW
RTC ID | US ID (RRC ID) | Total VCs | In Scoep AC/VC # | State | Regression Scope Y/N | Track | Dev Timeline | Priority Group Date | Scenario Id | Automation Start Date | Planned Automation End Date | Status 09/28/2015 | Status 10/05/2015
491364 | 880-880NJ-03 Consolidated Form Stories - PRINTED Forms - Packets - Sequence - DCS mapping - BFC specs | 2 | 2 | NJ | Yes | MC | Group 4 | 2015-10-05 | C-AU-SS-HC-NJ-01 | 2015-10-05 | 2015-10-09 |  | In Development
491349 | 880-888NJ-01 Renewal Notice Cover Form | 9 | 8 | NJ | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-NJ-01 | 2015-09-21 | 2015-10-09 | On Hold | On Hold
495844 | 880-253NJ-02 Documents - New Business - Named Driver Exclusion Endorsement | 5 | 3 | NJ | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-NJ-01 | 2015-09-21 | 2015-10-09 | On Hold | On Hold
473324 | 700-130NJ-05 Lookup Interface | 0 | 0 | NJ | No | MC | Group 4 | 2015-10-05 | NA |  |  |  | Test Execution Complete
478581 | 090-010NJ-18 Rating - Rate a quote or policy | 0 | 0 | NJ | No | Capping | Group 4 | 2015-10-05 | NA |  |  | In Development | On Hold
496642 | 880-733NJ-02 - Consolidated Form Content and Triggers - NJ Auto Standard Policy Coverage Selection Form - AACSNJ | 8 | 4 | NJ | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-NJ-01 | 2015-09-21 | 2015-10-09 | In Development | In Development
495441 | 880-723PA-02 EMBPA Extraordinary Medical Benefits Coverage Endorsement | 2 | 2 | PA | Yes | MC | Group 1 | 2015-09-14 | C-AU-SS-HC-PA-003 | 2015-09-14 |  | On Hold | On Hold
478653 | 090-010PA-26_Rating - Rate_a_quote_or_policy | 0 | 0 | NJ | No | Capping | Group 4 | 2015-10-05 | NA |  |  |  | On Hold
491347 | 880-820PA-05 Consolidated Form Stories- Forms Page | 2 | 2 | PA | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-PA-003 |  |  | Ready To Build | On Hold
491306 | 880-880PA-03 Consolidated Form Stories - PRINTED Forms - Packets - Sequence - DCS mapping - BFC Specs | 3 | 3 | PA | Yes | MC | Group 4 | 2015-10-05 | C-AU-SS-HC-PA-004 |  |  |  | In Development
499312 | 880-715PA-03 - AA52IPAC Underinsured Motorists Coverage - PA Stacked | 2 | 2 | PA | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-004 |  |  | On Hold | On Hold
491366 | 880-888PA-01 Renewal Cover Notice Form | 9 | 8 | PA | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-004 |  |  | On Hold | On Hold
499309 | 880-717PA-03 - AA52UPAC Uninsured Motorists Coverage - PA Stacked | 2 | 2 | PA | Yes | MC | Group 1 | 2015-09-14 | C-AU-SS-HC-PA-004 | 2015-09-14 |  | On Hold | On Hold
495447 | 880-721PA-02 AALTPA Limited Tort Alternative Information Notice | 2 | 2 | PA | Yes | MC | Group 1 | 2015-09-14 | C-AU-SS-HC-PA-008 | 2015-09-14 |  | On Hold | On Hold
491292 | 090-010PA-24 _Rating - Rate_a_quote_or_policy | 0 | 0 | PA | No | MC | Group 4 | 2015-10-05 | NA |  |  |  | On Hold
495437 | 880-716PA-02 - AA52UPAB Uninsured Motorists Coverage-PA Non-Stacked | 2 | 2 | PA | Yes | MC | Group 1 | 2015-09-14 | C-AU-SS-HC-PA-003 | 2015-09-14 |  | On Hold | On Hold
491354 | 880-882PA-01 Consolidated Form Content & Triggers Plus (Pennsylvainia PA100G) | 8 | 4 | PA | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-001 | 2015-09-21 | 2015-09-30 | On Hold | On Hold
491354 | 880-882PA-01 Consolidated Form Content & Triggers Plus (Pennsylvainia PA100G) | Split | 1 | PA | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-008 |  |  | On Hold | On Hold
491354 | 880-882PA-01 Consolidated Form Content & Triggers Plus (Pennsylvainia PA100G) | Split | 2 | PA | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-009 |  |  | On Hold | On Hold
473329 | 700-130PA-06 Lookup Interface | 0 | 0 | PA | No | MC | Group 4 | 2015-10-05 | NA |  |  |  | Test Execution Complete
497768 | 880-885PA-01 Consolidated Form Content & Triggers Travel Deductible Waiver End 100TPA | 8 | 4 | PA | yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-005 |  |  | On Hold | On Hold
497768 | 880-885PA-01 Consolidated Form Content & Triggers Travel Deductible Waiver End 100TPA | Split | 1 | PA | yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-008 |  |  | On Hold | On Hold
497768 | 880-885PA-01 Consolidated Form Content & Triggers Travel Deductible Waiver End 100TPA | Split | 1 | PA | yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-009 |  |  | On Hold | On Hold
473332 | 080-143PA-02 Premium Page-Coverage Rules and Dependencies | 17 | 9 | PA | yes | MC | Group 4 | 2015-10-05 | C-AU-SS-HC-PA-007 |  |  |  | Ready To Test
491345 | 880-840PA-03 Consolidated Form Stories - GODD Page | 4 | 4 | PA | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-PA-005 |  |  | In Development | In Development
491350 | 880-881PA-01 Consolidated Form Content & Triggers-Plus (Pennsylvania Promise) (AAA100PAG) | 8 | 4 | PA | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-008 |  |  | On Hold | On Hold
495443 | 880-253PA-02 Documents - New Business - Named Driver Exclusion Endorsement | 3 | 3 | PA | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-PA-003 |  |  | On Hold | On Hold
491352 | 880-889PA-02 FIrst Party Benefits Coverage and Limits Selection Form (Grandfathered Coverage) | 18 | 9 | PA | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-PA-002 | 2015-09-28 | 2015-09-30 | In Development | Ready To Test
495432 | 880-887PA-01 Pennsylvania Notice in regards to Liability Coverage Limits and Discounts - Manual Conversion | 11 | 1 | PA | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-PA-009 |  |  | Ready To Build | On Hold
495432 | 880-887PA-01 Pennsylvania Notice in regards to Liability Coverage Limits and Discounts - Manual Conversion | Split | 6 | PA | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-PA-006 |  |  |  | On Hold
495434 | 880-714PA-02 Underinsured Motorists Coverage-PA Non Stacked | 2 | 2 | PA | Yes | MC | Group 1 | 2015-09-14 | C-AU-SS-HC-PA-003 | 2015-09-14 |  | On Hold | On Hold
452859 | 090-601CL-02 View Capping Details page- Business Rules v2.0 | 9 | 9 | CL | Yes | Capping | Group 4 | 2015-10-05 | C-AU-SS-HCCAP-CL-018 | 2015-10-05 | 2015-10-23 |  | In Development
451992 | 090-600CL-02 Capping Details Screen - Field Validation v2.0 | 18 | 18 | CL | Yes | Capping | Group 4 | 2015-10-05 | C-AU-SS-HCCAP-CL-018 | 2015-10-05 | 2015-10-23 |  | In Development
451993 | 090-117CL-01 Assign Program Code | 2 | 1 | CL | Yes | Capping | Group 3 | 2015-09-28 | C-AU-SS-HCCAP-CL-018 | 2015-10-05 | 2015-10-23 | Test Execution Complete | Test Execution Complete
452370 | CMN-PER-01-01CL-02.1 20309 AUS-PER-01-2.1 US Manage Privilege v2.1 | 4 | 4 | CL | Yes | Capping | Group 1 | 2015-09-14 | C-AU-SS-HCCAP-CL-018 | 2015-10-05 | 2015-10-23 | Planned | Planned
451991 | 090-116CL-03 Ability to calculate Capping V 3.0 | 19 | 19 | CL | Yes | Capping | Group 4 | 2015-10-05 | C-AU-SS-HCCAP-CL-001 TO C-AU-SS-HCCAP-CL-017 C-AU-SS-HCCAP-CL-018 | 2015-10-05 | 2015-10-23 |  | On Hold
495459 | 880-888CL-01 Renewal Cover Notice Form | 9 | 8 | CL | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-CL-004 |  |  | On Hold | On Hold
491770 | 090-117CL-02 Assign Program Code | 1 | 1 | CL | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-CL-003 |  |  | On Hold | On Hold
478890 | 700-803CL-01 Business Requirement - Data elements for manual conversion | 4 | 0 | CL | No | MC | Group 4 | 2015-10-05 | NA |  |  |  | In IT Team Review
482734 | 080-010CL-03 Premium Page - Premium is not calculated automatically | 1 | 1 | CL | Yes | MC | NONE |  | C-AU-SS-HC-CL-001 |  |  |  | On Hold
474988 | 660-122CL-02 Search Connections | 2 | 2 | CL | Yes | MC | Group 1 | 2015-09-14 | C-AU-SS-HC-CL-004 |  |  | On Hold | On Hold
491369 | FR410-015-02 Ability to order MVR reports in a batch process | 2 | 2 | CL | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-CL-004 |  |  | Cancelled | Cancelled
491948 | CFR190-010CL-02 Home Banking-Support an indicator to differentiate Home Banking and OPC participants | 2 | 1 | CL | Yes | MC | Group 1 | 2015-09-14 | C-AU-SS-HC-CL-002 |  |  | On Hold | On Hold
491957 | 130-222CL-02 Ability to Re-order Insurance Score at Renewal. Only applied if it improves the renewal offer / tier | 2 | 2 | CL | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-CL-004 |  |  | Cancelled | Cancelled
491299 | 130-383CL-03 Ability to override rule on renewals | 3 | 3 | CL | Yes | MC | Group 1 | 2015-09-14 | C-AU-SS-HC-CL-001 |  |  | On Hold | On Hold
497309 | 880-505CL-03 Documents - Membership Validation Letter | 4 | 3 | CL | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-CL-003 |  |  | Ready To Build | On Hold
491951 | CFR040-030CL-05 Generate Home Banking Reminder at R-20 | 7 | 7 | CL | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-CL-002 |  |  | On Hold | On Hold
492698 | 080-005CCL-05 Premium Page - Top portion of the page up to the coverages section | 4 | 4 | CL | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-CL-001 |  |  | Ready To Build | On Hold
470442 | 020-008CCL-12 General Page - Policy Information Section fields | 5 | 5 | CL | Yes | MC | Group 4 | 2015-10-05 | C-AU-SS-HC-CL-005 |  |  |  | Test Execution Complete
496638 | AUTO-CMCL-01 21189:US CONV Auto - Customer Match | 8 | 3 | CL | Yes | MC | Group 3 | 2015-09-28 | C-AU-SS-HC-CL-001, C-AU-SS-HC-CL-002, C-AU-SS-HC-CL-004 |  |  | Ready To Build | On Hold
491362 | 700-091CCL-03 Enhance existing batch jobs | 1 | 1 | CL | Yes | MC | Group 4 | 2015-10-05 | C-AU-SS-HC-CL-003 |  |  |  | In Development
491302 | 170-082CL-07 Underwriting rules and tasks - spin | 4 | 0 | CL | No | MC | Group 4 | 2015-10-05 | NA |  |  |  | On Hold
473351 | 100-125CL-01 Number Ranges for Policy Numbers | 1 | 0 | CL | No | MC | Group 1 | 2015-09-14 | NA |  |  | On Hold | On Hold
491960 | CFR500-010CL-02 Implement Balance Transfer file processing for Manual Conversion Policies | 1 | 1 | CL | Yes | MC | NONE |  | INTEGRATIONS |  |  | In Development | In Development
497059 | CFR040-035CL-04 Manual Conversion Pre-Renewal Notice | 4 | 3 | CL | Yes | MC | Group 2 | 2015-09-21 | C-AU-SS-HC-CL-005 |  |  | On Hold | On Hold
491368 | 130-320CL-02 Automatic Creation of Renewal Preview | 1 | 0 | CL | No | MC | Group 2 | 2015-09-21 | NA |  |  | Ready To Build | On Hold
451994 | 020-240CL-15 Online help functionality v15.0 | 0 | 0 | CL | No | MC | Group 3 | 2015-09-28 | NA |  |  |  | On Hold
478127 | AUTO-CMCL-02 - 21331:US CONV Auto - Move Policy from one customer account to another | 7 | 2 | CL | Yes | MC | NONE |  | C-AU-SS-HC-CL-005 |  |  |  | In Development

## PLAN
| 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-04-13 | 2015-04-20 | 2015-04-27 | 2015-05-04 | 2015-05-11 | 2015-05-18 | 2015-05-25 | 2015-06-01 | 2015-06-08 | 2015-06-15 | 2015-06-22 | 2015-06-29 | 2015-07-06 | 2015-07-13 | 2015-07-20 | 2015-07-27 | 2015-08-03 | 2015-08-10 | 2015-08-17 | 2015-08-24 | 2015-08-31 | 2015-09-07 | 2015-09-14 | 2015-09-21 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07 | 2015-12-14 | 2015-12-21 | 2015-12-28
| 2015-03-27 | 2015-04-03 | 2015-04-10 | 2015-04-17 | 2015-04-24 | 2015-05-01 | 2015-05-08 | 2015-05-15 | 2015-05-22 | 2015-05-29 | 2015-06-05 | 2015-06-12 | 2015-06-19 | 2015-06-26 | 2015-07-03 | 2015-07-10 | 2015-07-17 | 2015-07-24 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-21 | 2015-08-28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 2015-12-11 | 2015-12-18 | 2015-12-25 | 2016-01-01
| Story Writing | [10 empty] | IT Team Review |  |  |  |  | Sprint 13
[12 empty] | IT Team Review |  |  |  |  | Functional Testing
[8 empty] | Story Writing | [9 empty] | IT Team Review |  |  |  |  | More ITTR |  | Sprint 14
[18 empty] | IT Team Review |  |  |  |  | More ITTR |  | Functional Testing
Stabilization
Regression Testing
Development Schedule
[26 empty] | Group 1 | Group2 | Group3 | Group4
CL CP SCENARIOS
3807 | 2015-09-18: 36
Lalitha Kiran Koduri | 2015-07-03: 45; 2015-07-10: 45; 2015-07-17: 36; 2015-07-24: 45; 2015-07-31: 45; 2015-08-07: 45; 2015-08-14: 45; 2015-08-21: 45; 2015-08-28: 45; 2015-09-04: 45; 2015-09-11: 45; 2015-09-18: 36; 2015-09-25: 45; 2015-10-02: 36; 2015-10-09: 27; 2015-10-16: 0; 2015-10-23: 36; 2015-10-30: 45; 2015-11-06: 45; 2015-11-13: 36; 2015-11-20: 45
Maanasa Gottipati | 2015-07-24: 45; 2015-07-31: 45; 2015-08-07: 45; 2015-08-14: 45; 2015-08-21: 36; 2015-08-28: 45; 2015-09-04: 45; 2015-09-11: 45; 2015-09-18: 27; 2015-09-25: 45; 2015-10-02: 36; 2015-10-09: 45; 2015-10-16: 45; 2015-10-23: 36; 2015-10-30: 45; 2015-11-06: 45; 2015-11-13: 36; 2015-11-20: 45
Ankita Bhutt | 2015-07-03: 45; 2015-07-10: 45; 2015-07-17: 36; 2015-07-24: 45; 2015-07-31: 45; 2015-08-07: 45; 2015-08-14: 45; 2015-08-21: 45; 2015-08-28: 45; 2015-09-04: 45; 2015-09-11: 45; 2015-09-18: 0; 2015-09-25: 45; 2015-10-02: 45; 2015-10-09: 45; 2015-10-16: 18; 2015-10-23: 27; 2015-10-30: 45; 2015-11-06: 45; 2015-11-13: 36; 2015-11-20: 45
Gowthami Volete | 2015-07-10: 45; 2015-07-17: 36; 2015-07-24: 45; 2015-07-31: 45; 2015-08-07: 45; 2015-08-14: 45; 2015-08-21: 45; 2015-08-28: 45; 2015-09-04: 45; 2015-09-11: 45; 2015-09-18: 36; 2015-09-25: 45; 2015-10-02: 36; 2015-10-09: 45; 2015-10-16: 27; 2015-10-23: 36; 2015-10-30: 45; 2015-11-06: 45; 2015-11-13: 36; 2015-11-20: 45
Zoheb | 2015-07-17: 36; 2015-07-24: 45; 2015-07-31: 45; 2015-08-07: 27; 2015-08-14: 45; 2015-08-21: 45; 2015-08-28: 36; 2015-09-04: 27; 2015-09-11: 45; 2015-09-18: 36; 2015-09-25: 45; 2015-10-02: 36; 2015-10-09: 45; 2015-10-16: 45; 2015-10-23: 36; 2015-10-30: 45; 2015-11-06: 45; 2015-11-13: 36; 2015-11-20: 45
Development - Resources | 2015-08-07: 0; 2015-08-14: 2; 2015-08-21: 2; 2015-08-28: 3; 2015-09-04: 8; 2015-10-09: 4; 2015-10-16: 4; 2015-10-23: 4; 2015-10-30: 4; 2015-11-06: 4; 2015-11-13: 4; 2015-11-20: 4
Total Hours | 2015-08-07: 0; 2015-08-14: 90; 2015-08-21: 90; 2015-08-28: 81; 2015-10-09: 180; 2015-10-16: 135; 2015-10-23: 135; 2015-10-30: 180; 2015-11-06: 180; 2015-11-13: 144; 2015-11-20: 180
ACs - Weekly Target | 2015-08-07: 0; 2015-08-14: 0; 2015-08-21: 0; 2015-08-28: 0; 2015-09-04: 0; 2015-09-11: 0; 2015-09-18: 0; 2015-09-25: 0; 2015-10-02: 0; 2015-10-09: 20; 2015-10-16: 15; 2015-10-23: 15; 2015-10-30: 20; 2015-11-06: 20; 2015-11-13: 16; 2015-11-20: 20
Total Acs developed | 2015-08-07: 0; 2015-08-14: 0; 2015-08-21: 0; 2015-08-28: 0; 2015-09-04: 0; 2015-09-11: 0; 2015-09-18: 0; 2015-09-25: 0; 2015-10-02: 0; 2015-10-09: 20; 2015-10-16: 35; 2015-10-23: 50; 2015-10-30: 70; 2015-11-06: 90; 2015-11-13: 106; 2015-11-20: 126
[18 empty] | 1AC | 9hrs - dev
[18 empty] | 4AC | 9hrs - scenario design
[21 empty] | 10 | 20 | 29 | 67 | 107 | 139 | 179 | 211 | 251 | 289
10
20
29
67
107
139
179
211
251
[21 empty] | 289 |  | 72 | 112 | 148 | 188 | 228 | 268 | 296
72
112
148
188
228
268
296
Note on A15: Sharad, Tushar: As per the SOW there are 5850 hrs available for the conversion & capping effort

## Automation Plan
DATES | 2015-09-14 | 2015-09-21 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07 | 2015-12-14 | 2015-12-21 | 2015-12-28
| 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 2015-12-11 | 2015-12-18 | 2015-12-25 | 2016-01-01
Functional Timeline | bar: 2015-09-18 to 2015-10-16
Regression Timeline | 2015-10-23: Stabilization
Regression Testing
Development Timeline | 2015-09-18: Development Schedule
| Group 1 | Group2 | Group3 | Group4
Dependency | 2015-09-18: 1- Capping Story 5 - PA MC 4 - CL MC; 2015-09-25: 5 - CL MC 3 - NJ MC 10 - PA MC; 2015-10-02: 1- Capping 6 - CL MC; 2015-10-09: 3 - Capping 4 - CL MC 4 - NJ MC 4 - PA MC; 2015-11-27: IMPORT TOOL ETL - TEST DATA
Automation Timelines | 2015-09-18: AUTOMATION SCHEDULE
Weekly/person | 36 | 45 | 36 | 45 | 45 | 36 | 45 | 45 | 36 | 45
No of Resources | 1 | 1 | 1 | 5 | 5 | 5 | 2 | 1 | 1 | 1
Total Hours | 36 | 45 | 36 | 225 | 225 | 180 | 90 | 45 | 36 | 45
Common Pattern VCs (40) | 2015-09-18: 10; 2015-09-25: 20; 2015-10-02: 10; 2015-11-06: TRIAL RUN; 2015-11-20: Implementation
CL Conversion VCs (49) | 2015-10-09: 14; 2015-10-16: 18; 2015-10-30: 17
NJ Conversion VCs (17) | 2015-10-30: 17
PA Conversion VCs (74) | 2015-10-09: 23; 2015-10-16: 29; 2015-10-23: 22
Capping VCs(51) | 2015-10-09: 6; 2015-10-16: 33; 2015-10-23: 12
Target No of Scenarios | 2015-10-09: 10; 2015-10-16: 6; 2015-10-23: 15; 2015-10-30: 2
Variance
Scenario specific Burn Down (Number of scenarios in 's'/Number of persons in 'p')
CL Conversion VCs (49) | 2015-10-09: 2s/1p; 2015-10-16: 2s/1p; 2015-10-30: 1s/1p
NJ Conversion VCs (17) | 2015-10-30: 1s/1p
PA Conversion VCs (74) | 2015-10-09: 3s/2p; 2015-10-16: 3s/2p; 2015-10-23: 3s/2p
Capping VCs(51) | 2015-10-09: 5s/1p; 2015-10-16: 2s/1p; 2015-10-23: 12s/2p

## SOW
|  |  |  | P2 | P3 | P4 | P5 | P6 | Start Date | End Date
|  |  |  | 2015-06-28 | 2015-07-26 | 2015-08-23 | 2015-09-20 | 2015-10-18
|  |  |  | 2015-07-25 | 2015-08-22 | 2015-09-19 | 2015-10-17 | 2015-11-14
|  |  |  | 180 | 180 | 180 | 180 | 180
Senior Consultant | Lalitha Kiran Koduri | Technology - Offshore | Testing Lead | 180 | 180 | 180 | 180 | 180 | 2015-06-28 | 2015-11-14
Consultant | Maanasa Gottipati | Technology - Offshore | Analysis / manual testing 1 | 135 | 180 | 180 | 180 | 45 | 2015-07-05 | 2015-10-24
Analyst | Ankita Bhutt | Technology - Offshore | Analysis / manual testing 2 | 135 | 180 | 180 |  |  | 2015-07-05 | 2015-09-19
Senior Consultant |  | Technology - Offshore | Test automation 1 | 135 | 180 | 180 |  |  | 2015-07-05 | 2015-09-19
Consultant |  | Technology - Offshore | Test automation 2 | 45 | 180 | 180 | 135 |  | 2015-07-19 | 2015-10-10
Consultant | Gowthami Volete | Technology - Offshore | Test automation 3 | 135 | 180 | 180 | 180 | 180 | 2015-07-05 | 2015-11-14
Analyst | Zoheb Banikar | Technology - Offshore | Test automation 4 | 45 | 180 | 180 | 180 | 180 | 2015-07-19 | 2015-11-14
Analyst |  | Technology - Offshore | Test automation 5 | 45 | 180 | 180 | 135 |  | 2015-07-19 | 2015-10-10
5310
General receiver | Empl./appl.name | 2015-07-04 | 2015-07-11 | 2015-07-18 | 2015-07-25 | 2015-08-01 | 2015-08-08 | 2015-08-15 | 2015-08-22 | 2015-08-29 | 2015-09-05
CAL11899-01-01-5000 | BANIKAR, ZOHEB AHMED | - | - | 27 | 44 | 45 | 32 | 45 | 36 | 45 | 18
| BHUTT, ANKITA | 45 | 45 | 36 | 45 | 45 | 32 | 45 | 45 | 45 | 45
| DALAL, SACHIN | 2 | 2 | - | 1 | 2 | 4 | 1 | - | 2 | 2
| DESHPANDE, MINAL | - | - | - | - | - | - | - | - | - | 2
| GOTTIPATI, MAANASA | - | - | - | 45 | 45 | 40 | 45 | 38 | 45 | 45
| KODURI, LALITHA KIRAN | 45 | 36 | 36 | 45 | 45 | 45 | 45 | 45 | 45 | 36
SATPUTE, PALLAVI PRAKASH | bar: 2015-07-04 to 2015-09-05
SOMAYAJULA, NAGA SAHITHI | bar: 2015-07-04 to 2015-09-05
| VOLETE, GOWTHAMI | - | 36 | 36 | 45 | 45 | 36 | 45 | 45 | 45 | 45
Total Per week |  | 92 | 119 | 135 | 225 | 227 | 189 | 226 | 209 | 227 | 193

## RTC Status
Status | Details
Open | The user story has been created in RTC
In Progress | Work has been started on the user story in EKM and test package creation has begun
In Stakeholder Review | The user story is being reviewed by the business stakeholders
Stakeholder Approved | The stakeholder has approved the US
Ready IT Team Review | User stories have been approved, test packages and data mapping have been completed; for PAScore the PAScore Overall Rank must also be completed
In IT Team Review | Development and QA pull items that are flagged and in Ready IT Team Review and start review
Approved | Development and QA understand the US and what is required for successful development and testing
Planned | The user story has been planned by Development and QA as part of the sprint
In Development | Development is working on the user story
Development Complete | Development has determined all coding is complete for the user story
Ready to Build | The user story is ready to be put into a build so it can be tested
Ready to Test | This is the trigger for QA so they know the user story can be tested
In Testing | QA is in the process of running all test packages
Test Execution Complete | QA has completed all test packages; defects may exist
QA Approved | QA has successfully completed all test packages AND there are no high and critical defects on the user story
(aka Testing Complete)
On Hold | Dev or QA have put the item on hold (usually because they need more information)
Blocked | Dev or QA have determined that the item cannot be worked on because of a blocking defect, user story, etc.
Cancelled | Business stakeholder decide the story is no longer necessary
TP Status | Corresponding US Status | Description
Not Started | Open In Progress | Default Status
In Progress | In Stakeholder Review
In BA Review | Stakeholder Approved
TA Updates Required | Stakeholder Approved | BA review comments to be implemented by TA
Ready for IT Team Review | Ready IT Team Review
In IT Team Review | In IT Team Review
In Clarification | In Stakeholder Review | TA has clarification on US
Stakeholder approved
Completed | Approved & Further
Cancelled | Cancelled
Not Required |  | US is retired, no Delta. PASCore usage
Existing TP in Review |  | PASCore usage only