## Slide 1: PAS Program Turn-Around Recommendations
Deloitte Consulting LLP
September 27, 2013

## Slide 2
The PAS program is at a critical junction – Auto and Property have been combined to remedy material gaps in performance and outcomes.
Stabilization and improved performance are expected, which requires significant changes including 1) executing a successful turnaround of the Property program; 2) implementing software factory best practices; and 3) clarifying the accountability model to deliver expected results.
Program success is dependent on a program “reset” to clarify scope, resource alignment and improve return on program spend.
Preface

## Slide 3: Issue, Impact and Solutions
Issue |  |  |  | Impact
Property is a failing project and is in turn-around status; Development and QA have missed delivery targets (timeline and quality). |  |  |  | Timeline and functionality milestones not achieved Significant rework required Low morale
Issue Highlights |  | Recommended Solutions |  | 
Property leadership failed to course-correct after metrics repeatedly indicated they were off-track Inconsistent adherence to code standards and coordination across scrum teams and multiple vendors created quality issues and rework Insufficient knowledge of Exigen product and architectural interdependencies; decision to exclude Exigen from implementation development team was flawed Exigen base product development delays hindered delivery timeliness and quality; top 10 features still have not been fully-delivered and stabilized, critical defects remain Exigen upgrades lack sufficient risk analysis, testing and release notes to prevent spike in upgrade release defects Property functional and regression testing strategy/execution was flawed and did not take advantage of Auto’s learnings Insufficient test bed to adequately test plausible scenarios and time points Automation testing failed in both functional and regression testing, creating 1,600 point backlog of untested code Immature use of QA tools, metrics and processes (e.g., root cause analysis, use of RTC/QC) |  | Program Director must demonstrate an ability to course-correct and leverage metrics Appoint senior Development leader who will impose a single set of code standards, a rigorous code quality peer review process, and cross-scrum team communication Add Exigen product specialists to implementation Development team Establish service level agreement with Exigen on: Prompt delivery of remaining fixes to stabilize base code Go-forward service level standards to achieve cleaner upgrade path (risk analysis, release notes, etc.) Appoint senior QA leader to course-correct strategy, define set of metrics, implement rigorous defect root cause analysis and drive Program accountability for mitigation Replace failed functional and regression testing approaches Institute proven Auto functional testing process Institute proven Auto regression framework (using UPI and select API testing) Leverage manual testing while updating regression test scripts |  | 

## Slide 4: Issue, Impact and Solutions
Issue |  |  |  | Impact
QA missed milestones and defect leakage into production indicate optimization opportunities. |  |  |  | Property defects multiply as Development builds on untested code base Root causes are neither identified nor mitigated
Issue Highlights |  | Recommended Solutions |  | 
Lack of proactive recommendations from QA vendor on environments planning, test coverage improvement, production-like test data, automation target levels, defect density modeling Insufficient program testing Insufficient coverage of “off happy path” functions, scenarios, and end to end testing Limited success with automated regression testing Lack of Program prioritization of functionality hinders Property QA ability to prioritize test scope and defect triage Insufficient defect triage, root cause analysis and follow-through Insufficient test data and regression test bed to support full range of test scenarios, functions and time points No use of production data Test data is created by individual test analysts who typically are not qualified to determine the full set of critical testing needs Program delays due to time point testing delays Multiple test teams (Program, Integrations, DCS, PAScore, Conversions, etc.) lack single leadership structure to manage testing capacity and dependencies Ad hoc, sub-optimized environments strategy Late Development code drops have hindered QA |  | Conduct strategic analysis of QA function to identify step-change improvement plan Reset QA test scope and execution Define test scope informed by business priority of story Determine requirements criticality during design to inform prioritization and focus of test coverage Institute end to end functional testing (including UI) Implement repeatable process for defect triage, root cause analysis and communication with defect owners Optimize test data superset, time point testing and regression test bed Create test data superset for program rather than have test data be created by individual test analysts Review virtual time stamp management and increase depth and breath of test cases so appropriate test cycles can be completed within a single sprint Consolidate program testing activities (Program, Integrations, DCS, PAScore, Conversions) under PAS QA leadership (not including unit testing, certification testing) Align environments strategy to support testing needs for multiple products across software development lifecycle Increase Program accountability to enforce code drop dates |  | 

## Slide 5: Issue, Impact and Solutions
Issue |  |  |  | Impact
Auto and Property requirements gathering approach, design documentation, and low degree of requirements reuse inconsistent with SDLC leading practices. |  |  |  | Increased program costs Excess demand on the software factory Increased risk of defects and delays Product resource burnout
Issue Highlights |  | Recommended Solutions |  | 
Product SME is single point of program failure in current requirements gathering approach SMEs dictate requirements rather than Program BAs creating requirements and engaging SMEs for joint review Approach places significant time demands on Product SMEs Business SME capacity has prevented Program from accelerating Current level of SME engagement has not led to enhanced outcomes on Property program; Property is experiencing higher than expected volume of change requests Design team structure, roles, processes and deliverables differ materially between Auto and Property, not optimized to share knowledge with Development, QA and DCS Current requirements gathering and analysis approach is executed state by state, rather than looking holistically at functions across states; this hinders reuse and creates duplicate effort across states and products, driving up costs, timeline and risk of defects (e.g., e-signature, motorcycle discount) UI customization between Auto and Property created an inconsistent user experience and triggered a refactoring effort Inconsistent use of RTC to manage unified backlog across Program, DCS, PAScore, et al |  | Launch cross-team (Design, Development, QA, DCS, PAScore, et al) leading practices review to: Redefine requirements gathering process and reposition product SMEs as reviewers, not creators, of requirements Optimize Design team structures, roles, processes and deliverables to more effectively share knowledge on most complex requirements Conduct reuse analysis of Auto and Property requirements (across states) to identify and implement “reduce and reuse” methods; establish accountability for ongoing, strict reuse across products and states Establish processes and controls to minimize UI deviations Enforce consistent use of RTC to manage backlog |  | 

## Slide 6: Issue, Impact and Solutions
Issue |  |  |  | Impact
Property Oversight team did not drive necessary accountability and transparency to accurately forecast and deliver to Program targets. |  |  |  | Undermined sense of urgency and morale among program staff Inability to predict throughput Inability to identify and mitigate risks Inability to manage interdependencies
Issue Highlights |  | Recommended Solutions |  | 
No use of daily burndown analysis to hold teams accountable for progress and identify / mitigate risks No enforcement of use of RTC backlog management tool, hindering ability to track shifting priorities real-time Insufficient cross-team planning process; Design, Development and QA teams made program decisions regarding priorities, scope and sprint planning without adequate consideration of interdependencies (e.g., Development agree to take on additional scope in a sprint without consideration of QA or Integrations impact) Ad hoc dependency management with outside parties that impact the program (Billing Central, Payments Central, Change Management, PAScore, et al) increases program risk No consistent measurement of Design, Development, QA teams’ throughput, hindering ability to forecast throughput, monitor progress and identify/investigate deviations from plan Property Development and QA teams unable to consistently deliver to targets Repeated revision of baseline due dates obscured delays and eliminated critical sense of urgency |  | Implement Auto burndown management approach in Property to drive sense of urgency, intensity Automate burndown reporting Institute procedures to rapidly analyze root causes of program deviations from plan Enforce real-time use of RTC across program for backlog management Focus all teams (Design, Development, QA, et al) on collaborative delivery of one program goal versus individual team goals Formalize dependency management with outside stakeholders that impact program success Implement reports to track throughput by team, by sprint Institute procedures to track root causes of program deviations from plan Monitor and hold teams accountable for throughput at each stage of the process Stop revising baseline due dates; convene joint team of Business, Design, Development, QA, Integrations, Environments and PAScore resources to determine actions needed to shift Program mandate from “on time, on budget” to “continuous improvement of program quality and value delivered” |  | 

## Slide 7: Issue, Impact and Solutions
Issue |  |  |  | Impact
PAS Program Design and Defect Triage resources do not report to Program Director; shifting priorities and external dependencies hinder software factory throughput. |  |  |  | Weakened program accountability for delivery scope, quality, timeliness Competing priorities
Issue Highlights |  | Recommended Solutions |  | 
Program Director not directly accountable for Design, Defect Triage resources and budget Program lacks a clearly-defined framework to quantify program priorities Stakeholders and Program churning on 2014 Program scope due to competing priorities No clear owner of prioritization; Sustaining Operations, Business and Clubs driving prioritization, often without Program input |  | Align Design and Defect Triage resources and budget to report to Program Director Establish prioritization framework to quantify business impact, risk, etc., and determine Program priorities |  | 

## Slide 8: The PAS Program Director is accountable for program delivery, but does not control Design and Defect Triage resources critical to program success.
PAS Program
Scott Hunt
Conversions
Quality Assurance
Policy Admin. Services
Kim Bissell
Process | Methods | Tools
Operational Infrastructure
Bob Valliere
Integrations
Environments
Product Design
Brian Suzuki
Change Management
Development
Design
Advance Team
Oversight / Finance / Metrics
PAScore Defect Triage
Sustaining Operations
Other
Auto
Property
Governance | Steering Committee
Software Factory
PAS Program Overview

## Slide 9
Copyright © 2013 Deloitte Development LLC. All rights reserved.