## Pivot
Custom field (RTC Status) | (All)
Row Labels | Count of Issue key
HDES_Generic_US | 29
No | 11
Yes | 18
(blank) | 26
No | 4
Yes | 16
(blank) | 6
Grand Total | 55
Row Labels | Count of Issue key |  |  |  | 22 | CA-CP
HDES_Generic_US | 29
No | 11 |  |  |  |  | CA-CP-100
Yes | 15
(blank) | 3
(blank) | 16 |  |  |  |  | 1 | US splits
No | 1 |  |  |  |  | 2
Yes | 12
(blank) | 3
Grand Total | 45
Scenario counts
XXX-CNV | 8 |  | CP
NB | 7
CP | 9
| R-58 | R-48 | R-10 | R | R+1 |  |  | 2R
801-CNV | CNV |  |  |  | CA-CP-100

## RTC_21_09
Id | Oversight | Scope label | Analyzed in JIRA? | Type | Work Item | Story ID | Status | Story Points | Preliminary Story Points | Summary | Scope | Project | Group Ownership | TP Status | Unified Business Priority | CR Number | BSS Number | QC ID String | Priority | Related To | Delta State | Unified Business Backlog | Planned For | Resolution | Bug Type | Priority Group | Epic - Activity | Feature Area | Lockdown | Tags | RRC ID | Removed from Scope | Added To Scope | Final Scope | Final Scope Date | Original Scope | Dev Delivered to QA | Dev Non-Delivered to QA | Target Sprint
586844 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-REN-AUTOINF-CA | Test Execution Complete | 2.5 | 2 | H-REN-AUTOINF-CA 25379:Apply Inflation Guard factors HO3 DP3 v2 |  | Property | Program | Ready for IT Team Review | 10000 | F0128 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_DNK |  |  | Group 01 | Renewal | Renew Policy | TRUE |  | 25379 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
679094 |  | Current RTC | #N/A | Story - Delta | WI0162 CA HDES Conversion | H-REN-AUTOINF-CA-03 | Ready To Test | NONE | 3 | H-REN-AUTOINF-CA-03 25380:Apply Inflation Guard CPI HO4 V3.0 | WI0162 CR15 | Property | Program | In IT Team Review | 10001 | WI0162 CR15 |  |  | NONE | CA | CA | TRUE | IE_Sprint_20_PHX-2 |  |  | Group 07 | Renewal | Renew Policy | TRUE |  | 25380 |  | PAS10 | PAS10 | 2016-09-20 12:00 |  |  |  | Sprint 20
679096 |  | Current RTC | #N/A | Story - Delta | WI0162 CA HDES Conversion | H-REN-AUTOINF-CA | Ready To Test | NONE | 3 | H-REN-AUTOINF-CA 25378: Apply Inflation Guard factors HO6 V03 | WI0162 CR15 | Property | Program | In IT Team Review | 10001 | WI0162 CR15 |  |  | NONE | CA | CA | TRUE | IE_Sprint_20_PHX-2 |  |  | Group 07 | Renewal | Renew Policy | TRUE |  | 25378 |  | PAS10 | PAS10 | 2016-09-20 12:00 |  |  |  | Sprint 20
587153 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | H-UWA-ACSMGT-CL | QA Approved | 4 | 2 | H-UWA-ACSMGT-CL-26508-UW Rules Authority Level - New Business & Endorsements |  | Property | Program | Ready for IT Team Review | 10000 | WH46 | 593043 |  | NONE | CL | CL | TRUE | Exigen_Sprint_19_SZV |  |  | Group 04 | Access Management - UW Rules Override | General | TRUE |  | 26508 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586898 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 1.5 | 3 | H-CONV-SUP-CA :26331 : Generate Renewal Offer Cover Letter Mortgagee Bill form 61 5155 - RETIRED |  | Property | Program | Ready for IT Team Review | 10000 |  | 593043 |  | NONE | NONE | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 01 | NONE | NONE | TRUE |  | 26331 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
589302 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | H-BND-ELGSCH-CCL | QA Approved | 1 | 2 | H-BND-ELGSCH-CCL 22531:Determine Eligibility Secondary/Seasonal home v3 |  | Property | Program | Ready for IT Team Review | 10000 | WH46 | 593043 |  | NONE | CCL | CCL | TRUE | IE_Sprint_19_PHX-2 |  |  | Group 01 | Determine Eligibility | General | TRUE |  | 22531 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
587117 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-INT-AAAMEM-CA | Test Execution Complete | 2 | 2 | H-INT-AAAMEM-CA-25723-Capture AAA Membership |  | Property | Program | Ready for IT Team Review | 10000 | UW46 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 01 | Integration - General | General | TRUE |  | 25723 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
587148 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-UWA-ACSMGT-CA | Test Execution Complete | 4 | 2 | H-UWA-ACSMGT-CA-26507-UW Rules Authority Level - New Business |  | Property | Program | Ready for IT Team Review | 10000 | WH46 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 03 | Access Management - UW Rules Override | General | TRUE |  | 26507 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
589306 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-BND-LIADED-CA | QA Approved | 1 | 2 | H-BND-LIADED-CA 24586:Validate Liability Limit and Deductible for Multiple Primary v2 |  | Property | Program | Ready for IT Team Review | 10000 | WH46 | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 01 | Determine Coverage | General | TRUE |  | 24586 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586906 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 4 | 3 | H-CONV-SUP-CA: 26327 :Generate Renewal Reminder (Mortgagee) form 61 0071_RETIRED |  | Property | Program | Ready for IT Team Review | 10000 |  | 593043 |  | NONE | NONE | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 01 | NONE | NONE | TRUE |  | 26327 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586623 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-WU64CA-CA | Test Execution Complete | 2 | 2 | C-DOC-WU64CA-CA 25734:Generate WU64CA Expiration Notice V03 |  | Property | Program | Ready for IT Team Review | 10000 | CR MO030 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 02 | Forms | Forms | TRUE |  | 25734 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
589297 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | H-BND-VALMULTIPRIM-CCL | Test Execution Complete | 1 | 2 | H-BND-VALMULTIPRIM-CCL: 24729 Bind Policy - Validate Multiple Primary Dwelling v2 |  | Property | Program | Ready for IT Team Review | 10000 | WH46 | 593043 |  | NONE | CCL | CCL | TRUE | Exigen_Sprint_19_DNK |  |  | Group 02 | Determine Eligibility | General | TRUE |  | 24729 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586897 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-PRERENCNV-CA | Test Execution Complete | 2.5 | 2 | C-DOC-PRERENCNV-CA Generate Pre-renewal form 61 5151 V02 |  | Property | Program | Ready for IT Team Review | 10000 | WI0208 CR04 | 593043, 566291 |  | NONE | NONE | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 03 | NONE | NONE | TRUE |  | 26407 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
587150 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-TSK-TASK-CA | Test Execution Complete | 11 | 2 | H-TSK-TASK-CA-25736-Task Management - New Business & Endorsements |  | Property | Program | Ready for IT Team Review | 10000 | UW46 & WH46 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_RIX |  |  | Group 04 | Task Management - New Business | General | TRUE |  | 25736 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586905 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-RENREM-CA | Test Execution Complete | 3 | 2 | C-DOC-WUNECACNV-CA 26530:Renewal WUNECA Insurance Renewal Reminder (non-Escrow Payment) V02 |  | Property | Program | Ready for IT Team Review | 10000 | WI0208 CR04 | 566291 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 03 | Forms | Forms | TRUE |  | 26530 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586891 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-AHRBXX-CA | Test Execution Complete | 6 | 3 | C-DOC-AHRBXX-CA Generate AHRBXX Renewal Bill |  | Property | Program | Ready for IT Team Review | 10000 |  | 593043 |  | NONE | NONE | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 04 | NONE | NONE | TRUE |  | 26446 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
500517 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-BND-ELGAE6-CA | QA Approved | 2.5 | 2 | H-BND-ELGAE6-CA: 25090:Determine Eligibility Automated Exception 6 v2 |  | Property | Program | Ready for IT Team Review | 10000 | CR UW41 | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 01 | Determine Eligibility | Create New Policy | TRUE | pas8.1 | 25090 | Unplanned | Unplanned | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 | Unplanned | Sprint 19
499274 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 2 | 3 | H-CONV-SUP-CA: 25434: Generate Property Installment Bill form 61 6129 _RETIRED |  | Property | Program | Ready for IT Team Review | 10000 |  | 593043 |  | NONE | NONE | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 03 | NONE | NONE | TRUE | conv | 25434 | Unplanned | Unplanned | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 | Unplanned | Sprint 19
452300 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-INT-CLAIMS-CA | Cancelled | 4 | 3 | H-INT-CLAIMS-CA 25186:Internal Claims – Batch | WI0191 CR03 | Property | Program | Ready for IT Team Review | 10000 | WI0191 CR03 | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | NONE | Integration - General | Conversion | TRUE | conv | 25186 | Unplanned | Unplanned | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 | Unplanned | Sprint 19
589298 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | H-PRI-PRIMPERC-CCL | QA Approved | 3.5 | 2 | H-PRI-PRIMPERC-CCL 24400:Capture percentage usage for multiple Primary HO policy v2 |  | Property | Program | Ready for IT Team Review | 10000 | WH46 | 593043 |  | NONE | CCL | CCL | TRUE | IE_Sprint_19_PHX-2 |  |  | Group 01 | Capture Applicant Info | General | TRUE |  | 24400 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
589311 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-AHTPC-CA | Test Execution Complete | 3 | 2 | C-DOC-AHTPC-CA 26300: Generate Third Party Designee Cover Page v3 |  | Property | Program | Ready for IT Team Review | 10000 | CRMO031/30 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 04 | Forms | Forms | TRUE |  | 26300 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
557388 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-PCQ-COVHO6-CA | QA Approved | 2 | 2 | H-PCQ-COVHO6-CA 24705: Determine Coverage HO-6 v3 |  | Property | Program | Ready for IT Team Review | 10000 | CR F0128 | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 01 | Determine Coverage | General | TRUE |  | 24705 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
587157 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-INT-MEM-UT | QA Approved | 2 | 2 | H-INT-MEM-UT- 25838: AAA Membership V02 |  | Property | Program | Ready for IT Team Review | 10000 | UW46 | 593043 |  | NONE | UT | UT | TRUE | Exigen_Sprint_19_SZV |  |  | Group 01 | Capture Membership Info | NONE | TRUE |  | 25838 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586890 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-INT-MOVPOLCNV-CA | Test Execution Complete | 3 | 3 | C-INT-MOVPOLCNV-CA 27167: Move Policy from one customer to another |  | Property | Program | Ready for IT Team Review | 10000 | WI0162; WI0208 CR04; | 593043; 566291; 596890 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 03 | Integration - General | NONE | TRUE |  | 27167 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586887 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-CONV-HMEBNK-CA | Test Execution Complete | 3 | 3 | 26489:H-CONV-HMEBNK-CA - Home Banking feed |  | Property | Program | Ready for IT Team Review | 10000 |  | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 01 | Integration - Renewal | NONE | TRUE |  | 26489 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586626 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-BFC-CA | Blocked | 3 | 2 | C-DOC-BFC-CA 26204: BFC Requirements and Print Order v3 |  | Property | Program | In IT Team Review | 10000 | CR MO023/030/031 | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 | Blocked from QA |  | Group 04 | Forms | Other - Document Management | TRUE |  | 26204 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586588 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-WU67CA-CA | Test Execution Complete | 3 | 2 | C-DOC-WU67CA-CA 25418:Generate Lapse Notice-Eligible for Reinstatement v3 |  | Property | Program | Ready for IT Team Review | 10000 | CR MO031 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 01 | Forms | Forms | TRUE |  | 25418 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586845 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-REN-AUTOINF-CA | Test Execution Complete | 2 | 2 | H-REN-AUTOINF-CA 25380:Apply Inflation Guard CPI HO4 v2 |  | Property | Program | Ready for IT Team Review | 10000 | F0128 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_DNK |  |  | Group 02 | Renewal | Renew Policy | TRUE |  | 25380 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586620 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-AH67XX-CA | Test Execution Complete | 4 | 3 | C-DOC-AH67XX-CA 26252:Generate Lapse Notice-Eligible for Reinstatement |  | Property | Program | In IT Team Review | 10000 | CR MO031 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 02 | Forms | Forms | TRUE |  | 26252 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586893 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 3 | 3 | H-CONV-SUP-CA :26293: Generate Expiration Notice form 61 6533_RETIRED |  | Property | Program | Ready for IT Team Review | 10000 | CRMO048 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 02 | NONE | NONE | TRUE |  | 26293 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586622 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-AH64XX-CA | Test Execution Complete | 4 | 3 | C-DOC-AH64XX-CA 26203:Generate AH64XX Expiration Notice |  | Property | Program | Ready for IT Team Review | 10000 | MO030 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 03 | Forms | Forms | TRUE |  | 26203 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
408227 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-DOC-RENREM-CA | QA Approved | 2 | 2 | H-DOC-RENREM-CA 25176:Renewal WURRCA Insurance Renewal Reminder v2 |  | Property | Program | Ready for IT Team Review | 10000 | WI0208 CR04 | 593043, 566291 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 02 | Forms | Forms | TRUE |  | 25176 | Unplanned | Unplanned | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 | Unplanned | Sprint 19
587156 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-BND-ELGMBR-UT | QA Approved | 3 | 2 | H-BND-ELGMBR-UT 25837 : Determine Eligibility - Membership v03 |  | Property | Program | Ready for IT Team Review | 10000 | UW46 | 593043 |  | NONE | UT | UT | TRUE | Exigen_Sprint_19_SZV |  |  | Group 01 | Capture Membership Info | NONE | TRUE |  | 25837 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
591571 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | P-BND-ELGNAEUW-CA | QA Approved | 6 | 2 | P-BND-ELGNAEUW-26028 CA PUP Underwriting rules with neither Automatic Exception model nor UW Approval v03 |  | Property | Program | Ready for IT Team Review | 10000 | UW46 ; UW42 | 593043 ; 596879 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 04 | PUP - New Business | General | TRUE |  | 26028 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
587114 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | H-TSK-TASK-CL | QA Approved | 7 | 2 | H-TSK-TASK-CL-25746-Task Management - New Business & Endorsements |  | Property | Program | Ready for IT Team Review | 10000 | UW46 & WH46 | 593043 |  | NONE | CL | CL | TRUE | Exigen_Sprint_19_RIX |  |  | Group 04 | Task Management - New Business | General | TRUE |  | 25746 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
557691 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-PRI-PROPVAL-CA | QA Approved | 2 | 2 | H-PRI-PROPVAL-CA 25814: Capture Property Value v3 |  | Property | Program | Ready for IT Team Review | 10000 | CR F0128 | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-2 |  |  | Group 02 | Capture Property Info | Create New Policy | TRUE |  | 25814 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
589304 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | H-BND-LIADED-CL | QA Approved | 1 | 2 | H-BND-LIADED-CL-22851-Validate Liability Limit and Deductible for Multiple Primary v3 |  | Property | Program | Ready for IT Team Review | 10000 | WH46 | 593043 |  | NONE | CL | CL | TRUE | Exigen_Sprint_19_DNK |  |  | Group 02 | Determine Coverage | General | TRUE |  | 22851 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586882 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-DOC-615154CNV-CA | Test Execution Complete | 1.5 | 3 | H-DOC-615154CNV-CA 26445:Generate Renewal Offer Cover Letter Mortgagee Bill form 61 5154 |  | Property | Program | Ready for IT Team Review | 10000 | WI0208 CR04 | 566291 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-2 |  |  | Group 04 | Forms | Forms | TRUE |  | 26445 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
589294 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | H-PCQ-PRIMDWELL-CCL | Test Execution Complete | 2 | 2 | H-PCQ-PRIMDWELL-CCL 24401:Calculate Premium - Check Primary Dwelling v2 |  | Property | Program | Ready for IT Team Review | 10000 | WH46 | 593043 |  | NONE | CCL | CCL | TRUE | Exigen_Sprint_19_DNK |  |  | Group 02 | Capture Property Info | General | TRUE |  | 24401 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586625 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | C-DOC-AHCWXX-CCL | Test Execution Complete | 4 | 3.5 | C-DOC-AHCWXX-CCL 26248: Generate AHCWXX Cancel Withdraw Notice Document |  | Property | Program | Ready for IT Team Review | 10000 | MO023 | 593043 |  | NONE | CCL | CCL | TRUE | Exigen_Sprint_19_SZV |  |  | Group 02 | Forms | Forms | TRUE |  | 26248 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
587159 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | H-BND-ELGDEST-CL | QA Approved | 2 | 2 | H-BND-ELGDEST-CL 25835:Determine Eligibility - Detached Structure v5 |  | Property | Program | Ready for IT Team Review | 10000 | UW46 | 593043 |  | NONE | CL | CL | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 01 | Determine Eligibility | NONE | TRUE |  | 25835 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
557373 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-PCQ-COVHO4-CA | Test Execution Complete | 1.5 | 2 | H-PCQ-COVHO4-CA 24672: Determine Coverage HO-4 v4 |  | Property | Program | Ready for IT Team Review | 10000 | CR F0128 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_DNK |  |  | Group 03 | Determine Coverage | General | TRUE |  | 24672 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
447507 | S20 Kickoff | Current RTC | JIRA Analyzed | Story - Integration | WI0162 CA HDES Conversion |  | Blocked | 0 | 0 | CA HDES Conversion Testing - BCT CEA Policy Updates | WI0211 IT03, WI0173 CR11/WI0174 CR00, WI0173 CR03 | Property | Integration | Not Started | 80000 | WI0211 IT03, WI0173 CR11/WI0174 CR00, WI0173 CR03 |  |  | NONE | CCL | CA | TRUE | Integration_Sprint_20 | Blocked from QA |  | Group 02 | Integration - General | NONE | TRUE |  |  | Unplanned | PAS10 | PAS10 | 2016-08-05 12:00 | Unplanned | Unplanned | Unplanned | Sprint 20
587161 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-BND-ELGDEST-CA | QA Approved | 2 | 2 | H-BND-ELGDEST-CA 25834: Determine Eligibility - Detached Structure v2 |  | Property | Program | Ready for IT Team Review | 10000 | UW46 | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 02 | NONE | NONE | TRUE |  | 25834 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
499278 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 2 | 3 | H-CONV-SUP-CA: 25430: Generate Property Installment Bill (Auto Pay) form 61 6130 _RETIRED |  | Property | Program | Ready for IT Team Review | 10000 |  | 593043 |  | NONE | NONE | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 03 | NONE | NONE | TRUE | conv | 25430 | Unplanned | Unplanned | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 | Unplanned | Sprint 19
499281 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-DOC-610069CNV-CA | Test Execution Complete | 3 | 2 | H-DOC-610069CNV-CA 25358:Generate Renewal Reminder (Home Banking) form 61 0069 V02 |  | Property | Program | Ready for IT Team Review | 10000 | WI0208 CR04 | 566291 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 03 | Forms | Forms | TRUE | conv | 25358 | Unplanned | Unplanned | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 | Unplanned | Sprint 19
586818 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-REN-AUTOINF-CA | Test Execution Complete | 3 | 2 | H-REN-AUTOINF-CA 25378: Apply Inflation Guard factors HO6 |  | Property | Program | Ready for IT Team Review | 10000 | F0128 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_DNK |  |  | Group 03 | Renewal | Renew Policy | TRUE |  | 25378 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
591572 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | P-BND-ELGNAEUW-UT | QA Approved | 1 | 2 | P-BND-ELGNAEUW-26010 UT-Underwriting rules with neither Automatic Exception model nor UW Approval v03 |  | Property | Program | Ready for IT Team Review | 10000 | UW46 | 593043 |  | NONE | UT | UT | TRUE | Exigen_Sprint_19_DNK |  |  | Group 02 | NONE | NONE | TRUE |  | 26010 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586903 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 2 | 3 | H-CONV-SUP-CA: 26329:Generate Renewal Reminder (Mortgagee) form 61 5156_RETIRED |  | Property | Program | Ready for IT Team Review | 10000 |  | 593043 |  | NONE | NONE | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 01 | NONE | NONE | TRUE |  | 26329 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586895 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-DOC-RENREM-CA | Test Execution Complete | 3 | 3 | H-DOC-RENREM-CA-Generate Renewal Offer Cover Letter (HO) form 61 5152 |  | Property | Program | In IT Team Review | 10000 |  | 593043 |  | NONE | NONE | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 04 | NONE | NONE | TRUE |  | 26413 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
589328 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-PRTODR-CA | Test Execution Complete | 2 | 2 | 26783: C-DOC-PRTODR-CA Generate Story for NB Amend Ren and Rev Ren Forms in correct order of packet |  | Property | Program | In IT Team Review | 10000 |  | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | Group 04 | Forms | Forms | TRUE |  | 26783 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
586624 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | C-DOC-WUCWCA-CA | Test Execution Complete | 3 | 2 | C-DOC-WUCWCA-CA 26148:Generate WUCWCA Withdrawn Notice Document v2 |  | Property | Program | Ready for IT Team Review | 10000 | MO023 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 03 | Forms | Forms | TRUE |  | 26148 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
447516 | S20 Kickoff | Current RTC | JIRA Analyzed | Story - Integration | WI0162 CA HDES Conversion |  | Test Execution Complete | 0 | 0 | CA HDES Conversion Testing - Payment Central | WI0211 IT03, WI0173 CR11/WI0174 CR00, WI0173 CR03 | Property | Integration | Not Started | 80000 | WI0211 IT03, WI0173 CR11/WI0174 CR00, WI0173 CR03 |  |  | NONE | CA | CA | TRUE | Integration_Sprint_20 |  |  | Group 00 | NONE | NONE | TRUE |  |  | Unplanned | PAS10 | PAS10 | 2016-08-05 12:00 | Unplanned | Unplanned | Unplanned | Sprint 20
452307 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | P-INT-CLAIMS-CA | Cancelled | 6 | 3 | P-INT-CLAIMS-CA 25516: US CONV PUP Internal Claims – Batch | WI0191 CR03 | Property | Program | Ready for IT Team Review | 10000 | WI0191 CR03 | 593043 |  | NONE | CA | CA | TRUE | IE_Sprint_19_PHX-3 |  |  | NONE | Integration - General | Conversion | TRUE | conv | 25516 | Unplanned | Unplanned | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 | Unplanned | Sprint 19
587158 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Common Library | WI0162 CA HDES Conversion | H-BND-ELGLOGH-CCL | Test Execution Complete | 4 | 2 | H-BND-ELGLOGH-CCL 25836 : Determine Eligibility - Log Home v05 |  | Property | Program | Ready for IT Team Review | 10000 | UW46 | 593043 |  | NONE | CCL | CCL | TRUE | Exigen_Sprint_19_SZV |  |  | Group 03 | Determine Eligibility | General | TRUE |  | 25836 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19
490382 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 4 | 2 | H-CONV-SUP-CA 25179:Suppress form Generation for conversion policies |  | Property | Program | Ready for IT Team Review | 10000 |  | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_SZV |  |  | Group 04 | Forms | Forms | TRUE |  | 25179 | Unplanned | Unplanned | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 | Unplanned | Sprint 19
557724 | S19 Kickoff | Current RTC | JIRA Analyzed | Story - Delta | WI0162 CA HDES Conversion | H-PRI-CAPPV-CA | Test Execution Complete | 1.5 | 2 | H-PRI-CAPPV-CA 25377: Capture Property Value - HO4 v2 |  | Property | Program | In IT Team Review | 10000 | CR F0128 | 593043 |  | NONE | CA | CA | TRUE | Exigen_Sprint_19_DNK |  |  | Group 02 | Capture Property Info | General | TRUE |  | 25377 |  |  | PAS10 | 2016-06-27 12:00 | PAS10 | PAS10 |  | Sprint 19

## JIRA_26_09
Custom field (RTC ID) | Issue Type | Issue key | Issue id | Part of Current RTC? | Part of JIRA? | Summary | High level summary | Custom field (RRC ID) | Status | Custom field (Release) | Reporter | Created | Custom field (RTC ID) | Custom field (Work Item Category) | Assignee | Updated | Custom field (Design Author) | Time Spent | Custom field (L1) | Custom field (L1) | Custom field (L1) | Custom field (L2) | Custom field (L2) | Custom field (L2) | Custom field (L2) | Custom field (Privilege) | Custom field (AC No) | Custom field (AC Count) | Custom field (Scenario Task Type) | Custom field (Pattern ID / Scenario ID/ TestCase ID / Test Case Name) | Custom field (Regression Scope) | Custom field (Regression Thread) | Custom field (Regression Thread) | Custom field (Regression Thread) | Custom field (FormID) | Custom field (Reason for not in Regression Scope) | Custom field (Product) | Custom field (Product) | Custom field (Product) | Custom field (Product) | Custom field (Product) | Custom field (RSG Category) | Custom field (Regression Reusability) | Custom field (RCA Impact) | Custom field (Parent RRC ID) | Custom field (Delta State) | Custom field (Time Spent in Design Review (hrs)) | Labels | Custom field (Target Sprint) | Custom field (RTC Status) | Custom field (Verified on Date) | Custom field (Scenario Thread) | Custom field (Reviewer - Design) | Custom field (Delta AC/TC Count) | Custom field (Total AC/TC Count) | Custom field (Analysis Priority)
447516 | Regression Analysis | DEMO-49098 | 184259 | Current RTC | JIRA Analyzed | CA HDES Conversion Testing - Payment Central |  |  | Integration Analysis | PAS10 |  | 2016-08-18 19:40 | 447516 | WI0162 CA HDES Conversion | vjetty | 2016-09-19 12:26 | harsabhatia | [14 empty] | Integration | [13 empty] | CA |  |  | Sprint 20 | Test Execution Complete | [5 empty] | Group 00
447507 | Regression Analysis | DEMO-49097 | 184258 | Current RTC | JIRA Analyzed | CA HDES Conversion Testing - BCT CEA Policy Updates |  |  | BCT | PAS10 |  | 2016-08-18 19:40 | 447507 | WI0162 CA HDES Conversion | ssanka | 2016-09-19 12:27 | harsabhatia | [14 empty] | BCT | [13 empty] | CA |  |  | Sprint 20 | In Testing | [5 empty] | Group 02
557724 | Regression Analysis | DEMO-44339 | 178160 | Current RTC | JIRA Analyzed | H-PRI-CAPPV-CA 25377: Capture Property Value - HO4 v2 | added | 25923 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 557724 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 11100 | Renewal | Sales | Service | Automated Renewal | Define Property | Endorsement | Rewrite |  |  | 5 |  |  | No | None |  |  |  | Capturing Information | HO4 |  |  |  |  | UI Validation-Field formats, limits and list of values |  | May be | 25377 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-20 17:34
452307 | Regression Analysis | DEMO-44338 | 178159 | Current RTC | JIRA Analyzed | P-INT-CLAIMS-CA 25516: US CONV PUP Internal Claims ? Batch |  | 25516 | Integration Analysis | PAS10 | vekurapati | 2016-06-28 16:15 | 452307 | WI0162 CA HDES Conversion | vjetty | 2016-09-15 15:44 | sichavan | [28 empty] | CA |  |  | Sprint 19 | Cancelled
589328 | Regression Analysis | DEMO-44337 | 178158 | Current RTC | JIRA Analyzed | 26783: C-DOC-PRTODR-CA Generate Story for NB Amend Ren and Rev Ren Forms in correct order of packet |  | 26783 | HVT | PAS10 | vekurapati | 2016-06-28 16:15 | 589328 | WI0162 CA HDES Conversion | shrbanerjee | 2016-09-15 15:44 | sichavan | [14 empty] | HVT | [13 empty] | CA |  |  | Sprint 19 | Test Execution Complete
499278 | Regression Analysis | DEMO-44336 | 178157 | Current RTC | JIRA Analyzed | H-CONV-SUP-CA: 25430: Generate Property Installment Bill (Auto Pay) form 61 6130 _RETIRED | added | 25427 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 499278 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | vdixit | 6900 | Document Fulfillment |  |  | Generate Document | [5 empty] | 1 |  |  | Yes | Manual |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 |  | Document Generation-Negative Approach Validation |  | No | 25430 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-07-22 02:48
586625 | Regression Analysis | DEMO-44335 | 178156 | Current RTC | JIRA Analyzed | C-DOC-AHCWXX-CCL 26248: Generate AHCWXX Cancel Withdraw Notice Document | added | 26253 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 586625 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 9120 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 6 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Mandatory Forms |  | Yes | 26248 | CCL |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-22 05:59
589294 | Regression Analysis | DEMO-44334 | 178155 | Current RTC | JIRA Analyzed | H-PCQ-PRIMDWELL-CCL 24401:Calculate Premium - Check Primary Dwelling v2 | To be checked | 26018 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 589294 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | cnigam | 6360 | Renewal | Service |  | Automated Renewal | Endorsement | Rewrite |  |  |  | 3 |  |  | No | None |  |  |  | Error message validation | HO3 | HO4 | HO6 |  |  | Error Message Validation-Warning messages |  | May be | 24401 | CCL |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-28 04:49
589304 | Regression Analysis | DEMO-44333 | 178154 | Current RTC | JIRA Analyzed | H-BND-LIADED-CL-22851-Validate Liability Limit and Deductible for Multiple Primary v3 |  | 26019 | Non-CA | PAS10 | vekurapati | 2016-06-28 16:15 | 589304 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | harsabhatia | 3300 | Conversions |  |  | Define Quote Policy | [5 empty] | 1 |  |  | No | None |  |  |  | Striked out Acceptance Criterion | HO3 | HO4 | HO6 |  |  | Rules-UW Rules |  | May be | 22851 | CL |  |  | Sprint 19 | QA Approved | 2016-08-04 05:31
587114 | Regression Analysis | DEMO-44332 | 178153 | Current RTC | JIRA Analyzed | H-TSK-TASK-CL-25746-Task Management - New Business & Endorsements |  | 26039 | Non-CA | PAS10 | vekurapati | 2016-06-28 16:15 | 587114 | WI0162 CA HDES Conversion | sichavan | 2016-09-16 18:49 | harsabhatia | 11400 | Task Management |  |  | Manage Tasks | [5 empty] | 7 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 |  | Rules-UW Rules |  | No | 25746 | CL |  |  | Sprint 19 | QA Approved | 2016-09-16 08:19
587156 | Regression Analysis | DEMO-44331 | 178152 | Current RTC | JIRA Analyzed | H-BND-ELGMBR-UT 25837 : Determine Eligibility - Membership v03 |  | 25865 | Non-CA | PAS10 | vekurapati | 2016-06-28 16:15 | 587156 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | cnigam | 3900 | Renewal | Sales | Service | Eligibility | [5 empty] | 4 |  |  | No | None |  |  |  | Covered as a part of Other US | DP3 | HO3 | HO4 | HO6 |  | Policy Features-Define Quote/Policy |  | Yes | 25837 | UT |  |  | Sprint 19 | QA Approved | 2016-08-01 04:59
586893 | Regression Analysis | DEMO-44330 | 178151 | Current RTC | JIRA Analyzed | H-CONV-SUP-CA :26293: Generate Expiration Notice form 61 6533_RETIRED | added | 26296 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 586893 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | cnigam | 5580 | Document Fulfillment |  |  | Generate Document | [5 empty] | 1 |  |  | Yes | RBT |  |  |  | N/A | HO3 | HO4 | HO6 |  |  | Document Generation-Negative Approach Validation |  | No | 26293 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-01 04:00
586620 | Regression Analysis | DEMO-44329 | 178150 | Current RTC | JIRA Analyzed | C-DOC-AH67XX-CA 26252:Generate Lapse Notice-Eligible for Reinstatement | added | 26255 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 586620 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 7380 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 2 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Mandatory Forms |  | Yes | 26252 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-21 04:18
586845 | Regression Analysis | DEMO-44328 | 178149 | Current RTC | JIRA Analyzed | H-REN-AUTOINF-CA 25380:Apply Inflation Guard CPI HO4 v2 | added | 25769 | WI Analysis | PAS10 | vekurapati | 2016-06-28 16:15 | 586845 | WI0162 CA HDES Conversion | harsabhatia | 2016-09-15 15:44 | harsabhatia | [13 empty] | Yes | [5 empty] | HO4 | [7 empty] | 25380 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete
586887 | Regression Analysis | DEMO-44327 | 178148 | Current RTC | JIRA Analyzed | 26489:H-CONV-HMEBNK-CA - Home Banking feed |  | 26494 | Integration Analysis | PAS10 | vekurapati | 2016-06-28 16:15 | 586887 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | harsabhatia | 1380 | Conversions |  |  | DB Tables | [5 empty] | 0 |  |  | Yes | Integration |  |  |  | Integration | HO3 | HO4 | HO6 |  |  | Billing & Payments-Exceptions |  | No | 26489 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-04 08:18
587157 | Regression Analysis | DEMO-44326 | 178147 | Current RTC | JIRA Analyzed | H-INT-MEM-UT- 25838: AAA Membership V02 |  | 25866 | Non-CA | PAS10 | vekurapati | 2016-06-28 16:15 | 587157 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | cnigam | 7500 | Sales |  |  | Eligibility | [5 empty] | 2 |  |  | Yes | None |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 |  | Policy Features-Define Quote/Policy |  | Yes | 25838 | UT |  |  | Sprint 19 | QA Approved | 2016-08-03 07:30
589311 | Regression Analysis | DEMO-44325 | 178146 | Current RTC | JIRA Analyzed | C-DOC-AHTPC-CA 26300: Generate Third Party Designee Cover Page v3 | added | 26304 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 589311 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 7620 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 4 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Mandatory Forms |  | Yes | 26300 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-21 02:45
589298 | Regression Analysis | DEMO-44324 | 178145 | Current RTC | JIRA Analyzed | H-PRI-PRIMPERC-CCL 24400:Capture percentage usage for multiple Primary HO policy v2 | added | 25839 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 589298 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-16 23:57 | harsabhatia | 3600 | Conversions |  |  | Define Quote Policy | [5 empty] | 0 |  |  | No | None |  |  |  | Striked out Acceptance Criterion | HO3 | HO4 | HO6 |  |  | UI Validation-Mandatory fields |  | Yes | 24400 | CCL |  | HDES_Generic_US | Sprint 19 | QA Approved | 2016-08-07 15:50
452300 | Regression Analysis | DEMO-44323 | 178144 | Current RTC | JIRA Analyzed | H-INT-CLAIMS-CA 25186:Internal Claims ? Batch |  | 25186 | Integration Analysis | PAS10 | vekurapati | 2016-06-28 16:15 | 452300 | WI0162 CA HDES Conversion | vjetty | 2016-09-15 15:44 | sichavan | [28 empty] | CA |  |  | Sprint 19 | Cancelled
499274 | Regression Analysis | DEMO-44322 | 178143 | Current RTC | JIRA Analyzed | H-CONV-SUP-CA: 25434: Generate Property Installment Bill form 61 6129 _RETIRED | added | 25431 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 499274 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | vdixit | 3000 | Document Fulfillment |  |  | Generate Document | [5 empty] | 1 |  |  | No | None |  |  |  | Covered as a part of Other US | DP3 | HO3 | HO4 | HO6 |  | Document Generation-Mandatory Forms |  | No | 25434 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-07-20 13:08
587150 | Regression Analysis | DEMO-44321 | 178142 | Current RTC | JIRA Analyzed | H-TSK-TASK-CA-25736-Task Management - New Business & Endorsements | added | 25741 | Secondary Review | PAS10 | vekurapati | 2016-06-28 16:15 | 587150 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | cnigam | 7440 | Task Management |  |  | Manage Tasks | [5 empty] | 7 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 |  | Exclusions |  | No | 25736 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete
586905 | Regression Analysis | DEMO-44320 | 178141 | Current RTC | JIRA Analyzed | C-DOC-WUNECACNV-CA 26530:Renewal WUNECA Insurance Renewal Reminder (non-Escrow Payment) V02 | added | 26531 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 586905 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 4860 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 2 |  | CA-CP-102 | Yes | Automation |  |  | WUNECA 09 11 | N/A | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Mandatory Forms |  | Yes | 26530 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-20 17:48
586897 | Regression Analysis | DEMO-44319 | 178140 | Current RTC | JIRA Analyzed | C-DOC-PRERENCNV-CA Generate Pre-renewal form 61 5151 V02 | added | 26408 | Closed | PAS10 | vekurapati | 2016-06-28 16:15 | 586897 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | vdixit | 10020 | Document Fulfillment |  |  | Generate Document | [5 empty] | 6 |  |  | Yes | Automation | HVT | Manual |  | N/A | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Mandatory Forms |  | No | 26407 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-03 08:10
589297 | Regression Analysis | DEMO-44318 | 178139 | Current RTC | JIRA Analyzed | H-BND-VALMULTIPRIM-CCL: 24729 Bind Policy - Validate Multiple Primary Dwelling v2 | NA | 26013 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 589297 | WI0162 CA HDES Conversion | sichavan | 2016-09-17 | harsabhatia | 2400 | Sales, Service |  |  | Define Quote Policy | [5 empty] | 6 |  |  | No | None |  |  |  | Striked out Acceptance Criterion | HO3 | HO4 | HO6 |  |  | Error Message Validation-Error Message that can not be over-ridden |  | May be | 24729 | CCL |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-04 08:53
586623 | Regression Analysis | DEMO-44317 | 178138 | Current RTC | JIRA Analyzed | C-DOC-WU64CA-CA 25734:Generate WU64CA Expiration Notice V03 | added | 26251 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586623 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 6300 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 2 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Negative Approach Validation |  | Yes | 25734 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-24 09:05
589306 | Regression Analysis | DEMO-44316 | 178137 | Current RTC | JIRA Analyzed | H-BND-LIADED-CA 24586:Validate Liability Limit and Deductible for Multiple Primary v2 | NA | 26041 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 589306 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | cnigam | 1920 | Sales |  |  | Define Quote Policy | [5 empty] | 4 |  |  | No | None |  |  |  | Striked out Acceptance Criterion | HO3 | HO4 | HO6 |  |  | Policy Features-Define Quote/Policy |  | No | 24586 | CA |  | HDES_Generic_US | Sprint 19 | QA Approved | 2016-08-22 06:49
587117 | Regression Analysis | DEMO-44315 | 178136 | Current RTC | JIRA Analyzed | H-INT-AAAMEM-CA-25723-Capture AAA Membership | added | 25725 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 587117 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-17 00:02 | harsabhatia | 2280 | [9 empty] | 3 |  |  | No |  |  |  |  | Capturing Information | DP3 | HO3 | HO4 | HO6 |  | UI Validation-Field formats, limits and list of values |  | No | 25723 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-26 01:18
587148 | Regression Analysis | DEMO-44314 | 178135 | Current RTC | JIRA Analyzed | H-UWA-ACSMGT-CA-26507-UW Rules Authority Level - New Business | To be checked | 26514 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 587148 | WI0162 CA HDES Conversion | vdixit | 2016-09-15 15:44 | harsabhatia | 7800 | Agency Management |  |  | Manage Agent Permissions | [5 empty] | 3 |  |  | No | None |  |  |  | Constituent US not in scope | DP3 | HO3 | HO4 | HO6 |  | Privileges-Validation of Business Critical Privileges (Container User Stories) |  | No | 26507 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-09-06 05:13
589302 | Regression Analysis | DEMO-44313 | 178134 | Current RTC | JIRA Analyzed | H-BND-ELGSCH-CCL 22531:Determine Eligibility Secondary/Seasonal home v3 | added | 25877 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 589302 | WI0162 CA HDES Conversion | sichavan | 2016-09-17 00:04 | vdixit | 2700 | Sales |  |  | Eligibility | [5 empty] | 2 |  |  | Yes | None |  |  |  | N/A | HO3 | HO4 | HO6 |  |  | Error Message Validation-Error Messages that can be over-ridden |  | May be | 22531 | CCL |  | HDES_Generic_US | Sprint 19 | QA Approved | 2016-08-04 08:28
586898 | Regression Analysis | DEMO-44312 | 178133 | Current RTC | JIRA Analyzed | H-CONV-SUP-CA :26331 : Generate Renewal Offer Cover Letter Mortgagee Bill form 61 5155 - RETIRED | added | 26332 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586898 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | vdixit | 4800 | Document Fulfillment |  |  | Generate Document | [5 empty] | 3 |  |  | Yes | Manual |  |  |  | N/A | HO3 | HO4 | HO6 |  |  | Document Generation-Mandatory Forms |  | No | 26331 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-07-22 06:12
490382 | Regression Analysis | DEMO-44311 | 178132 | Current RTC | JIRA Analyzed | H-CONV-SUP-CA 25179:Suppress form Generation for conversion policies | To be checked | 25177 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 490382 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | cnigam | 17880 | Document Fulfillment |  |  | Generate Document | [5 empty] | 11 |  |  | Yes | Automation |  |  |  | N/A | HO3 | HO4 | HO6 |  |  | Document Generation-Mandatory Forms |  | No | 25179 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-02 12:48
587158 | Regression Analysis | DEMO-44310 | 178131 | Current RTC | JIRA Analyzed | H-BND-ELGLOGH-CCL 25836 : Determine Eligibility - Log Home v05 | added | 25867 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 587158 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | harsabhatia | 4320 | Sales |  |  | Eligibility | [5 empty] | 6 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 |  |  |  | N/A |  | No | 25836 | CCL |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-26 02:37
586903 | Regression Analysis | DEMO-44309 | 178130 | Current RTC | JIRA Analyzed | H-CONV-SUP-CA: 26329:Generate Renewal Reminder (Mortgagee) form 61 5156_RETIRED | added | 26330 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586903 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | cnigam | 4680 | Document Fulfillment |  |  | Generate Document | [5 empty] | 1 |  |  | Yes | RBT |  |  | 61 5156 | N/A | HO3 | HO4 | HO6 |  |  | Document Generation-Negative Approach Validation |  | Yes | 26329 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-01 05:11
586624 | Regression Analysis | DEMO-44308 | 178129 | Current RTC | JIRA Analyzed | C-DOC-WUCWCA-CA 26148:Generate WUCWCA Withdrawn Notice Document v2 | added | 26212 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586624 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 128400 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 6 |  |  | Yes | Manual |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Negative Approach Validation |  | Yes | 26148 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-22 06:00
586895 | Regression Analysis | DEMO-44307 | 178128 | Current RTC | JIRA Analyzed | H-DOC-RENREM-CA-Generate Renewal Offer Cover Letter (HO) form 61 5152 | added | 26411 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586895 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 4320 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 2 |  |  | Yes | Automation |  |  |  | N/A | HO3 | HO4 | HO6 |  |  | Document Generation-Mandatory Forms |  | No | 26413 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-21 07:54
591572 | Regression Analysis | DEMO-44306 | 178127 | Current RTC | JIRA Analyzed | P-BND-ELGNAEUW-26010 UT-Underwriting rules with neither Automatic Exception model nor UW Approval v03 |  | 26011 | Non-CA | PAS10 | vekurapati | 2016-06-28 16:14 | 591572 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | cnigam | 8400 | Renewal | Sales | Service | Eligibility | [5 empty] | 3 |  |  | Yes | RBT |  |  |  | N/A | PUP |  |  |  |  | Rules-UW Rules |  | Yes | 26010 | UT |  |  | Sprint 19 | QA Approved | 2016-08-01 04:29
586818 | Regression Analysis | DEMO-44305 | 178126 | Current RTC | JIRA Analyzed | H-REN-AUTOINF-CA 25378: Apply Inflation Guard factors HO6 | added | 25798 | WI Analysis | PAS10 | vekurapati | 2016-06-28 16:14 | 586818 | WI0162 CA HDES Conversion | harsabhatia | 2016-09-15 15:44 | harsabhatia |  | Service |  |  | General Capability | [8 empty] | Yes | [5 empty] | HO6 | [7 empty] | 25378 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete
499281 | Regression Analysis | DEMO-44304 | 178125 | Current RTC | JIRA Analyzed | H-DOC-610069CNV-CA 25358:Generate Renewal Reminder (Home Banking) form 61 0069 V02 | added | 25356 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 499281 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | harsabhatia | 10020 | Conversions |  |  | Content Accuracy, Generate Documents / Triggers | [5 empty] | 6 |  |  | Yes | Automation | Manual | RBT |  | N/A | DP3 | HO3 | HO4 | HO6 |  | Document Generation-Mandatory Forms |  | No | 25358 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-03 07:27
587161 | Regression Analysis | DEMO-44303 | 178124 | Current RTC | JIRA Analyzed | H-BND-ELGDEST-CA 25834: Determine Eligibility - Detached Structure v2 | added | 25869 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 587161 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | harsabhatia | 6840 | Sales | Service |  | Eligibility | [5 empty] | 6 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 |  |  |  | Policy Features-Define Quote/Policy |  | No | 25834 | CA |  | HDES_Generic_US | Sprint 19 | QA Approved | 2016-08-28 04:43
557373 | Regression Analysis | DEMO-44302 | 178123 | Current RTC | JIRA Analyzed | H-PCQ-COVHO4-CA 24672: Determine Coverage HO-4 v4 | added | 24671 | Secondary Review | PAS10 | vekurapati | 2016-06-28 16:14 | 557373 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | harsabhatia | 3960 | Conversions |  |  | Define Coverages | [5 empty] | 8 |  |  | Yes | Automation |  |  |  | N/A | HO4 |  |  |  |  | Policy Features-Define Coverages |  | No | 24672 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete
587159 | Regression Analysis | DEMO-44301 | 178122 | Current RTC | JIRA Analyzed | H-BND-ELGDEST-CL 25835:Determine Eligibility - Detached Structure v5 |  | 25868 | Non-CA | PAS10 | vekurapati | 2016-06-28 16:14 | 587159 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | harsabhatia | 8880 | Renewal | Sales | Service | Eligibility | [5 empty] | 6 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 | HO6 |  |  | Rules-UW Rules |  | No | 25835 | CL |  |  | Sprint 19 | QA Approved | 2016-08-05 09:25
586882 | Regression Analysis | DEMO-44300 | 178121 | Current RTC | JIRA Analyzed | H-DOC-615154CNV-CA 26445:Generate Renewal Offer Cover Letter Mortgagee Bill form 61 5154 | added | 26532 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586882 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | harsabhatia | 10980 | Conversions |  |  | Content Accuracy, Generate Documents / Triggers | [5 empty] | 5 |  |  | Yes | Automation | RBT |  |  | N/A | DP3 | HO3 | HO6 |  |  | Document Generation-Mandatory Forms |  | No | 26445 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-19 08:33
557691 | Regression Analysis | DEMO-44299 | 178120 | Current RTC | JIRA Analyzed | H-PRI-PROPVAL-CA 25814: Capture Property Value v3 | added | 25815 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 557691 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | harsabhatia | 8040 | Sales | Service |  | Define Quote Policy | [5 empty] | 9 |  |  | No |  |  |  |  | Capturing Information | DP3 | HO3 | HO6 |  |  | UI Validation-Field formats, limits and list of values |  | No | 25814 | CA |  | HDES_Generic_US | Sprint 19 | QA Approved | 2016-08-28 05:26
591571 | Regression Analysis | DEMO-44298 | 178119 | Current RTC | JIRA Analyzed | P-BND-ELGNAEUW-26028 CA PUP Underwriting rules with neither Automatic Exception model nor UW Approval v03 | added | 26029 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 591571 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | harsabhatia | 3600 | [9 empty] | 6 |  |  | No | None |  |  |  | Error message validation | PUP |  |  |  |  | Error Message Validation-Helptext messages |  | No | 26028 | CA |  | HDES_Generic_US | Sprint 19 | QA Approved | 2016-08-23 05:52
408227 | Regression Analysis | DEMO-44297 | 178118 | Current RTC | JIRA Analyzed | H-DOC-RENREM-CA 25176:Renewal WURRCA Insurance Renewal Reminder v2 | added | 25174 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 408227 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 11160 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 2 |  |  | Yes | Automation |  |  | WURRCA | N/A | DP3 | HO3 | HO6 |  |  | Document Generation-Mandatory Forms |  | May be | 25176 | CA |  | HDES_Generic_US | Sprint 19 | QA Approved | 2016-08-28 05:39
586622 | Regression Analysis | DEMO-44296 | 178117 | Current RTC | JIRA Analyzed | C-DOC-AH64XX-CA 26203:Generate AH64XX Expiration Notice | added | 26210 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586622 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 11220 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 4 |  |  | Yes | Automation | Manual |  |  | N/A | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Mandatory Forms |  | May be | 26203 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-21 02:56
586588 | Regression Analysis | DEMO-44295 | 178116 | Current RTC | JIRA Analyzed | C-DOC-WU67CA-CA 25418:Generate Lapse Notice-Eligible for Reinstatement v3 | added | 25524 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586588 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 2580 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 3 |  |  | No | None |  |  |  | Covered as a part of Other US | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Negative Approach Validation |  | Yes | 25418 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-21 08:03
586626 | Regression Analysis | DEMO-44294 | 178115 | Current RTC | JIRA Analyzed | C-DOC-BFC-CA 26204: BFC Requirements and Print Order v3 |  | 26204 | HVT | PAS10 | vekurapati | 2016-06-28 16:14 | 586626 | WI0162 CA HDES Conversion | shrbanerjee | 2016-09-15 15:44 | sichavan | [14 empty] | HVT | [13 empty] | CA |  |  | Sprint 19 | Blocked
586890 | Regression Analysis | DEMO-44293 | 178114 | Current RTC | JIRA Analyzed | C-INT-MOVPOLCNV-CA 27167: Move Policy from one customer to another | added | 26541 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586890 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | harsabhatia | 9300 | Conversions |  |  | General Capability | [5 empty] | 7 |  | C-HO-HO6-CA-861-CNV | Yes | Manual |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 | PUP | UI Validation-Field formats, limits and list of values |  | No | 27167 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-17 06:02
557388 | Regression Analysis | DEMO-44292 | 178113 | Current RTC | JIRA Analyzed | H-PCQ-COVHO6-CA 24705: Determine Coverage HO-6 v3 | To be checked | 24704 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 557388 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | harsabhatia | 7020 | Conversions |  |  | Define Coverages | [5 empty] | 4 |  |  | No | Automation |  |  |  | UI validation | HO6 |  |  |  |  | Policy Features-Define Coverages |  | No | 24705 | CA |  | HDES_Generic_US | Sprint 19 | QA Approved | 2016-08-28 05:34
500517 | Regression Analysis | DEMO-44291 | 178112 | Current RTC | JIRA Analyzed | H-BND-ELGAE6-CA: 25090:Determine Eligibility Automated Exception 6 v2 | added | 25094 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 500517 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | harsabhatia | 9600 | Conversions |  |  | Eligibility | [5 empty] | 4 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 | HO6 |  |  | Rules-Automated Exceptions |  | Yes | 25090 | CA |  | HDES_Generic_US | Sprint 19 | QA Approved | 2016-08-24 03:40
586891 | Regression Analysis | DEMO-44290 | 178111 | Current RTC | JIRA Analyzed | C-DOC-AHRBXX-CA Generate AHRBXX Renewal Bill | added | 26486 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586891 | WI0162 CA HDES Conversion | gurpkaur | 2016-09-15 15:44 | sichavan | 7200 | Conversions |  |  | Generate Documents / Triggers | [5 empty] | 8 |  |  | Yes | Automation |  |  |  | N/A | DP3 | HO3 | HO4 | HO6 | PUP | Document Generation-Mandatory Forms |  | No | 26446 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete | 2016-08-26 07:59
586906 | Regression Analysis | DEMO-44289 | 178110 | Current RTC | JIRA Analyzed | H-CONV-SUP-CA: 26327 :Generate Renewal Reminder (Mortgagee) form 61 0071_RETIRED | added | 26328 | Closed | PAS10 | vekurapati | 2016-06-28 16:14 | 586906 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | cnigam | 3660 | Document Fulfillment |  |  | Generate Document | [5 empty] | 1 |  |  | Yes | RBT |  |  | WUNECA | N/A | DP3 | HO3 | HO4 | HO6 |  | Document Generation-Negative Approach Validation |  | May be | 26327 | CA |  |  | Sprint 19 | Test Execution Complete | 2016-08-01 04:07
587153 | Regression Analysis | DEMO-44288 | 178109 | Current RTC | JIRA Analyzed | H-UWA-ACSMGT-CL-26508-UW Rules Authority Level - New Business & Endorsements |  | 26516 | Non-CA | PAS10 | vekurapati | 2016-06-28 16:14 | 587153 | WI0162 CA HDES Conversion | sichavan | 2016-09-15 15:44 | vdixit | 4800 | Sales |  |  | Approval/Override | [5 empty] | 2 |  |  | No | None |  |  |  | Covered as a part of Other US | DP3 | HO3 | HO4 | HO6 |  | Rules-UW Rules |  | No | 26508 | CL |  |  | Sprint 19 | QA Approved | 2016-08-04 08:44
586844 | Regression Analysis | DEMO-44287 | 178108 | Current RTC | JIRA Analyzed | H-REN-AUTOINF-CA 25379:Apply Inflation Guard factors HO3 DP3 v2 | To be checked | 27278 | WI Analysis | PAS10 | vekurapati | 2016-06-28 16:14 | 586844 | WI0162 CA HDES Conversion | harsabhatia | 2016-09-15 15:44 | harsabhatia | [13 empty] | Yes | [5 empty] | DP3 | HO3 | [6 empty] | 25379 | CA |  | HDES_Generic_US | Sprint 19 | Test Execution Complete