## Sheet2
PAS2,3 | TC_34_Validate Endorse existing policy and validate MVLE Fee | AAAQA-20437 | I-F-A-VehicalUsage-NY-492 | done | DMV -Current Carrier Service should notify DMV - - Addition of replacement Vehicle as a normal addition in the policy. | done/ Integration
PAS2,3 | TC_36_Look Ups Interface General Tab | AAAQA-28124 |  | done
PAS2,3 | TC_39_Contents _ LOSS PAYABLE CLAUSE | AAAQA-27464 | F-A-New Business-VA-1572 | done
PAS2,3 | TC_42_Towing and Labor Coverage Document validation_Endorsement | AAAQA-27466 | F-A-Endorsement-VA-1553 | done
PAS2,3 | TC_43_Header_Trailer_Camper_Body Coverage Form | AAAQA-27467 | F-A-New Business-VA-1572 | done
PAS 4 | HO_18265_TC_01_Batch for split PPC value-Subscription indicator_T
PAS 4 | HO_18587_TC_01_Generate WUNECA 09 11Renewal_Reminder Notice-weekday |  |  | Fail | Issue#25- not yet resolved

## consolidated
12th Jan
PAS | Test Case Name | Tester Name | Date Of Execution | Status (Pass/Fail) | Defect Raised (Yes/No/NA) | Defect Id | Set | Comments
PAS 4 | HO_15275_TC_01_Generate Customer Declination_Letter | Anusha Konchada | 12th Jan,2015 | Failed | N/A | N/A | PAS 4 | Yet to raise a defect
PAS 4 | HO_14959_TC_01_Determine Inspection-Yes for Slope UW Question-New Business | Anusha Konchada | 12th Jan,2015 | Passed | N/A | N/A | PAS 4
PAS 4 | HO_17654_TC_01_Generate Forms for newly added endorsement -first time at amendment_before bind | Anusha Konchada | 12th Jan,2015 | Passed | N/A | N/A | PAS 4
PAS 4 | Validate whether the Premium is calculated correctly with HS 04 93 05 13 ACV Roof Endorsement under Endorsement Tab and when Agent clicks on the Calculate Premium button in the Premiums & Coverages page for a New Policy | Anusha Konchada | 12th Jan,2015 | Passed | N/A | N/A | PAS 4
PAS 4 | HO_17665_TC_04_ HS 03 12 05 13 Wind or Hail deductible percentage_New Policy-Midterm change | Anusha Konchada | 12th Jan,2015 | Passed | N/A | N/A | PAS 4
HO_15275_TC_01_Generate Customer Declination_Letter
HO_14959_TC_01_Determine Inspection-Yes for Slope UW Question-New Business
HO_17654_TC_01_Generate Forms for newly added endorsement -first time at amendment_before bind
Validate whether the Premium is calculated correctly with HS 04 93 05 13 ACV Roof Endorsement under Endorsement Tab and when Agent clicks on the Calculate Premium button in the Premiums & Coverages page for a New Policy
HO_17665_TC_04_ HS 03 12 05 13 Wind or Hail deductible percentage_New Policy-Midterm change
13th Jan
PAS | Test Case Name | Tester Name | Date Of Execution | Status (Pass/Fail) | Defect Raised (Yes/No/NA) | Defect Id | Set | Comments
PAS2,3 | HO_PTL_TC_251_Bind_Policy_ | Anusha Konchada | 13th Jan,2015 | Pass | N/A | N/A | PAS2,3 | NJ HO6 ; JIRA ID-31731
PAS2,3 | HO_PTL_TC_259_Decline_payment | Anusha Konchada | 13th Jan,2015 | Pass | N/A | N/A | PAS2,3 | JIRA ID- 31757
PAS 4 | HO_15013_TC_03_Determine Eligibility on Bind Policy-Year Built-less than 1900_midterm | Anusha Konchada | 13th Jan,2015 | Pass | N/A | N/A | PAS 4 | F-H-Endorsement-CA-939
PAS 4 | HO_17654_TC_01_Generate Forms for newly added endorsement -first time at amendment_before bind | Anusha Konchada | 13th Jan,2015 | Failed | N/A | N/A | PAS 4 | Issue#38 C-P-DocumentGeneration-CO-853
PAS 4 | HO_17791_TC_3_ DS 04 80_New Policy | Anusha Konchada | 13th Jan,2015 | Pass | N/A | N/A | PAS 4 | C-H-Endorsement-IN-965
PAS 4 | HO_17791_TC_6_ DS 04 80_MTC | Anusha Konchada | 13th Jan,2015 | Pass | N/A | N/A | PAS 4 | C-H-Endorsement-IN-965
PAS 4 | HO_17788_TC_02_Add DS 04 _endorsement at midterm | Anusha Konchada | 13th Jan,2015 | Pass | N/A | N/A | PAS 4 | C-H-Endorsement-IN-965
14th Jan
PAS | Test Case Name | Tester Name | Date Of Execution | Status (Pass/Fail) | Defect Raised (Yes/No/NA) | Defect Id | Set | Comments
PAS2,3 | HO_PTL_TC_251_Bind_Policy_ | Anusha Konchada | 14th Jan,2015 | Pass | N/A | N/A | PAS2,3 | JIRA ID- 31725
PAS2,3 | HO_PTL_TC_251_Bind_Policy_ | Anusha Konchada | 14th Jan,2015 | Pass | N/A | N/A | PAS2,3 | JIRA ID- 31728
PAS2,3 | HO_PTL_TC_251_Bind_Policy_ | Anusha Konchada | 14th Jan,2015 | Pass | N/A | N/A | PAS2,3 | JIRA ID- 31729
15th Jan
PAS | Test Case Name | Tester Name | Date Of Execution | Status (Pass/Fail) | Defect Raised (Yes/No/NA) | Defect Id | Set | Comments
PAS2,3 | TC_34_Validate Endorse existing policy and validate MVLE Fee | Anusha Konchada | 2015-01-15 | Pass | NA | NA | PAS2,3 | Couldn’t execute the last step in this test case as it involves Integration. Checked with Ankita Reshu and this test case was executed at her end and it passed.
PAS2,3 | TC_36_Look Ups Interface General Tab | Anusha Konchada | 2015-01-15 | Pass | NA | NA | PAS2,3
PAS2,3 | TC_39_Contents _ LOSS PAYABLE CLAUSE | Anusha Konchada | 2015-01-15 | Pass | NA | NA | PAS2,3
PAS2,3 | TC_42_Towing and Labor Coverage Document validation_Endorsement | Anusha Konchada | 2015-01-15 | Pass | NA | NA | PAS2,3
PAS2,3 | TC_43_Header_Trailer_Camper_Body Coverage Form | Anusha Konchada | 2015-01-15 | Pass | NA | NA | PAS2,3
PAS 4 | HO_18265_TC_01_Batch for split PPC value-Subscription indicator_T | Anusha Konchada | 2015-01-15 | In Progress |  |  | PAS 4
PAS 4 | HO_18587_TC_01_Generate WUNECA 09 11Renewal_Reminder Notice-weekday | Anusha Konchada | 2015-01-15 | Fail | No | NA | PAS 4 | Issue# 25: EFolder Structure unavailable at Renewal Timelines
16th Jan
PAS | Test Case Name | Tester Name | Date Of Execution | Status (Pass/Fail) | Defect Raised (Yes/No/NA) | Defect Id | Set | Comments
PAS2,3 | HO_GD_TS_TC_42_Revised Renewal_Declaration page-HO4 | Anusha Konchada | 16th Jan,2015 | Fail | No | N/A | PAS2,3 | Issue# 25 still exists- Folders not getting generated under eFolder/ Fastlane during Renewal timelines
PAS2,3 | HO_GD_TS_TC_43_Revised Renewal_Declaration page-HO6 | Anusha Konchada | 16th Jan,2015 | Fail | No | N/A | PAS2,3 | Issue# 25 still exists- Folders not getting generated under eFolder/ Fastlane during Renewal timelines
PAS2,3 | HO_GD_TS_TC_44_Revised Renewal_Declaration page-DP3 | Anusha Konchada | 16th Jan,2015 | Fail | No | N/A | PAS2,3 | Issue# 25 still exists- Folders not getting generated under eFolder/ Fastlane during Renewal timelines
PAS2,3 | HO_GD_TS_TC_45_Revised Renewal_Declaration page-PUP | Anusha Konchada | 16th Jan,2015 | Fail | No | N/A | PAS2,3 | Issue# 25 still exists- Folders not getting generated under eFolder/ Fastlane during Renewal timelines
PAS2,3 | HO_GD_TS_TC_46_Revised Renewal_Endorsements-HO3 | Anusha Konchada | 16th Jan,2015 | Fail | No | N/A | PAS2,3 | Issue# 25 still exists- Folders not getting generated under eFolder/ Fastlane during Renewal timelines
PAS2,3 | HO_PTL_TC_06_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 75000 and less than 150000 and FR Score is greater than equal to 2 and less than or equal to_716 | Anusha Konchada | 16th Jan,2015 | On Hold | N/A | N/A | PAS2,3 | Involves Backend Table validation
PAS2,3 | HO_PTL_TC_07_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 150000 and less than 265000 and FR Score is greater than equal to 2 and less than or equal to_716 | Anusha Konchada | 16th Jan,2015 | On Hold | N/A | N/A | PAS2,3 | Involves Backend Table validation
PAS2,3 | HO_PTL_TC_08_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 265000 and FR Score is greater than equal to 2 and less than or equal to_716 | Anusha Konchada | 16th Jan,2015 | On Hold | N/A | N/A | PAS2,3 | Involves Backend Table validation
PAS2,3 | TC_49_Validate content of Important Notice during New Business | Anusha Konchada | 16th Jan,2015 | Pass | N/A | N/A | PAS2,3 | PASS
PAS2,3 | TC_51_UM_UIM Motorist Coverage Selection document_Lower limit_Validation_New Quote | Anusha Konchada | 16th Jan,2015 | Pass | N/A | N/A | PAS2,3 | PASS
PAS2,3 | TC_52_Document _Non Owner Coverage Endorsement_Policy_NB_Endorsement. | Anusha Konchada | 16th Jan,2015 | Pass | N/A | N/A | PAS2,3 | PASS
19th
PAS | Test Case Name | Tester Name | Date Of Execution | Status (Pass/Fail) | Defect Raised (Yes/No/NA) | Defect Id | Set | Comments
PAS2,3 | HO_GD_TS_TC_78_Credit Card Expiration Date | Anusha Konchada | 19th Jan,2015 | Fail | No | N/A | PAS2,3 | Issue# 60
PAS2,3 | HO_GD_TS_TC_79_Unclaimed Search Letter | Anusha Konchada | 19th Jan,2015 | Fail | No | N/A | PAS2,3 | Issue# 60
PAS2,3 | HO_PTL_TC_06_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 75000 and less than 150000 and FR Score is greater than equal to 2 and less than or equal to_716 | Anusha Konchada | 19th Jan,2015 | On Hold | No | N/A | PAS2,3 | Involves Backend Table validation
PAS2,3 | HO_PTL_TC_07_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 150000 and less than 265000 and FR Score is greater than equal to 2 and less than or equal to_716 | Anusha Konchada | 19th Jan,2015 | On Hold | No | N/A | PAS2,3 | Involves Backend Table validation
PAS2,3 | HO_PTL_TC_08_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 265000 and FR Score is greater than equal to 2 and less than or equal to_716 | Anusha Konchada | 19th Jan,2015 | On Hold | No | N/A | PAS2,3 | Involves Backend Table validation
PAS2,3 | TC_45_Uninsured Motorist Property Damage Coverage Rejection form | Anusha Konchada | 19th Jan,2015 | Pass | N/A | N/A | PAS2,3
PAS2,3 | TC_47_Auto Insurance Quote Form_New Quote_data attributes | Anusha Konchada | 19th Jan,2015 | Pass | N/A | N/A | PAS2,3
PAS2,3 | TC_48_NB_Personal _Auto_Policy_Forms_Content | Anusha Konchada | 19th Jan,2015 | Pass | N/A | N/A | PAS2,3
PAS 4 | HO_15313_TC_02_Generate No Fee-No Restriction form_Manual | Anusha Konchada | 19th Jan,2015 | Pass | N/A | N/A | PAS 4
20th Jan
PAS | Test Case Name | Tester Name | Date Of Execution | Status (Pass/Fail) | Defect Raised (Yes/No/NA) | Defect Id | Set | Comments
PAS 4 | HO_18498_TC_05_Do not Re-rate at Midterm_HO3 | Anusha Konchada | 20th Jan,2015 | De-scoped | No | N/A | PAS 4 | Involves validation of rating algorithm
PAS 4 | HO_17116_TC_05_Subscription question_not answered | Anusha Konchada | 20th Jan,2015 | Pass | N/A | N/A | PAS 4
PAS 4 | HO_15591_TC_01_Additional Premium change –Processed on Mortgage_policy | Anusha Konchada | 20th Jan,2015 | Pass | N/A | N/A | PAS 4
PAS 4 | HO_15088_TC_04_Generate report when there is zip level match_Re-Order | Anusha Konchada | 20th Jan,2015 | Fail | N/A | N/A | PAS 4 | Defect :342596 still persists. Cannot test this until the test package gets updated as per comments in the defect. Defect raised by Ruchi Chaudhary.
21st Jan
Jira ID | Unique Test Cases | Interface Name | Tester Name | Date Of Execution | Status (Pass/Fail) | Defect Raised (Yes/No/NA) | Defect Id | Set | Comments
AAAQA-24129 | HO_E2E_TC_03_ Endorsement_HO3 | PAM and RBAC | Anusha Konchada | 21st Jan,2015 | cannot be executed | N/A | N/A | N/A | 1.Test case's pre-requiste involves configuration of Agent in PAM interface but there is no access to PAM UI. 2. Need query to run the RBAC SQL job to extract user information.
AAAQA-24130 | HO_E2E_TC_03_ Endorsement_HO3 | PAM and RBAC | Anusha Konchada | 21st Jan,2015 | cannot be executed | N/A | N/A | N/A | Duplicate of 24130
AAAQA-24134 | HO_E2E_TC_04_ PUP_Endorsement | PAM and RBAC | Anusha Konchada | 21st Jan,2015 | cannot be executed | N/A | N/A | N/A | 1.Test case's pre-requiste involves configuration of Agent in PAM interface but there is no access to PAM UI. 2. Need query to run the RBAC SQL job to extract user information.
AAAQA-24138 | HO_E2E_TC_05_HO4-HO6-DP3 _Endorsement | PAM and RBAC | Anusha Konchada | 21st Jan,2015 | cannot be executed | N/A | N/A | N/A | 1.Test case's pre-requiste involves configuration of Agent in PAM interface but there is no access to PAM UI. 2. Need query to run the RBAC SQL job to extract user information.
AAAQA-24148 | HO_E2E BP_TC_08_New business_Autopay | PAM and RBAC | Anusha Konchada | 21st Jan,2015 | cannot be executed | N/A | N/A | N/A | 1.Test case's pre-requiste involves configuration of Agent in PAM interface but there is no access to PAM UI. 2. Need query to run the RBAC SQL job to extract user information.
AAAQA-29918 | HO_E2E_TC_01_E2E Interface_IVANS New Business | IVANS | Anusha Konchada | 21st Jan,2015 | Pending | N/A | N/A | N/A | Created a policy- UTH3910019716 as per the steps. IVANS/ ETL job needs to be run-> Notified Vikram about this.

## Sheet5
PAS2,3 | HO_GD_TS_TC_42_Revised Renewal_Declaration page-HO4
PAS2,3 | HO_GD_TS_TC_43_Revised Renewal_Declaration page-HO6
PAS2,3 | HO_GD_TS_TC_44_Revised Renewal_Declaration page-DP3
PAS2,3 | HO_GD_TS_TC_45_Revised Renewal_Declaration page-PUP
PAS2,3 | HO_GD_TS_TC_46_Revised Renewal_Endorsements-HO3
PAS2,3 | HO_GD_TS_TC_78_Credit Card Expiration Date
PAS2,3 | HO_GD_TS_TC_79_Unclaimed Search Letter
PAS2,3 | HO_PTL_TC_06_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 75000 and less than 150000 and FR Score is greater than equal to 2 and less than or equal to_716 | Backend Table validation
PAS2,3 | HO_PTL_TC_07_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 150000 and less than 265000 and FR Score is greater than equal to 2 and less than or equal to_716 | Backend Table validation
PAS2,3 | HO_PTL_TC_08_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 265000 and FR Score is greater than equal to 2 and less than or equal to_716 | Backend Table validation
PAS2,3 | TC_49_Validate content of Important Notice during New Business | PASS | F-A-DocumentGeneration-VA-1024
PAS2,3 | TC_51_UM_UIM Motorist Coverage Selection document_Lower limit_Validation_New Quote | PASS | F-A-Coverage-IN-1502
PAS2,3 | TC_52_Document _Non Owner Coverage Endorsement_Policy_NB_Endorsement. | PASS | C-A-NANO-CO-1402
PAS2,3 | HO_GD_TS_TC_78_Credit Card Expiration Date | Fail | Issue# 60
PAS2,3 | HO_GD_TS_TC_79_Unclaimed Search Letter | Fail | Issue# 60
PAS2,3 | HO_PTL_TC_06_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 75000 and less than 150000 and FR Score is greater than equal to 2 and less than or equal to_716 |  | Backend Table validation
PAS2,3 | HO_PTL_TC_07_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 150000 and less than 265000 and FR Score is greater than equal to 2 and less than or equal to_716 |  | Backend Table validation
PAS2,3 | HO_PTL_TC_08_Determine-Bundle-Eligibility-Membership less than 10-Primary home-CovA greater than or equal to 265000 and FR Score is greater than equal to 2 and less than or equal to_716 |  | Backend Table validation
PAS2,3 | TC_45_Uninsured Motorist Property Damage Coverage Rejection form | PASS | AAAQA-27180
PAS2,3 | TC_47_Auto Insurance Quote Form_New Quote_data attributes | PASS | AAAQA-27182
PAS2,3 | TC_48_NB_Personal _Auto_Policy_Forms_Content | PASS | AAAQA-23267
PAS 4 | HO_15313_TC_02_Generate No Fee-No Restriction form_Manual
20th |  |  | server 107
PAS 4 | HO_18498_TC_05_Do not Re-rate at Midterm_HO3 | T-H-Endorsement-CA-916 | Fail | Policy#: | defect
PAS 4 | HO_17116_TC_05_Subscription question_not answered | F-H-Stove-CA-928 | Pass | QCAH6910019374
PAS 4 | HO_15591_TC_01_Additional Premium change –Processed on Mortgage_policy | C-H-Endorsement-CA-929 | Pass | CAH6910019373
PAS 4 | HO_15476_TC_18_invalid zip code_display error message. | F-P-NewBusiness-CA-933 | Amrit
PAS 4 | HO_18987_TC_2_Add new underlying HO policy_One primary HO and PUP exists | F-P-NewBusiness-CA-933 | Amrit
PAS 4 | HO_15088_TC_04_Generate report when there is zip level match_Re-Order | F-H-Premium-CA-942 |  | Defect :342596 still persists. Cannot test this until the test package gets updated as per comments in the defect