## 23-June
Discussion was held Design team perspective
Query | Response | For additional details
Scope
1. Assumption: There are no hybrid conversion requirements (Forms) for HDES policies. Please confirm. | There are some form related US under HDES Category. Tushar to share requirements pertaining to document content updates | To be routed to SMEs for futher inputs if required (Shankar Balasubramaniam and Paresh Lohia)
2. From the preconditions perspective to what extent the converted policies will be available to test the specific conversion related functionalities. (E.g. Do Not generate Renewal Reminder (Mortgagee) form 61 0071 for converted policies etc. In order to test this we will need a policy on mortgagee plan) | The conversion team is planning to share 5000 policies for functional testing. Based on what we scope for regression, we can share a list of pre-conditions for which we need policies from the legacy systems
Quotations which were not converted into policies in HDES will also be migrated to EIS PAS? (this is important to know to form a strategy on testing the eligibility, approval and task management related user stories mapped to HDES conversion work item) | Quotes will not be migrated from HDES to PAS. Renewal image bind will be behave as NB bind for converted policies and any functionality around NB/bind will need to be validated at the bind of renewal quote.
4. Assumption: All PAS functionalities are applicable to converted policies as they are to PAS originated policies. (unless delta is specifically called out in release scope) Please confirm. | Yes, once the renewal quote is bound, renewed policy will behave in same way as PAS originated policies. For the specific set of rules which trigger at NB but do not run at renewal (As covered in ‘Manual Changes to renewal image’ category in PAS9), Tushar to confirm behavior
5. Assumption: There are no capping related requirements in scope for the HDES converted policies | There could be capping requirement for HDES in PAS10 scope.
Approach
1. Assumption: All the sections of the converted policies will be present in the XML when they are loaded into PAS. (Unlike MAIG and Hybrid). Please confirm. | HDES and DPE (AS400) are fully automated i.e. there will be no data entry required after importing the policy in PAS. DP3 is a hybrid which requires manual data entry in PAS to propose the policy – similar to MAIG | DP3 data will be complete when migrated from HDES
2. Assumption: All XMLs are loaded correctly into PAS and are being validated by functional team. |  | Sample XML provided
3. What will be the status of the policy the import tool places in PAS from legacy system and at what timeline will it place in PAS | Only policies up for renewal in HDES will be migrated to PAS as renewal quote at timeline R-58 (Renewal rating) or after. | Need to confirm behaviour based on pilot performed by automation team
4. What extent of manual updates/additions would be required during testing phase | None, since HDES is fully automated conversion, all fields are expected to be prepopulated in PAS
Schedule
1. What are the completion dates for IT Team Review, Development and Functional testing | Present in attached excel (Not available work item wise)
2. What is the start date and end date of stabilization period for HDES conversion | Key Dates: o PAS 10 functional testing start date – 6/27 to 9/16 o Requirements Freeze Date – 8/12 o Draft converted XML availability – 09/19 o Final converted XML availability – 10/24 o PAS 10 Stabilization phase – 9/19 to 12/9
Other queries
1. IS HDES restricted to HO3, HO4 and HO6? Or does it include some DP3 policies also? | Yes, it contains a few DP3 policies as well
2. As per communication received ETL for HDES won’t be ready until late in the PAS 10 Stabilization Phase. Does the same apply to FoxPro ETL?[ | Yes. CSAA executives have agreed on 10/24 as the ETL completion date for all three legacy systems
3. Training on Property XML structure to the conversion automation team (good to have) | Would a sample XML help? Currently they do not have one from the actual ETL but mockups of the expected result – is that sufficient | Sample XML received

## 12-July
Discussion was held from Automation and XML availability perspective
# | Points Discussed | Decisions Made
1 | Availability of Draft and Final XML for the Conversion Work Item categories in PAS10 (CA HDES Conversion, WI0208 CA Prop Conversion SIS-DP3, Foxpro-PUP, WI0340 Enable Book roll in New Business and Capping): Schedule outline: a. PAS 10 functional testing start date – 6/27 to 9/16 (Sprint 19) b. Requirements Freeze Date – 8/12 c. Draft converted XML availability – 09/19 d. Final converted XML availability – 10/24 e. PAS 10 Stabilization phase – 9/19 to 12/9 Draft and final XMLs will not be available before specified dates and XML availability dates are the same for all 3 conversion categories of Sprint19. | > Due to unavailability of Draft and Final XMLs currently, it is proposed to use Sample XMLs to kick-start automation for Conversion scenarios
> Sample XMLs will be shared by Tushar which can be used to start automation
(Sample XMLs are NOT actual outputs of ETL but expected outputs. Actual XMLs may vary from these samples which might lead to a risk of rework for Automation)
> Tushar to provide Reference US to automation team for mapping of XMLs
> Availability of converted policies (XMLs) with required preconditions for Testing will be provided to Regression team on request
> Automation team proposed to perform a pilot to check the feasibility of using the sample XMLs for Automation of conversion items
> Automation team to proceed with the automation of conversion scenarios using Sample XMLs if pilot is successful
> Design team to check the feasibility of prioritizing Sprint 20 work item designs over the Conversions work items in case the Automation pilot using the sample XMLs is unsuccessful
2 | Use of existing MAIG XMLs for ‘WI0340 Enable Book roll in New Business and Capping’ testing | Current MAIG XMLs cannot be used for ‘WI0340 Enable Book roll in New Business and Capping US’ of Sprint19, since they create renewal quote, and whereas book-roll testing requires creation of NB quote
3 | Impact on overall schedule | > Automation schedule of Conversions work items will depend on the success of the Automation pilot using sample XMLs
> Actual testing of conversion can happen only after Final Converted XML availability (10/24) which falls in Milestone2
> Test Plan to capture these details

## 21-July
Sr No | Query related to | Query | Response | Additional comments
1 | Generic functionality | 1. Does it mean for generic user stories the functionality needs to be tested on both PAS originated as well as on converted policies? Do we need to create one scenario for converted policy and create/modify another scenario for PAS originated policy? | Applies to both organic and converted policy PAS10: test for converted policy Organic suite: modified | If yes, it will significantly increase our regression testing efforts. e.g. Attached US# 25418 (Child RRC# 25524), mentions WU67CA is getting retired and replaced with ‘AH67XX 03 16’.
2 | Delta state other than CA and CCL | For US with delta state as CL/UT, functionality can only be tested on PAS originated policies. Considering HDES is limited to CA policies, our assumption is there won’t be any CL/UT policies converted from HDES to test such cases. Please confirm. e.g. The delta mentioned in US # 26010 (Child RRC# 26011), Bind PUP policy without membership, can only be validated on PAS originated UT policy. | Converted policies need not be validated. Since UT CA tested conversion non-CA to be tested on organic
3 | Applicable products contains PUP or is limited only to PUP | When US tagged under HDES specifically mentions behaviour of PUP policy, are they referring PUP policy converted from HDES or Foxpro. (If reference is Foxpro, need to confirm whether it needs to be covered separately for PUP) (e.g. 26408) Similarly HDES US which is applicable to PUP only, does it refer to Converted HDES policy from HDES or Foxpro (e.g. 26028) | User stories: HDES: CA HO3,HO4,HO6 SIS: DP3 Foxpro: CA PUP
4 | Applicable products contain DP3 | When US tagged under HDES specifically mentions behaviour of DP3 policy, are they referring DP3 policy converted from HDES or SIS (If reference is SIS, need to confirm whether it needs to be covered separately for DP3) (e.g. 26408)

## 21-July MOM
Sr No | Query related to | Query | Response | Additional comments
1 | Generic functionality | Generic US which do not specifcally call out the behaviour for converted policies, do they apply to both organic and converted policies in same way? | Generic US apply to both organic and converted policies in same way. These are tagged under HDES category, since the delta is initiated by conversion team | If yes, it will significantly increase our regression testing efforts. e.g. Attached US# 25418 (Child RRC# 25524), mentions WU67CA is getting retired and replaced with ‘AH67XX 03 16’.
2 | Delta state other than CA and CCL | For US with delta state as CL/UT, functionality can only be tested on PAS originated policies. Considering HDES is limited to CA policies, our assumption is there won’t be any CL/UT policies converted from HDES to test such cases. Please confirm. e.g. The delta mentioned in US # 26010 (Child RRC# 26011), Bind PUP policy without membership, can only be validated on PAS originated UT policy. | HDES contains only CA policies. Functionality covered in non-CA/ non-CCL User stories under HDES WI needs to be validated only on organic policies. |  | Converted policies need not be validated. Since UT CA tested conversion non-CA to be tested on organic
3 | Applicable products contain PUP and DP3 | When US tagged under HDES specifies the behaviour of DP3 policy as separate AC, is it referring DP3 policy converted from HDES or SIS? (e.g. Parent RRC# 26407 -> Child RRC# 26408) Similarly, When US tagged under HDES specifies the behaviour of PUP policy as separate AC, is it referring PUP policy converted from HDES or Foxpro. (e.g. Parent RRC# 26407 -> Child RRC# 26408) | There are no DP3 and PUP policies in HDES. All DP3 policies will be converted from SIS All PUP policies wiill be converted from Foxpro Srividya to check the reason for including DP3 and PUP policies under HDES WI, and provide inputs
4 | Applicable product is PUP only | Why are some userstories which are applicable only to PUP, are tagged under HDES WI (e.g. 26028) | Srividya to check the reason for including PUP specific US under HDES WI, and provide inputs
User stories: HDES: CA HO3,HO4,HO6 SIS: DP3 Foxpro: CA PUP

## CP Optimization
Sr No | Description | Points discussed | Decision | Team Responsible
1 | Approach finalization: optimized CPs vs reusing old CP's | Benefits over optimizing over Reusing 1. RCA maintanace is lower 2. Optimized code can be rused for Converted as well as organic both 3. Data issues will be resolved from RCA prospective | Approach 1 - Optimized CP should be used. | Automation/Design
2 | Shuffling of the validations | 1. Resuffle and move the AC's across all CP's in order to make sure all the CP's have on an average 12 AC's and Max 15 AC's 2. Sequence of the validations changed requires an extra effort apart from estimates given | Automation team to check for extra effort in that case | Automation
3 | Modular Designs | 1. Use state table and use a Data driven approach for Automation coding 2. CP's will generic precondition, no specific preconditions will come in CP's(exception being: payplan etc) 3. Avoid things at Quote which are not generic (Design team to take care on that) 4. Create Few common function which will create basic vanilla policy with payplan | Automation team to work on the effort of creating and resuing the common functions | Automation/Design
4 | Suggested product and payplan | CP's will be specific to suggested product and suggested payplan In case functionality has variations based on products these will be covered in separate CP's Eg : Inflation guard validation unique AC combinations to be covered in multiple CPs | Suggested payplan and suggested products to be fixed and used across all CP's evenly | Design
5 | Non Standard Timepoints | Rewrite : 1.DO it on 2nd Renewal term only and that would be last validation in a CP. | 1. No recomputation of timepoints due to rewrite moved to 2nd renewals terms 2. Validations on rewritten policy to be created as calender scenarios | Design
6 | Clubbing calender scenarios with similar timepoints (RCA) | Club Calender scenarios with same no of timepoints based on batch jobs | Automation team to identify those scensrios and club them for execution | Automation
7 | Calender feasibility for Conversions | Converted policies will have Effective date as R-58 which cannot be run in calender fashion | Automation team to find a workaround on this and if it does not work it will work as timepoints | Automation
8 | FoxPro and SIS appraoch | Append and Run 1-2 CP's for Foxpro/SIS scenarios | FoxPro and SIS will not have extensive coverage in terms generic functionality Only 1-2 scenarios will be appended with CP's to cover generic functionality Design team to inform and conclude with Jerry on this. | Design
9 | ProRated Functionality | Prorata premiums to be calculated and coding by Automation | Automation team to get a clarification and understanding with SME on rounding logic | Automation
10 | Preconditions specific XML's | XML's coming for converted policies should have scenario specific preconditions or it has to be changed in PAS | Automation team to check with jerry if preconditions specific XML's will be provided for execution | Automation
11 | Documents List | Generate CL related documents list | Design team to provide CL and CA related documents list for coverage in CL-CP's and CA-CP's | Design

## 29-Aug
Sr No | Points discussed | Team Responsible
1 | Design team to Convert D-T scenarios to calendar(Conversion specific) and AC’s in these scenarios to be content validated by ADT team | Design
2 | Deliver CP's as is with all forms (Among all forms ADT to validate only specific forms covering important transactions for conversions) – Design team to convey this information to ADT team separately | Design
Internal Discussion with Automation team