## Sheet1
# | Points Discussed | Decisions Made
1 | PAS 9 Update | > Mostly 7 new states being rolled out > Manual Changes to Renewal Image > PAS Property UI changes, enhancements > Design team would require more detailed understanding of the UI changes before the PAS9 designs are initiated

## 14th March
# | Points Discussed | Decisions Made
1 | Target for User Story Analysis | > 5.8 ~ 6 User Stories to be analysed by individual design author. > Approximately 22 minutes per AC is the estimated time including review.
2 | Target for User Story Review | > 11.2 User Stories to be reviewed by individual reviewer
3 | JIRA Field Clean-Up | > Separate Sheet will be shared with agreed upon changes.
4 | Design Counter Dashboard | > Need to update 'PayPlan 1R' for Scenario Tasks in JIRA that do not have this field populated.
5 | Pattern Reusability | > Pattern can be reused only if all the AC's in the design are reusable or have a matching delta. > If the Pattern is partially reusable only, then we need to create a new pattern for the delta state.
6 | User Story Dump | > If a design author is downloading the User Story and Supporting artifacts, upload them on SVN as well for ease of reference.
7 | PAS9 Design Counter | > PAS9 design counter starts from 650.

## 15th March
# | Points Discussed | Decisions Made
1 | JIRA Updates | > Additional fields as discussed were created. > Certain fields were removed and made non-mandatory.
2 | AC Count for User Story | > In case reference to multiple versions are give under one Parent RRC, first check the 'Implemented by RTC #' section and validate the release. > If there are 2 versions of the same release, then the total AC count of both the user stories need to be considered. > Even the greyed out portion should be considered as that is part of PAS9 too, it has been greyed out only because a new version is created in the same release. > Validate both the versions and mark the total AC count [Excluding the Common AC's]
3 | Payment Plans | > Need to start using payment plans that are not much tested, Ex: Monthly Low Down Monthly Zero Down Eleven Pay Low Down Eleven Pay Zero Down
4

## 16th March
# | Points Discussed | Decisions Made
1 | User Stories for Different Thread | > User Stories falling under difference thread such as 'CFT' need to be assigned to the respective team member from the thread. > Need to provide the necessary KT on JIRA process if required.
2

## 17th March
# | Points Discussed | Decisions Made
1 | Voice Bind Script Validation | > Currently marked as UI validation since voice bind is not part of the PAS implementation. > In the UI only the Text Script can be checked.
2 | Search Functionality | > Need to discuss specific User Story and check if it needs to be convered as part of Regression.
3 | DB Related Validation | > Past example such as DOI and UW Code check, these specific validations were included in regression. > Database validations are subjective and will be dealt with in case to case basis.

## 18th March
# | Points Discussed | Decisions Made
1 | Validate State Tax field in display premium section | > Cross check if the Calculate premium with state tax US is also in scope for PAS09. > Do not cover the validate state tax fields US if calculate premium US is covered > Check with Rohan and Integration if Values in state tax field should be covered in Integration as the values of state tax is being fetched from Tritech integration system
2 | Retrospective Meeting | > Need to schedule another retrospective meeting to discuss more areas like Reusability - is the current process working, Aspects related to changes to designs,patterns etc
3 | Reusability of Scenarios across release | > For the scenarios that can be fully reusable between releases, if only few AC's have a Delta use rest of the AC's as is if they are CL applicable. > Discussion related to reporting of CL AC's that are extra and not part of the release scope is pending with Bhushan and Sachin.
4 | Manual changes to renewal image | >This is as per the mail sent by anugya with updated combination and how much coverage to be provided by every team.

## 21st March
# | Points Discussed | Decisions Made
1 | Targets | > 6.5 User Stories to be analyzed per person per day. > 11 User Stories to be reviewed per person per day. > Planned analysis targets should be completed by Thursday EOD (Wednesday EOD for this Week) and not beyond.
2 | Cross Team Learning | > During AHM (VC) we have a cross team learning session. > Expectation: How various teams can work with each other efficiently. > SLA to be defined for Design Tickets. > Request Development team to also look at User Stories mapped to the designs, some folks do it already and that helps in resolving any query at the earliest. > PAS8 Release Scope Summary to be one of the Key learning. Will be shared across teams.
3 | Rules related to Manual Changes in Renewal Image | > Rules can be clubbed as long as there is no conflict.
4 | CP Related AC's | > Till the CL CP's are not finalized based on PAS9 changes, do not analyze the CP related functionalities in Delta State.
Cross Team Learning Evening Call
1 | Cross Team Learning | > Request Development team to also look at User Stories mapped to the designs, some folks do it already and that helps in resolving any query at the earliest. > PAS8 Release Scope Summary to be one of the Key learning. Will be shared across teams. > Regular feedback discussion with Automation team to understand their constraints with respect to existing designs, helped in further enhancing design quality and readability. > Sharing RCA impact of User Stories helps tracing any existing requirement > Separating the Document Generation validations from generic validations. Document Generation validation are now part of separate scenarios which makes it easier for tracking. > Optimization of Regression Scoping guideline has helped every team. > PAS Core team had incorporated the new design process which helped in maintaining consistency in the format. > SLA to be defined for Design Tickets and Defect Review.

## 22nd March
# | Points Discussed | Decisions Made
1 | PAS 6.1 Scenario Traceability | > PAS 6.1 scenarios are to be created in JIRA. > PAS Core team to provide the scenarios in the required Jira Upload Format. > JIRA upload format to be shared with PAS Core team > L1 L2 mapping for the scenarios have been done. > Going forward the format for patterns and designs for Core & Factory to be in Sync.
2

## 23rd March
# | Points Discussed | Decisions Made
1 | JIRA Flow Update | > JIRA flow update has been updated, fields that were not required have been removed from the screens as discussed. > Analysis workflow has fewer fields than earlier. > Need to see if the 'Scenario Task' workflow can be made more effective. > JIRA POC has been completed based on the changes discussed. [Mail Attached for Reference]
Retrospective Call
# | Points Discussed | Decisions Made
1 | Consolidated Pattern Sheet | > Consolidated Pattern Sheet to be maintained only to track newly created scenario and the counters. > Any analysis being done (AC's to put in patters) needs to be done in the State Wise Sheet > Finish analysis in the State Wise Sheet and just copy over the counter in the Consolidated Pattern once analysis is complete. > Ensure the counters are allotted before US analysis.
2 | Fields in Pattern Sheet | Fields to be Removed: Column Level Date Pre-Condition Work Item Category Fields to be Removed : Info Type Reusability Not Applicable Product Not Applicable Product Fields to be Added: Column Level Delta AC Count Total AC Count (AC Count field to be Renamed) Scenario Type Thread Fields to be Added : Info Type Source Release Modified Release
3 | Key Notes | > Suggested Payment Plan at Renewal to be Given only when the policy is being renewed. > Do Not Leave any field 'Blank'. Mark 'NA' for the fields that are not applicable. > Any Time Point/Scenario Step heading not applicable for a particular state, that needs to be removed. > Document Generation Patterns - In PAS9 irrespective of whether the document generation has Content Validation or not. Separate Time Point scenarios have to be created for document validations. > Continue to used SVN. Google Sheets will not be used for Pattern Creation. > Need to maintain the recommendations from the Automation Team and have a session on the same. > Design Review Checklist to be implemented.

## 25th March
# | Points Discussed | Decisions Made
1 | Daily status | > Team to work on Document Generations designs to create Buffer > Work on Design tickets
2 | PAS8 scope summary preparation | > Team to prepare for formal presentation with accurate time required for presenting each slide

## 28th March
# | Points Discussed | Decisions Made
1 | Weekly Target | > 29 US to be analyzed for Analysis per design author. > 55 US to be reviewed by the reviewers.
2 | Release Scope Summary | > Need to create the Release Scope Summary for Work Item Wise for Analysis done so far. (Including this week's) > Share the Release Scope Summary draft with Anugya by Friday EOD.
3 | Pattern Creation & Format | > Current consolidated pattern sheet will be modified as per the new format discussed during the 'Retrospective Call'. > All PAS9 patterns need to have the same format. For patterns from previous release the format is to be updated only if the pattern is undergoing a change in PAS9. > Once the Pattern Format is finalized and updated in Consolidated Pattern Sheet, the patterns need to be moved in the State Wise Suite and not the Consolidated Pattern Sheet.

## 29th March
# | Points Discussed | Decisions Made
1 | Burndown for Week Ending 1st April | > As of now the current burden will remain as is. > In case Shireesh and Gurpreet are unavailable, Anugya/Siddhi to pitch in reviews. > Anugya to check with Shireesh/Gurpreet on review status and availability.
2 | Design Update for Scenarios of Previous Release | > Depending on the changes required a design ticket is to be raised. Ex: If the changes are related to Time Lines and other major step updates. >Changes to be made in the Design Suite corresponding to latest release (PAS8)

## 30th March
# | Points Discussed | Decisions Made
1 | Review Status | > Check for the Status Update of Reviews. > Check if it is on track to be completed by Saturday, else move to Plan B (Anugya/Siddhi to pitch in for Reviews)
2 | PAS Core | > Shweta - Target 10 WI Remaining 3 WI > Purva - Target 10 WI Remaining 1 WI > On Track for Friday

## 31st March
# | Points Discussed | Decisions Made
1 | PAS Core | Revised Burndown 15 Analysis 5 Designs & 15 Reviews per team member: Shweta - Analysis - 3 remaining Design - 5 remaining Review - 15 remaining Purva - Analysis - 5 remaining Design - 5 remaining Review - 15 remaining
2 | PAS Factory | > Review status received, on track to meet the internal target burndown.

## 1st April
# | Points Discussed | Decisions Made
1 | PAS Core | > Shweta - Analysis 0 Remaining - Design 5 Remaining - Reviews 10 Remaining > Purva - Analysis 0 Remaining - Design 5 Remaining - Reviews 10 Remaining On track to meet the targets by EOD
2

## 4th April
# | Points Discussed | Decisions Made
1 | Incomplete Patterns | > Work on the Incomplete Patterns as per the list shared by Shireesh. > Move them to Ready for Design/Ready for Review as applicable.
Query Addressal Schedule Proposal - MOM
1 | New Model for Query Addressal | > To avoid any impact on individual design team members deliverables, a new model for Query Addressable is proposed. > Each design Team Member is allotted certain slots during the day of 1.5h each during which they will address the queries. > Incase the query is functionally critical and the respective design team member is unable to address the query, in such case design team to internally discuss the same and then provide the solution. Member raising the query need not explain the query to multiple person from design team. > On an average 3-4 queries are received per day by a design author. > Currently the Query goes to the respective Design Author.
2 | Type of Queries | > Query related to Design Template Update. > Steps in design and application behavior. > Queries regarding Error Messages/Data Fields. > Categorize the kind of queries and check for any common types of queries across release and take a one time session with possible solutions. (It may help in reducing common queries across release)
3
4

## 5th April
# | Points Discussed | Decisions Made
1 | Scenario Design | > Patterns ready for design to be uploaded in JIRA, design to be initiated once allocation is done.
2 | Analysis Scope | > Continue with the current scope, any changes would be communicated as and when finalized.
3 | Documents to be shared along with Design Delivery | > Checklist of key documents to be shared with extended team along with the Design Documents. > As discussed, documents such as MML/DD's will not be uploaded in Confluence by Design Team, latest files to be retrieved from RTC.
4 | Endorsement View on UI | > Example : If a requirement says XYZ endorsement should not be displayed on the UI for a Delta state. > This is not a negative validation, endorsements may have premium impact. Such validation can be covered for few states. > Regression Thread for such validations can be internally discussed.
5 | Manual Changes to Renewal Image | > Need to check whether or not Category 4 should be covered in Regression. Some will be part of Regression and some RBT. > If Regression Yes, check which thread needs to cover it. > Need to discuss some examples with Automation Team and check the automation feasibility.

## 6th April
# | Points Discussed | Decisions Made
1 | Scenario Workflow Updated | > Purpose of having a new workflow is to have traceability for Automation, Manual & RCA. > If any field is not updated correctly notify Shireesh, do not manually edit any information. > Mark the design as Design Complete and log time accordingly.
2 | Defect Reviews | > Any defect that comes for Review needs to be reviewed within 1 hr and sent back with appropriate comments. > If more information is required send the same response immediately. > Mark Gurpreet & Shireesh in all defect related E-Mails.
3 | Pattern Information Missing | > For some patterns 'Comments' row was not created. In some 'Comments' row was empty. > Scenario Task Type - Spelling mistakes and other inconsistencies observed. > Going forward when creating a New Pattern if there are multiple products and states. Mark them as comma separated but do not leave and space between them. Ex: HO3,HO4,HO6,DP3 - Correct HO3, HO4, HO6, DP3 - Incorrect > Payment Plan Inconsistency - Ex:- Mortgagee/Mortgagee-Plan , consistency needs to be followed

## 11th April
# | Points Discussed | Decisions Made
1 | PAS Factory | > Continue with scenario designs till further intimation on User Story Analysis.

## 12th April
# | Points Discussed | Decisions Made
1 | PAS Factory | > New User Stories for Sprint 18 have been uploaded in JIRA. >Teal to continue to work on scenario design for this week as planned > Newly added US will be picked up next week for analysis and some team members would continue scenario design.
2 | PAS Core | > Members of PAS Core team will be involved in Test Execution and will not be doing any analysis,design and reviews for today. > Burndown to be adjusted because of the unplanned test execution

## 19th April
# | Points Discussed | Decisions Made
1 | Design Allocation | > Pick up the 23 Open Designs under Anugya's name and reallocate within (Siddhi,Harsh & Varun) based on the target AC count.
2 | PAS 9 CP Designs | > Based on the PAS9 state roll out, Delta's for the CL CP's have been indentified. > Around 75 CP's have been identified for design changes. > As per Automation team out of 75 CP's only 22 can be automated. > Of the 75 CP's which 22 need to be designed is yet to be decided. > PAS9 CP design is currently on Hold. > Remaining User Story analysis to be picked up post NB designs.
3 | CL-CP Design Update | > CL-CP's are being modfied based on the design tickets. > When starting PAS9 designs, ensure the latest version of the design is picked up from PAS8 Suite.

## 20th April
# | Points Discussed | Decisions Made
1 | Additional Analysis[PAS Factory] | > Team members were held up with many queries on PAS8 designs/deltas, Defect Reviews and other analysis. > As a result of other analysis the internal planned burndown might be slightly off-track.
2 | PAS Core Burndown Week Ending 22nd April | > PASCore design practitioner's will be supporting Manual execution > They will be also involved in the analysis/designing of additional 7.2 scope WI's, which have been provided by Kartik > Additional scope items have been added are to be discussed with Shree/Sachin post which the burndown would be updated and shared for current week.

## 25th April
# | Points Discussed | Decisions Made
1 | CP Design | > Siddhi and Varun to work on CP designs that are to be delivered to the Automation Team.
2 | Changes to CP Design based on Design Ticket | > Communication will be sent out to Automation team that any changes to the base CL-CP's will reflect in the PAS9 Suite only.
3 | Demarcation in CP's | Following are the types of categories which define the CP changes: > CD - Code Change, any pattern marked as CD > TCD - Time line changes and code changes > TD - Change in step sequence due to time line changes > TC - Just a time line change, steps can be as it is moved to the new time points. > Refer to the sheet created by Anugya for more details.
4 | PAS Core Updates (7.2) | > 48 Defect Analysis complete. > Defect Design to be initiated.

## 26th April
# | Points Discussed | Decisions Made
1 | PAS Core | > Design for additional 47 defects has been started. Weekly Target is to cover 16 WI's in design > PAS 8.1 Analysis started

## 28th April
# | Points Discussed | Decisions Made
1 | CP Design | > Need to design Must Have CPs > Do not initiate design for 'Good to Have' CPs till we get a confirmation from Automation team.
2 | Defect Workflow Walk Through | > Scheduled for next week.
3 | PASCore Updates | > Design for all 19 defects that were in scope from the 47 additional defects has ben completed.

## 4th May
# | Points Discussed | Decisions Made
1 | Manual Changes to Renewal Images | > Certain validations are independent of manual changes to renewal image. > Need to decide an approach on a workaround so that the remaining validations can be checked, following options discussed: i. By commenting only the manual changes to renewal part. [Need to check feasibility, removal/commenting out of a piece of code should not impact remaining validations] ii. Find out from manual team on the bandwidth, to check if the remaining validations can be checked manually. iii. A quick check can be done on the failed scenarios to see what workaround can be used and its possible impact on remaining scenario.
2 | PAS Core Requirements | > Functionality enhancements coming as part of PAS 8.1/8.2 that impact the CP's/NBP's needs to be in sync with Factory Designs. > This needs to be discussed with extended team including Automation (Bhushan) to decide on an approach on design and code updates (If Any)

## 9th May
# | Points Discussed | Decisions Made
1 | PAS8 Additional Scope | > Anugya & Varun to work on PAS8 additional scope (22 US)
2 | PAS9 | > Siddhi & Harsh to work on PAS9 pending items and Design Tickets > Patterns in the Consolidated Pattern Sheet need to be copied over to state specific sheet and ensure that the unique format is followed across. [Entire design team to work on this from tomorrow] > Once the Pending PAS9 items are closed, team to focus on RBT executions.
3 | Additional Activities | > Team to take up KT from Anugya on the different kind of Additional Activities that we perform during a release.
4 | PAS9 High Level Scope Summary | > Need to present the Final version of PAS9 High Level Scope Summary.
5 | PAS Core Design Updates | > How to update PAS Factory designs based on the changes coming as part of PAS Core requirements. > If PAS Core US are impacting the PAS Factory designs. Ex:- PAS 9 designs have been completed. If there are any changes to an existing design based on PAS 8.1 US, then PAS8 design needs to be copied over to PAS8.1 and changes should be made. Once the PAS8.1 automation is complete the and the changes are finalized, then the changes need to be copied over to PAS9 design. > PAS Core design team should update the PAS Factory team in case any of the PAS Factory designs are updated due to PAS Core requirements. > For newly added AC's the PAS Core team should design new scenarios instead of updating existing Factory Scenarios. > Although Philip's model is RSG No, the new condition has to be included for states for which Philip's model has not been covered yet, as an exception.

## 10th May
# | Points Discussed | Decisions Made
1 | Complexity of Scenarios (PAS9) | > Need to give the complexity (Simple,Medium & Complex) for the existing PAS9 scenarios. > Process needs to be setup with Automation team to give a one to one (Design Author to Script Author) walkthrough for 'Complex' scenarios whenever required.

## 18th May
# | Points Discussed | Decisions Made
1 | Session on various functional areas | > Design team to initiate KT sessions on various functionalities/areas such as Billing/Automated Exception etc. > Design team to come up with a list of functionalities to cover > Design team to reach out to Automation/Manual team for their inputs > Connect with Shree for his inputs on these sessions.
Functional Review of Defects - Points to take care of
# | Points Discussed | Decisions Made
1 | Defects logged in Golden Build | > For defects being logged in Golden Builds, extra information is required such as - Status in previous milestones? - Is this defect introduced newly? Etc. > Do not approve any defect before we have all the required information
2 | Milestone | > During Milestone 1 & Milestone 2 idealy all the new defects should be caught > Milestone 3 should focus on regression test for defects logged in Milestone 1 & Milestone 2 and other leakages brought in due to changes. > If a defect is observed in Milestone 3 & 4 which could have been observed in Milestone 1 or 2 then there is a gap in testing.
3 | Timepoints in Scenarios | > Perception that in a timepoint scenario we jump from 1 timepoint to next timepoint bypassing the fillers, is incorrect. > Always follow the business flow, i.e. run all the billing filler/renewal fillers with correct batch jobs when executing or replicating a defect.
4 | Steps & Screens | > Every screen should be preceded by the appropriate step performed to reach the respective screen
5
6

## 19th May
# | Points Discussed | Decisions Made
1 | Server Availability | > Need to check for server availability with Chittranjan
2 | Timepoint Clashes in Scenarios | > For any timepoint clashes identified, first check with automation team if they can handle the clash using if statement or some other logic. > If the framework can not handle the clash, then move the steps to an alternate feasible timepoint. Ex: In NY the clash is between DD9(R-90) and R-R1(R-88), in this case move the steps that are present at DD9 to DD9-20 or alternate timepoint. > Check which team needs lesser time to come up with a fix. Most likely design team can do the changes quicker, design team to take ownership to identify such cases and reolve the same proactively.
3

## 23rd May
# | Points Discussed | Decisions Made
1 | PAS9 Pending Items | Integration items are still in 'Open'. Need to check for the status before sending out WSR. Release Champion to follow up on the same.
Check the items that are marked in Regression Scope 'Yes'. Ensure that the design is present for all the AC's that are marked in scope. There have been cases where AC's/US are marked in Regression Scope but there is no design associated with them, as they may have been descoped later but JIRA was not updated.
High level analysis of US in Regression Scope 'No'. Check for US that are marked in Regression Scope Yes, check that at least 1 AC is in scope for regression.
High Level Scope Summary completion.
For all the scenarios that are getting updated in a release a new regression sceanrio task needs to be created and a label needs to be added to the old Regression Scenario task to make it obsolete. Ex: NBP210 is created in PAS8. In PAS9 NBP210 is updated [AC added Modified] Then in PAS9 new Regression Scenario Task fro NBP210 is created and a label is added to existing PAS8 Regression Scenario for NBP210 to mark it as obselete.
7 AC's related to Document Generation are part of Priority Group 2 CP's. Need to check with Automation Team if those CP's can be added to Automation Scope or separate timepoint scenarios need to be created for these 7 AC's
Query on Comp Rater related US is yet to be resolved, once the response is received need to take the necessary action needs to be taken.
Regression Traceability Task Creation for PAS9 Scenarios in JIRA
2 | Tasks performed Every Release | Comparative analysis for Estimated AC count for each thread vs Actual AC counts and variance.
> Release Scope - Sprint 18 scope is baseline for PAS9 scope. Need to check for any additional items that are added against the baseline. Scope needs to be checked twice a week. > Once scope is baselined, any additional items that come in scope needs to be informed to the leadership.
> Checks to be performed at the end of every release, ensure all the items are in ideal state [Closed/Completed] > There should not be any items in open/edit/pending status > Check for items tagged to different threads and follow up with the respective team to know the status or to inform them what needs to be done.
Reporting: WSR and Special Project Report format shared with the team and KT provided on the same

## 24th May
# | Points Discussed | Decisions Made
1 | PAS9 Pending Items | Work on CP optimization to revise the count of 'Must Have' CP's delivered to automation
Work on High Level Scope Summary Deck and send it for review
Re-analysis of User Stories marked in Regression Scope 'No' to check for any discrepancy and leak in coverages.
Follow up on items that are in pending query, Comp Rater related US is resolved, action to be taken on pending items

## 14th June
# | Points Discussed | Decisions Made | Ownership
1 | User Groups in CPs | Work on changes to CP's shared by Madhuri [Priority] | Siddhi
| User Groups in CPs | Need to update this in Base CP's as well, work on list shared by Madhuri on priority. [Check CA CP's as well] Note: To be picked up based on design team bandwidth | TBD
2 | E34 & L41 Access to renewal image | This needs to updated across designs. In designs (At R-R1) wherever we have mentioned that check renewal has initiated successfully, we need to mention the specific privilege as only E34/L41 can view the renewal image at R-R1. [Early Policy Renewal Inquiry is the privilege] Note: To be picked up when team has bandwidth
3 | Updated to Cancellation beyond NB discovery timeline for MD scenarios. | > Need to do further research on the same | Varun
4 | Functional testing pilot | > Need to start functional pilot today > Analysis to be done on Excel for now, JIRA tracking would be done later. > Need to do both Functional/Regression analysis Ex: If we have 5 AC's talking about 5 products [1 AC will be Regression/Functional, rest 4 would be functional] Start Date: 6/14 End date: 6/24 | Varun/ Harsh
5 | Scenarios that are moving from Automation to Manual Thread | > Design team need to create the respective regression scenario in JIRA and communicate the same to Manual Team by mail. | Design Team
6 | Prorated premium formula | > As per communication from Shree, awaiting updates from Automation team on exact framework constaints | TBD
7 | Updates to the High level scope summary deck | > Common functionality slide can be updated to mention the significance. > WSR Slide to be updated. > Include details for Water Back Up CR | Harsh/Gurpreet
8 | Retrospection call | TBD | Design Team
9 | Weekend logic for a policy across multiple transactions [Cancellation/Bill etc.] | > Need to create a consolidated list [Auto/Property] time points along with weekend logic. Note: To be picked up when team has bandwidth

## 26th May
# | Points Discussed | Decisions Made
1 | User Privilege - CA Access Issue | To be put on hold till further communication from Jerry/Jishnu.
2 | User Privilege - Mentioned in Designs | As per discussion with Shree, communication to be sent out to automation. Automation team to continue with previous role until another role is specified. [Instead of using L41, except for Batch Job runs.]
3 | Generic (if any) validations | On-Going to be dealt in case to case basis. Design changes to be made wherever applicable and design team to avoid such cases in future designs.
4 | CPs with content validation | > For specific cases where the validation can only be done on the document generated, then such validations have to be removed from CP's and a separate scenario should be created for it depending on the validation. Ex: Checking amount due on Renewal Reminder Notice, this needs to be done by manual team > However, check with document automation team if the above case can be handled at their end.
5 | Complex functionalities walkthrough | Scheduled one session on AE - Harsh to schedule it for Monday
6 | Changes to renewal image | Automation - No action
7 | Changes to AC count after delivery | Design team to respond - Harsh
8 | Combining stub related scenarios | Not feasible as per initial discussion - To be communicated to Automation team with the identified constraints
9 | Document Generation validations in CPs. | Automation to provide more input
10 | Ad-Hoc request to change designs other than Design Team's design | > Design team is not responsible for updating designs created prior to PAS5 > Directly the code can be updated with the required changes post verification from design team member > Scenarios can't be partially automobale or partial manual, if a validation can't be automated then separate manual scenario to be created. > Check for the priority of the issue regarding PAS 2,3,4 scenarios. > A design ticket can be raised for such requests and new scenario should be created based on priority. > Mark the ticket as additional details requested, design ticket to be used for tracking.
11 | Privileges used in Designs | > Currently in designs, roles and privileges are mapped only against specific steps where validations are present. > Not all filler steps have a role or privilege assigned. > Design team need not mention roles and privileges at every step

## 31st May
# | Points Discussed | Decisions Made
1 | High level Scope Summary | > Need to setup a call to discuss the same
2 | Traceability Task | > Working on optimizing the patterns to get it in the required format
3 | Regression Scope No - Reanalysis | > Some items are pending and will be completed by EOD
4 | Additional PAS9 Items | > Need to start analysis for the additional User Stories added to PAS9 scope.

## 8th June
# | Points Discussed | Decisions Made
1 | Design Ticket Reviews | > Need to pick design tickets for reviews
2 | Automated Document testing | > Varun to follow up with Vibha on these [Removing 53 documents from Automated Doc testing]
3 | Design for Automated Document Testing | > Need to create time point designs for the PAS9 documents which need to be generated [AH60XX,AH61XX,AHAUXX]
4 | Prorate Premium formula | > Need to finalize the approach on this and decide whether the formula should be used or not.
5 | Query Process | > Need to discuss with other teams regarding query process in JIRA.
6 | NY AE1 US: 25444 - NY (about auto tier update) | > Discuss and review design for mentioned US, it was earlier marked in regression scope but now is considered in scope
7 | User Groups in CPs | Need to update this in Base CP's as well, work on list shared by Madhuri on priority. [Check CA CP's as well]
| E34 & L41 Access to renewal image | This needs to updated across CP's
9 | Prorated premium formula | To be discussed with automation, should ask SME how the formula works for large premiums
10 | Defect reviews coming towards end of the week
11 | Defect review process [Primary Review misses] Ex: RRC RTC ID incorrect mapping | Mail sent for the same and response is received
12 | Functional testing pilot | TBD
13 | Weekend logic for a policy across multiple transactions [Cancellation/Bill etx]
14 | Updated to Cancellation beyond NB discovery timeline for MD | To be updated once clarification is resolved.

## 22nd Jun
# | Points Discussed | Decisions Made
1 | HDES Conversion WI analysis | > Need to setup a session with Shree/internal team on the same
2 | PAS10 Functional Pilot in Progress | > Focusing on 30 WI to be analyzed.
3 | Design Tickets | > Open design ticket to be addressed > For invalid design tickets, if there is a pattern in the tickets do bring it to notice of automation team. Take a session with Automation Team. > Issues with the base CP's they are existing, now design tickets are coming to remove these validations.
4 | Response to clarifications | > If the response to clarification is unsatisfactory, even after multiple queries. Then take it up with the onshore team with required details.

## 23rd June
# | Points Discussed | Decisions Made
1 | HDES Conversion WI analysis | > A session with Tushar took place and some of the queries were answered.
2 | PAS10 Functional Pilot in Progress | > Looked at 4 more WI categories and did a quick high level analysis to check reusability as opposed to the detailed Functional/Regression Analysis.
3 | Design Tickets | > As discussed, keep a track of design tickets that are impacting base scenarios, specially CL-CP's since had they been identified in earlier releases the change impact would have been lesser
4 | Queries | > Query process needs to be implemented, ask the other team members to follow the query flow in JIRA so that all the queries are tracked and available for future reference.
5 | Burndown | > Beginning of the week, overall release burndown and weekly targets to be shared.
# | Feedback points to Automation team
SR NO | Points | Examples
1 | Design tickets coming in late for designs coming from previous releases(design steps not being followed correctly) | a. CL-CP-116 – AHAUXX generations - (Count of scnearios: 6) b. CL-CP-118- update to reinstatement date (Count of scenarios:3)
2 | Second copy generation of same form | a. CT-CPs
3 | Miscommunication to the Manual team from Automation team | (Scenario ID : T-HO-HO3-SCL-184)
4 | Issues (Invalid design tickets) | Examples : a. Asking to specify the base behavior in the design (Design ticket ID's : DEMO-42616) b. Steps are not being followed correctly (Design ticket ID's :DEMO-42436 )

## 24th June
# | Points Discussed | Decisions Made
1 | PAS10 Pilot | > Design are in progress, 20 AC designs completed.
2 | HDES Discussion | > Siddhi had a follow up call with Tushar and Anusha. > To start analysis of HDES User Stories

## 27th June
# | Points Discussed | Decisions Made
1 | PAS Core: Sprint 6 Analysis and Design is complete | > This week, PAS Core would be supporting the Manual Execution/RCA team
2 | PAS Factory: Functional Pilot [PAS10] is closed | > Need to check with Jerry on the schedule of items moving to QA Approved/ Test execution complete/ Test Development complete (and cover it as part of regular Regression)
3 | Production Defect Analysis | > Production defect analysis is in progress
4 | Coverage Heat map | > Going forward, this needs to be done as soon as the final designs are delivered.
5 | Design Tickets | > Team to close the design tickets from past releases
6 | PAS10 Regression | > PAS10 analysis to be picked up > Need to prioritize the WI that will be "Development Complete" / "Ready to Build" by week-ending (1st July) > Connect with Jerry to check on the Sprint 19 planning deck [Kick Off Deck] > There are some Tier 1, Tier 2, Tier 3 which have a schedule assigned to it, check for the same.
7 | Retrospection Call [PAS 9] | > Retrospection call to be scheduled on this Wednesday. [27/06/2016]

## 28th June
# | Points Discussed | Decisions Made
1 | PAS9 Additional Scope | > Design team to continue to check for Additions to PAS9 base scope till last milestone of PAS9. > In case of new additions, check when the additions had come in and inform Jerry about the same and take the necessary course of action. > This activity was performed by Harsh during WSR creation. > This check ideally should be performed every Monday.
2 | Updates to CP114 | > In design ticket for CL-CP-114, though the release was marked as PAS6, issue cropped up in PAS9 [Privilege related]. > The change to Base CP will impact 2 CP's in PAS9. These need to be updated on priority, for CP's before PAS9 delta CP's will not be updated. But Base CP will be updated in PAS9 suite. > Keep a note of previous release CP's that are to be updated for future reference.
3 | CP107 Issue with Content Validation | > For CA update the US reference in JIRA, update the pattern ID and Regression Thread. > For CL create a new scenario with the AC's to be validated and tag it to Manual Thread > Existing CP designs, pattern and JIRA will not be updated for now. Need to check with Madhuri on this
4 | PAS10 | > Setup a call with automation team before finalizing the analysis and design approach for Conversion Items > Burndown may need to be adjusted based on the inputs from Automation. > Siddhi to provide the WI to be uploaded in JIRA to Shireesh. > WSR to be published to internal leadership with Burndown, Risks etc.

## 29th June
# | Points Discussed | Decisions Made
1 | PAS10 Analysis | Harsh: 1 WI started Chandni: 1 Analyzed 1 in progress Siddhi: To review the items currently in 'Ready for Review'
2 | Document Automation Scenarios PAS9 | > Document Automation scenarios of PAS9 are still in open state, need to check with concerened team on how it is being tracked.
3
4

## 30th June
# | Points Discussed | Decisions Made
1 | PAS10 Analysis | > AC Count should only be DELTA AC Count > In PAS10 child US, there are completely greyed out AC's stil those should not be included in analysis. BCT: > Design team may have to look at the US from BCT perspective. > Sravan to take a session with design team to give an overview on the kind of functionalities covered as part of BCT.
2

## Pending activites
SR NO | Activity | Description
1 | User group updates to base CPs (i.e. CL-CPs) | As per automation team's request user groups have been updated in only PAS9 state CPs. Same updates to base CPs are pending
2 | CP-107 Update
Pending activities: To be picked up when bandwidth is available with design team

## 1st July
# | Points Discussed | Decisions Made
1 | PAS10 Analysis | > Once the Group 1 & Group 2 items are analyzed except conversion and capping, start with the design for Group 1 reusable AC's.
2 | BCT Analysis | > To avoid reanalysis of WI by BCT team, design team to categorize the WI that may impact BCT/will be in BCT scope. > As part of Regression, other teams create policies and perform various transactions. > BCT team takes already created policies from production and once the latest build is deployed in regression, BCT team takes the policies retrieved from production and run a list of important jobs [Functions] in the regression environment. This is is called batch processing. 2nd Type of activity is online validations [Endorsements etc performed on policy] Ex:- During Analysis is you come across a US saying for existing policy if you do an endorsement following changes would happen. Important Points: 1. BCT team does not work with quote creation, hence no NB US should be assigned to BCT. 2. Endorsement/Renewal and other such functionality is in BCT scope. 3. User Stories realted to Multiple time shifts, such as generating cancel notice, then cancellation is not in BCT scope. They do not follow time shifts. 4. Document Generation is not in scope for BCT team, however, if there is a change in timeline for a particular document generation that can be informed to BCT team. 5. Change in time line for Renewal Image generation/offer generation/ cancellation notice/cancellation confirmation for any existing state etc needs to be informed to BCT. 6. Content validation is not in scope of BCT. > Sravan would be sharing the list of batchjobs and BCT regression scoping guideline with design team.

## 4th July
# | Points Discussed | Decisions Made
1 | PAS10 Analysis | > Team to start with the designs for the US that are Development Complete/Ready to Test > For US that are RTC Status 'Cancelled', may have to create a new Workflow where an Analyzed US can be moved to 'Cancelled' : TBD > Individual authors to connect with reviewers to get the US closed so design can be initiated.
2
Inputs from Automation team for PAS10 designs
Inputs from Automation team for PAS10 designs |  |  | Design team comments
1 | New Scenarios or Modified Scenarios | > Automation team would like to know, how many designs are undergoing enhancements and how many are getting designed newly. > Design Team to inform RCA team which designs are getting updated in PAS10, so that they are not picked up. | Based on the available information, difficult to provide these counts (for at least 2 weeks)
2 | Duplicate Form Generation | > Due to automation framework constraints duplicate form generation cannot be done. Design team to avoid marking such validations in Automation scope. | Started including from PAS9 onwards
3 | Privileges - Renewal Related Validation | > If possible design team should use E34/L41 for steps at Renewal, since A30 does not have many privileges at Renewal. Ex: Early Policy Renewal Inquiry | Wherever steps/validation are present at R-R1, use of E-34 is specified. Automation team to continue with the same role until the next role is specified. Automation team to point out cases where user group is completely missing at renewal time points
4 | Privilege Sheet | > As confirmed, automation team is familiar with the use of consolidated privilege sheet. >For inputs on Overriding privileges - Need to connect with Sudha and setup a session with Jishnu | NA
5 | Doc Gen Scenarios | > For Document Generation scenarios, Design Team should include the Document ID/Form ID that is generated in XML and not directly as per User Story. > Wherever the document is available, design team to mention form ID as mentioned in the forms mapping sheet. | Automation team to provide design team with the link to the latest sheet which specifies the details about Document ID in XML is located.
6 | Time Point Clashes | > Design team has identified time point clashes in Design, 1 time point clash was missed | NA
7 | Logging Steps | > Some of the logging steps in the design document are not applicable to all the products. Design team to either remove these based on Suggested product or mention if statement. > Suggestion: Design team to just cross check that the fields/pre-conditioned mentioned in the design are as per the Suggested Product. | > Design team : This is already followed and would be more thorough going forward
8 | Time Lines for Auto | > Design team has created time point sheets for all the states being rolled out. > As part of stabilization, Dipti and Ved may create one consolidated time point sheet for Auto. | NA
9 | Multiple Privileges for 1 transactions | > Design team to avoid including multiple privileges for one transactions. | The user privileges are mentioned as per the user story. Automation team can chose either of the mentioned privileges as they will be associated with corresponding role. The expected result will not be impacted.
10 | Time Point Updates | >Some of the time points in the time point sheet do not have weekend logic. | > Design team : Weekend logic is mentioned for most of the time points. Wherever there is no weekend logic 'NONE' is called out. For the one's where it is missing, it will be updated based on the available bandwidth.
11 | Design Ticket & Queries | > There are 3 possibilities: i. Design Ticket - If the design step is not as per the requirement that is mentioned against it, then a design ticket needs to be raised. ii. Defect - After verifying that the design steps are in sync with requirement, if the outcome is not as per design/requirement, then a defect should be raised in JIRA as per the process. Note: Defect confirmation cannot be provided over query. iii. Query - If there is an ambiguity in the design and the same cannot be cleared after looking at the user story, then a query should be raised. Note: Query workflow currently is against the Design Sub-Task, this flow may change. Design team will adhere to SLA of 2 Hours for Query Resolution as proposed by Automation team. | Queries raised after 4:00 PM on Fridays will be picked up on Mondays

## 5th July
# | Points Discussed | Decisions Made
1 | Next items for analysis | Non-Conversion items from Group1 and Group 2 will be exhausted by mid-week (8th July) Based on the response from onsite regarding availability of conversion XMLs (Bhushan to provide confirmation), design team will pick up Either 1. Non-conversion items from group3 and group 4 OR 2. Conversion items from group1 and group2

## 6th July
# | Points Discussed | Decisions Made
1 | First Time Right Ratio [FTRR] | > As per the analysis of week ending 1st July, the FTRR is not satisfactory. [Details to be shared later] > Design team to bring any concerns during analysis itself to Siddhi/Gurpreet so as to avoid review comments later.
2 | SLA for Design Tickets | > In case of design tickets, design team does inform and confirm the changes to tester. It's only the flow in JIRA that at times is not completed on time due to other deliverables. > Confluence update currently has been fixed for 2 days a week. [Tuesday/Friday] > SLA for the design ticket is 1 day as discussed. Need to decide if the SLA depends on updated design delivery.
3 | PAS9 Design Tickets | > For Design tickets related to PAS9 or earlier designs, should we update the PAS9 Suites or start updating the PAS10 suite? > Need to check with Automation team on which approach is feasible for them
4 | PAS10 Analysis | > There has been a case where User Story had some AC's as hidden in the excel file. Design team will be raising a clarification to find out if that has any significance. > Design team to perform this check whenever they analyze the user stories to see if more such cases exist.
5 | Multiple Privileges for one transaction | > Design team should mention just one privilege in the design even if multiple privileges are applicable going forward.

## 11th July
# | Points Discussed | Decisions Made
1 | PAS10 Analysis | > Continue analysis of Group 3 and 4 Non Conversion items > Conversion items have a dependency on XML's. > Harsh to check with Tushar/Anusha regarding the XML's and capping related items
2 | PAS10 Regression Scenario | > The scenarios have been uploaded them in JIRA > When marking the scenario as Design Complete in JIRA, cross check the details such as Delta AC Count Total AC Count Scenario Type etc. from the pattern sheet. Same to be done during review as an additional check > For patterns coming from previous releases, old scenarios need to be marked as Obsolete [Siddhi/Varun to look into this] > Completed Designs may again be re-opened in JIRA by enhanced design, when further analysis is done

## 12th July
# | Points Discussed | Decisions Made
1 | Discussion With Automation Team on PAS10 Designs | > Automation team will inform design team if the Agile approach is feasible. > Need to finalize if Group 1 & Group 2 AC's will be combined with Group 3 & Group 4 AC's > Design
2 | Changes to US after analysis | > It was observed during PAS Core analysis, that a new version of a US was created in the same release as the status of the RTC item was not QA Approved. > There may be cases like above in the analysis done by Factory team as well. Need to check for such cases.
3 | Automated Exception US PAS10 | > In group 1 and 2 US AE6 was retiring and was replaced with Fire line score US. > In group 3 and 4 US AE2 & AE3 were retiring and were replaced by AE1 US. > AE2 and AE3 US will be marked as no and existing patterns that are getting impacted should be mentioned in comments. > Analysis of these US are taking more time than usual since patterns across release are getting impacted.
4 | Task Management US | > These contain tasks from multiple US, hence analysis of task management US is taking a little longer than usual.
5 | Marking Regression Scenarios Obsolete in JIRA | > For scenarios that are being opened from previous releases, new regression scenarios will be created for those. Hence, for the old regression scenarios put a label 'To be Obsolete in PAS10' and RCA team can later mark them obsolete.

## 13th July
# | Points Discussed | Decisions Made | Additional Comments
1 | PAS10 Overview to Early Regression Team | > Need to give an overview to Early regression team on the kind of changes that are coming as part of PAS10. | 1. UBI 2. UW Rules 3. HS 04 20 form title is getting updated
2 | Regression Reusability | > AC's that are striked out and just US update is full reusability and no effort is logged.
3 | RCA Impact | > Need to inform RCA team about the patterns that are getting updated or patterns that are completely getting obselete.

## Sheet2
# | Points Discussed | Decisions Made | Additional Comments
1 | Defect Reviews | > Please ensure you mention the exact time that was spent in review. It is noted that, we're logging less time than what we actually spent. > Time spent should include the initial discussion and interim discussions. > Do inform team members who are not aware on how a US can be searched and how to look up RTC.

## 19th July
# | Points Discussed | Decisions Made | Additional Comments
1 | PAS10 Analysis | > Team to start analyzing 'WI0162 CA HDES Conversion' and 'WI0208 CA Prop Conversion SIS-DP3 and Foxpro-PUP' respectively.
2 | PAS10 Design Merging with old scenarios | > To check with Shree if we can merge new designs with older defect designs. > Also, if we can change Scenario Type. For Ex: Changing a functional scenario to calendar on adding more AC's Discussed with Shree: > As long as we can maintain the traceability and logical flow, we can reuse the old designs [Funtional/Timepoint/Calendar/Defect] and change the scenario type if/when needed.
3 | Design Completion in JIRA | > While marking Design SubTask as 'Complete' in JIRA, validate the details from the pattern sheet. > Ensure that the DesignSubtask, Scripting SubTask and Regression Scenario have details in sync.

## 20th July
# | Points Discussed | Decisions Made
1 | PAS10 Conversion WI Analysis | > There are items which are common to Conversion Policies and Organic (PAS Originated) in this case we need to check impact on existing scenarios and create new scenarios for Conversions.
2

## 29th July
# | Points Discussed | Decisions Made
1 | PAS10 Conversion WI Analysis | > There are items which are common to Conversion Policies and Organic (PAS Originated) in this case we need to check impact on existing scenarios and create new scenarios for Conversions. > For AC's that can be newly designed, check if a common pattern can be created for Conversion/Non Conversion Scenario. [To check the feasibility of this with Automation] Note: Since no such US [US with generic functionalities having no prior coverage] have been identified this approach will be on hold. > If 1 US talks about multiple products, please note (HO3,HO4,HO6) come from the same Legacy System. DP3 and PUP come from separate systems. In this case we can't deprioritize AC's by saying covered as part of other product.
2

## 2nd August
# | Points Discussed | Decisions Made
1 | PAS10 Conversion US Analysis | > Cases where US is applicable to both PUP & DP3 - In this case we need to create designs for both PUP and DP3 for AC's in regression scope. > Before deciding an approach, we need to find out the count of US that are applicable to PUP & DP3.

## Feedback to Automation Team
# | Feedback points to Automation team
SR NO | Points | Examples
1 | Design tickets coming in late for designs created in previous releases(design steps not being followed correctly). Such late changes to base CPs impact huge number of state variant CPs. Need to understand how these changes were missed in PAS6 when base CPs were finalized | a. CL-CP-116 – AHAUXX generations - (Count of scnearios: 6) b. CL-CP-118- update to reinstatement date (Count of scenarios:3) c. CL-CP-107 - Timeline for generation of HSRR2XX - (Count of scenarios :14)
2 | Second copy generation of same form: Was designed and delivered in PAS8 as part of CT-CPs . However the non-feasibility was pointed out only in PAS9. Need to check how such validations were handled in CT-CPs. | a. CT-CPs
3 | Miscommunication to the Manual team from Automation team | (Scenario ID : T-HO-HO3-SCL-184)
4 | Issues (Invalid design tickets) | Examples : a. Asking to specify the base behavior in the design (Design ticket ID's : DEMO-42616) b. Steps are not being followed correctly (Design ticket ID's :DEMO-42436 )
5 | removal of validations w/o communicating to design team? | Doc valdiations removed from CPs
6 | Constraint with Auto policies with pre-conditions | > For automated endorsement, scenarios have been created with pending auto policies which later become active. This is restricted due to Framework conststraints and can't be automated. But such validations are existing from PAS6 decision to remove/change designs in PAS9/10 causes major a lot of rework.

## Sheet3
# | Points Discussed | Decisions Made | Additional Comments
1 | Background to the introduction of MVR Report Redesign | > The fee associated with ordering reports is quite high and business spends a lot of money in ordering reports. > Business decided rather than spending that amount in quotes, they would instead spend it when the quote is bound. > Mostly it is the MVR and CLUE that have now been moved to Purchase screen and should be ordered on click of purchase, however an authorized user can order these during quote. [To confirm further when requirements are analyzed] > Now there may be self-reporting initially at the time of quote creation and later the data will be verified with the data received from reports. How any discrepancy is handled and premium is adjusted is something that we may get an idea from requirements or may need to reach out to QA coordinator for the same. | NA
2 | Expectation from Regression Team for MVR Report Redesign Analysis | > Regression team to follow the classical approach which is :- - To use as many existing tests to check the functionality, modify some of the existing tests based on the requirements. - Add new tests based on the requirements. Ex- New Rules/Authorities that need to be tested. > Leverage the high level analysis and the existing notes that have been shared. | NA
3 | How to differentiate Major/Minor user stories coming as part of Sprint 20 | > There are about 89 User stories as per the earlier spread sheet that have 'Unique Business Priority' filled. These are most likely to be the Major US and the rest would be minor. > Mail has been sent to Jennifer for the same. | Regression design team have got the response for the same. There are about 82 User stories and these are all major. Regression team not to look at minor user stories for now
4 | How to leverage the test packages created by Balvinder for Regression and how to retrieve the same | > Regression team should follow their own approach of requirement analysis and creating tests comprising multiple features > Test packages created by Balvinder can be used for reference and for understanding how specific features are being tested > Mail sent to Balvinder for information on how to look for and retrieve the test packages | Regression design team have got the response for the same. The test packages for the major versions are attached as usual to the RTC work item.
5 | Major updates to functionality Vs New Functionality | > Need to understand if most of the user stories are updates to existing functionality or are new functionality. Based on this the analysis can be either done by Regression Team or given to RCA > The approach can be decided once we look at the requirements, it could be a mix of update to functionality and new functionality. > We can also choose to run our scripts and see where it is breaking. Somewhat similar to what was followed for UI simplification. Regression team to take a call on which approach is more feasible. | NA
6 | Detailed testing for MVR testing - Can we have tests where somehow through the scripts we can setup the data in a way that user reported date is same as the MVR report data to avoid major script updated? | > It is important to test how the system handles discrepancy between the self-reported data Vs what comes from the MVR report. So we will need tests around this
7 | Technical details such as Caching and overview | > Conference call with one of the developers to get more details on this aspect can be setup when required.
8 | Is functionality changing only for MVR or other reports | > There are updates to CLUE reports, not really updates to membership reports, insurance scores. > Since the reports are on the same screen, arrangement and navigation can be different. > Changes in CLUE may impact property as well. Since this category is being rolled out in multiple phases, first phase is mainly focusing on Auto. Subsequent phases may have requirements for property.
9 | Impact on integrations | > Ideally there should be no impact on integrations. However there are requirements coming in for integrations and more details can be found in those requirements about the kind of impact.
10

## 4th Aug
# | Points Discussed | Decisions Made
1 | Conversion User Stories | > Some of the basic checks need to be performed for converted policies. Ex:- Source policy # , Source system. Though this is not in RSG scope we will be including this in regression for Conversion [1 AC] > Suppression of documents ideally not included in regression, but an exception has been made for Conv US.
2 | Design Status | > For conversion only pattern - AC count not sufficient to start design > Generic US/Patterns - Decision still pending > Hence converting AC design count to US analysis count
3 | ForPro & SIS US where PUP/DP3 are common | > Cover validation for both the products > Mark both the patterns against the AC in JIRA.
4 | Sample Scenario for Conversion | > Pattern 810/813/815 - Create design for one of the patterns and send to automation team
5 | MAIG Related User Stories | > We have not analyzed any user stories from this category as of now.
6 | Cost Analysis | > The sheet is updated > Both the approaches discussed, confirmation mail will be sent out to automation team with sample design

## 9th Aug
# | Points Discussed | Decisions Made
1 | SIS Fox Pro Conversion | > Some of the important generic validations should also be tested on SIS/Fox Pro converted policies. > Based on the decision for CA HDES conversion approach, decision can be taken for SIS Fox Pro conversion.
2

## MOM CP Optimization
# | Points Discussed | [5 empty] | Decisions Made
1 | Coverage of important functionalities on Converted Policies | [5 empty] | > Split CP's in Calendar and keep only the important validations that are required
2 | UI Validation | [5 empty] | > While optimization, ensure UI validations are removed Ex: Post rewrite is performed, validate XYZ fields.
3 | Partially Automation AC's | [5 empty] | > Design team should remove such validation from the optimized scenarios > For the manual validation separate scenario needs to be created
4 | Multiple transactions at the same timeline/across timeline | [5 empty] | > Optimize steps and if possible try to limit transactions and group them in a logical flow > If there are transactions in 2 timelines that can be done at same time point then combine them logically > If multiple endorsements are done at the same time points, try to combine those. Ex: One of the scenario has 2-3 endorsement at the same time point
5 | Scenarios that go until 2R, 3R | [5 empty] | > Try to limit the CP's to 1R > In case a validation has to be performed at 2R/3R then retain it as part of separate calendar scenario > If an existing validation that is happening at 2R/3R can be performed at 1R then these should be moved to 1R and to be adjusted in 1R. Recommendation: CP should be completed at 1R + 2DD3 at max
6 | Filler steps that are missing | [5 empty] | > Design team will be providing important filler steps > For basic filler steps that may be missing that need to be handled in Code
7 | Overlapping Time points | [5 empty] | > Keep a difference of at least 5 days between 2 validations > Handled in CL-CP. CA CP are to be updated as part of optimization
8 | Billing validation/Amount Related Validation (Discussion still pending) | [5 empty] | Ex: Perform an AP endorsement and validate billing is updated > In such cases during parallel execution additional transactions appear which leads to fail in validation Ex: $100 is due. Payment is made within short pay tolerance $90. Check policy status > In system due to various transactions such as cross-policy transfer etc. the policy status is updated.
9 | Redundant Preconditions | [5 empty] | > If there is no validation associated with a precondition then precondition should be removed > In case a validation is no longer valid based on requirement update, then the respective pre-conditions should be removed as well
10 | Redundant validations across multiple CP's | [5 empty] | > Redundant validations across CP's will be removed as part of optimization (ex. Same validations duplicated across multiple CPs)
11 | Document generation validation Steps performed just for generation of document Ex: Cancellation Notice setup, Cancellation Notice Removal | [5 empty] | Design Team: > CP's were created for checking these core transactions, hence these validations will be retained in the CP's Automation: > There have been cases where because of setting pre-conditions only for generation of documents, defect have been observed and the CP's have been put on hold through multiple releases due to which subsequent validations are not performed. > Can such validations be moved to separate Calendar scenarios or split into multiple CP's (TBD) Recommendation: > Have the document generation validation with the validation of setting cancel notice etc. > Reinstatement Notice generation should be in a scenario where reinstatement is also a validation not just a logging step.
12
13
# | Description | Priority | Responsibility | Date Opened | Due by Date | Date Completed | Additional Notes | STATUS
1 | Removal of UI Validations : Automation team to provide the list of scenarios containing such validations | Medium | Dipti/Madhuri | 2016-08-09
2 | Partially automable validations to be removed : Automation team to provide the list of scenarios containing such validations |  | Dipti/Madhuri

## Production Defect Analysis
# | Points Discussed | Decisions Made
1 | Production Defect Analysis | > Ongoing activity, a person picks up production defects and sends it across to Functional/Regression team
2 | Release Focus | > Defects post PAS4 are required to be analyzed
3 | Analysis by Functional Team | > Functional team marks the defects that need to be looked at by Regression
4 | Regression Team Inputs | > We should request for analysis on a weekly basis in small chunks rather than having huge number of defects coming in
5 | Categorization of Analyzed defects | > Regression Gap - [Category to be mapped] > Covered in Regression (Change after QA Sign off) - Test Passed > Not a Regression Scope (Reason) - Not in Regression Scope [Change in definition for Point 1] > Invalid - Invalid Defect To check if the above categories are mapped correctly. Note: Perform a check on defects analyzed for updated state

## 10th August
# | Points Discussed | Decisions Made
1 | CP Optimization | > Team to prioritize CP optimization
2 | PAS10 Analysis - Pending/Open US | > 090-116CL Ability to calculate Capping > 27154 -Tasks > 25733 - Privilege > UBI to be closed
3 | FoxPro Designs | > Designs to be put on hold for today 10th August > 6 AC's already designed
4 | UBI - Removal of participation discount | > Since this is time bound validation, we will test it by reducing the value of no. of terms to 1-2. [Current Configuration 50 terms] > As per RSG discount removal criteria is a no, but since participation discount is an important validation we can cover this in Manual/RBT > Changes need to be made in US already designed

## 25th August
# | Points Discussed | Decisions Made | Ownership
1 | Updates to BookRoll Items | >Items that are in update status should be moved to secondary status | Harsh
2 | High Level Analysis of SP20 FoxPro WorkItem | > High Level analysis of SP20 FoxPro work Items to be done to see if these can go into anyof thepatterns before it starts for designs | Harsh
3 | Product updates to either scenario 864 or 866 to make sure they run on different products for better coverage | > Functional team marks the defects that need to be looked at by Regression | Harsh
4 | Update suggested product of Scenario 867 | >Scenario 867 should be run for DP3 product instead of HO3 as it is a SIS and FoxPro work item and the Delta has come for DP3/PUP product | Harsh
5 | Clarification to be raised for PUP product AC under HDES | > Raise Clarification for PUP specific AC's in HDES US to check if the convereted policy would come from FOxPro system or its wrongly create under HDES US | Harsh

## 30th Aug
# | Points Discussed | Decisions Made
1 | CP Optimization | > Team to prioritize CP optimization - Varun and Siddhi to work on it
2 | HDES - Reopened Calendar scenarios | > 1 person to work on designs of reopened calendar scenario (Harsh)
3
4

## 1st Sept
# | Points Discussed | Decisions Made
1 | MAIG Item | > To take an high level scan at MAIG user stories and initiate discussion with onsite team if required. [Preparatory work for next week's analysis]
2 | MVR Report Redesign | > Get in touch with Gurpreet and get all the required mails related to MVR. [Preparatory work for next week's analysis] > Initiate discussion with onsite team if required. [Varun]
3
4

## 6th Sept
# | Points Discussed | Decisions Made
1 | MVR Report Redesign | > Varun had a word with Sudha, 16 US were analyzed of 82 on high level. > Most of the US were impacting existign scenarios and were UI related. Some US were related to functionality changes > Harsh to analyze a sample of 10 US (Excluding the 16 already analyzed by Sudha). Based on the analysis an approach can be decided on MVR category.
2 | MAIG | > 5 US to be analyzed this week of the 29
3 | CA CP Optmization | > Pattern Analysis to be closed and sent for review by today EOD or max tomorrow. (7th Sept)

## 0915
# | Points Discussed | Decisions Made
1 | MAIG | > Analysis and Design is completed for MAIG (4 US) > 1 US related to capping is pending >
2
3

## 0929
# | Points Discussed | Decisions Made
1 | PAS10 Analysis & Design | > Prioritize non HDES items and finish the analysis and designs.
2
3

## 0930
# | Points Discussed | Decisions Made
1 | PAS10 Analysis & Design | > Work on the Inflation Guard WI's. > CA CP's that are impacted can be updated.

## 4th Oct
# | Points Discussed | Decisions Made
1
2
3