## Pivot 8July
Design Status | Count of Key | Review Status | Count of Key
Clarification Pending | 1 | Complete | 24
Complete | 24 | Grand Total | 24
Grand Total | 25
Design status | Complete | Regression Thread | (Multiple Items)
Row Labels | Count of Key | Row Labels | Count of Pattern ID / Scenario ID/ TestCase ID / Test Case Name
In Development | 9 | Full | 2
In Testing | 12 | New | 12
Ready To Test | 3 | Partial | 10
Grand Total | 24 | (blank) | 1
|  | Grand Total | 25
Design status | (Multiple Items)
Row Labels | Count of Key
C-AU-SS-CL-169 | 1
C-AU-SS-CL-471 | 1
C-AU-SS-CL-799 | 2
C-AU-SS-CL-800 | 1
C-HO-HO3 -SCL-CT-766 | 1
C-HO-HO3-CA-804 | 1
C-HO-HO3-CL-790 | 1
C-HO-HO3-CL-798 | 2
C-HO-HO3-CL-802 | 2
C-HO-HO3-CL-805 | 1
C-HO-HO3-CO-801 | 1
C-HO-HO4-CL-676 | 1
C-HO-HO6-CL-267 | 1
F-HO-HO3-ID-670 | 2
F-HO-HO3-OR-702 | 2
F-HO-HO6-NV-658 | 2
T-HO-HO4-DE-185 | 1
T-PU-PUP-CL-691 | 1
D-T-HO-HO3-NV-786 | 1
Grand Total | 25

## Designs_8_July
RTC ID | Group | Status | Status_8thJuly | Status_11thJuly | Status_11_July | Key | Summary | Allocated To | RRC ID | Pattern ID / Scenario ID/ TestCase ID / Test Case Name | AC No | Regression Reusability | Regression Thread | Labels | Design status | Design complete date | Reviewer | Review Status | Review Complete Date | Review comments
611191 | Group 01 | In Testing | In Testing | In Testing | In Testing | DEMO-44556 | DEMO-42466 Underwriting Guidelines:- When AE = N and Manual UW Exception = NCommercial property with more than four units are ineligible. | NA | 26630 | RBT | 13 |  | RBT |  | RBT |  | NA | RBT
624529 | Group 02 | In Development | Ready To Test | In Testing | In Testing | DEMO-44552 | DEMO-44050 Renewal - Dwelling address changeProduct - HO4 | Chandni | 26885 | C-HO-HO4-CL-676 | 8 (Rule AC 7) | Partial | Manual |  | Complete | 2016-06-07 | Gurpreet | Complete | 2016-07-08 | Scenario description updated
624529 | Group 02 | In Development | Ready To Test | In Testing | In Testing | DEMO-44550 | DEMO-44050 Enable NB rules at Midterm where - Endorsement Date = Policy Effective Date | Harsh | 26885 | C-HO-HO3-CL-798 | 6 (Rule AC2) | New | Automation |  | Complete | 2016-05-07 | Siddhi | Complete | 2016-07-06 | applicable to design CL-798: DD0: 1. Update paymnet plan 2R 2. Step#3: Is stub data needed for PPC=10 , if yes mention that in design 3. Not sure why do we need to override insurance score 4. Step$4 i) specifiy the exact roof type to be selected. DD4-20: 5. Step#1: Not sure why is E-34 being used to login. (Instead F35 should be used) 6. Step#4 to #6: All of these conditions need not be set, failing any 1 condition can suffice for validation #V2. 7. Step#8: Once the WM is valdiated, please login with E-34, override the error and proceed. 8 Even though validations end at DD4-20, write the remaining billing fillers as as per the payment plan.
624529 | Group 02 | In Development | Ready To Test | In Testing | In Testing | DEMO-44545 | DEMO-44050 Determine Eligibility PPC rules satisfiedProduct - HO3/HO6/DP3 | Harsh | 26885 | C-HO-HO3-CL-798 | 1 | New | Automation |  | Complete | 2016-05-07 | Siddhi | Complete | 2016-07-06 | applicable to design CL-798: DD0: 1. Update paymnet plan 2R 2. Step#3: Is stub data needed for PPC=10 , if yes mention that in design 3. Not sure why do we need to override insurance score 4. Step$4 i) specifiy the exact roof type to be selected. DD4-20: 5. Step#1: Not sure why is E-34 being used to login. (Instead F35 should be used) 6. Step#4 to #6: All of these conditions need not be set, failing any 1 condition can suffice for validation #V2. 7. Step#8: Once the WM is valdiated, please login with E-34, override the error and proceed. 8 Even though validations end at DD4-20, write the remaining billing fillers as as per the payment plan.
627378 | Group 02 | In Development | In Development | In Development | In Development | DEMO-44543 | DEMO-42474 Prefill Mailing address along with dwelling address | Harsh | 27100 | C-HO-HO3-CA-804 | 25 | New | Manual |  | Complete | 2016-06-07 | Gurpreet | Complete
627377 | Group 02 | In Development | In Development | In Development | In Development | DEMO-44535 | DEMO-42473 Prefill - Prefilled Dwelling address zip is in different State | Harsh | 27106 | C-HO-HO3-CL-805 | CL-31 |  | Manual |  | Complete | 2016-06-07 | Gurpreet | Complete
624537 | Group 01 | Ready To Build | In Testing | In Testing | In Testing | DEMO-44515 | DEMO-44040 Fireline Zip Non-Match | Harsh | 26956 | F-HO-HO3-ID-670 | ID-02 | Partial | Automation |  | Complete | 2016-01-07 | Siddhi | Complete | 2016-07-05 | Corrected scenario description Corrected date #V3: removed statement 'AE6 model passes'
624537 | Group 01 | Ready To Build | In Testing | In Testing | In Testing | DEMO-44513 | DEMO-44040 Fireline Zip Match | Harsh | 26956 | F-HO-HO3-ID-670 | ID-01 | Partial | Automation |  | Complete | 2016-01-07 | Siddhi | Complete | 2016-07-05 | Corrected scenario description Corrected date #V3: removed statement 'AE6 model passes'
623086 | Group 01 | Ready To Test | In Testing | In Testing | In Testing | DEMO-44485 | DEMO-44391 Renewal Rule generation to Underwriter for Usage based Insurance .Rule No to 200777 | Varun | 130-380CL | C-AU-SS-CL-169 | 130-380-16CL | Partial | Automation |  | Complete | 2016-07-04 | Siddhi | Complete | 2016-07-06 | Updated following during review 1. modified release 2. scenario description 3. Removed step#2 at R-R5 4. Added note regarding negative validation
618706 | Group 02 | In Development | In Development | In Development | In Development | DEMO-44500 | DEMO-42478 System binds the quote or policy when Insurance Score is Declined for all Named Insureds | Harsh | 26817 | C-HO-HO3-CL-802 | CL-39 | New | Automation |  | Complete | 2016-06-07 | Gurpreet | Complete | 2016-07-08
618706 | Group 02 | In Development | In Development | In Development | In Development | DEMO-44501 | DEMO-42478 Compare Insurance Score when ordering is done for more than one Named Insured - No hit and Declined | Harsh | 26817 | C-HO-HO3-CL-802 | CL-40 | New | Automation |  | Complete | 2016-06-07 | Gurpreet | Complete | 2016-07-08
624545 | Group 01 | Ready To Build | In Testing | In Testing | In Testing | DEMO-44469 | DEMO-44069 Fireline Zip Non-Match | Harsh | 26973 | F-HO-HO6-NV-658 | NV-02 | Partial | Automation |  | Complete | 2016-01-07 | Siddhi | Complete | 2016-07-06 | Corrected scenario description Corrected date, Author Updated validations V1 V3 which were mentioning AE 6 pass or fail
624545 | Group 01 | Ready To Build | In Testing | In Testing | In Testing | DEMO-44468 | DEMO-44069 Fireline Zip Match | Harsh | 26973 | F-HO-HO6-NV-658 | NV-01 | Partial | Automation |  | Complete | 2016-01-07 | Siddhi | Complete | 2016-07-06 | Corrected scenario description Corrected date, Author Updated validations V1 V3 which were mentioning AE 6 pass or fail
624551 | Group 01 | Ready To Build | In Testing | In Testing | In Testing | DEMO-44464 | DEMO-44073 Fireline Zip Non-Match | Harsh | 26958 | F-HO-HO3-OR-702 | OR-02 | Partial | Automation |  | Complete | 2016-01-07 | Siddhi | Complete | 2016-07-06
623080 | Group 02 | In Development | In Development | In Development | In Development | DEMO-44462 | DEMO-44395 Vehicle swaps - Replace button - UBI eligible vehicle - telematics discount | Chandni | 050-145CL | C-AU-SS-CL-471 | 050-145-10CL | Partial | Automation |  | Complete | 2016-06-07 | Gurpreet | Complete | 2016-07-08 | Scenario description updated Modified release updated Legends in the file are missing in Auto Signature series - to be updated still
623088 | Group 02 | In Development | In Development | Ready To Test | Ready To Test | DEMO-44460 | DEMO-44385 Policies without any existing vehicles enrolled in UBI have one new vehicle added and enrolled in UBI or an existing vehicle is enrolled in UBI when endorsed, renewed - rule# 200125 [UW Level 2] | Varun | 180-042CL | C-AU-SS-CL-800 | 180-042-14CL | New | Automation |  | Complete | 2016-07-05 | Gurpreet | Complete | 2016-07-06
623088 | Group 02 | In Development | In Development | Ready To Test | Ready To Test | DEMO-44459 | DEMO-44385 Policies without any existing vehicles enrolled in UBI have one new vehicle added and enrolled in UBI or an existing vehicle is enrolled in UBI when endorsed, renewed | Varun | 180-042CL | C-AU-SS-CL-799 | 180-042-13CL | New | Automation |  | Complete | 2016-07-05 | Gurpreet | Complete | 2016-07-06
623083 | Group 02 | In Development | In Development | Ready To Test | Ready To Test | DEMO-44451 | DEMO-44399 Validation of signed UBI terms & conditions required for mid term UBI additions on a non- UBI policy. | Varun | 020-061CL | C-AU-SS-CL-799 | 200125 | New | Automation |  | Complete | 2016-07-05 | Gurpreet | Complete | 2016-07-06
613282 | Group 01 | Ready To Build | In Testing | In Testing | In Testing | DEMO-44417 | DEMO-42482 Selected Endorsement DisplayProduct - HO3 Heritage | Chandni | 26760 | C-HO-HO3-CO-801 | 1 | New | Automation |  | Complete | 2016-05-07 | Gurpreet | Complete | 2016-07-08
624551 | Group 01 | Ready To Build | In Testing | In Testing | In Testing | DEMO-44177 | DEMO-44073 Fireline Zip Match | Harsh | 26958 | F-HO-HO3-OR-702 | OR-01 | Partial | Automation |  | Complete | 2016-01-07 | Siddhi | Complete | 2016-07-06
620673 | Group 02 | Planned | In Development | In Development | In Development | DEMO-42604 | DEMO-42471 REN - Guns/Firearms | Chandni | 26819 | T-PU-PUP-CL-691 | 15 (AC 7) | Full | Automation, PAS10 Functional |  | Complete | 2016-06-07 | Siddhi | Complete | 2016-07-06 | 1. Update the modified release to PAS10 2. Update the author and date w.r.t. current release 3. R-R5: while reusing a design,existing information (steps/validations/US_AC references) are not to be deleted. They should be striked off in red. Secondary review: Corrected formatting in design sheet and removed valdiation #V11
613283 | Group 02 | In Development | In Development | In Development | In Development | DEMO-42541 | DEMO-42461 Generate Declaration Form at New Business. | Chandni | 26896 | C-HO-HO6-CL-267 | 1 | Full | Automation, PAS10 Functional |  | Complete | 2016-06-07 | Siddhi | Complete | 2016-07-08 | Added precondition during review
624045 | Group 02 | In Development | In Development | In Development | In Development | DEMO-42539 | DEMO-42468 When there is a 'No Hit', 'No Score', 'Declined' Insurance Score | Varun | 26875 | C-HO-HO3-CL-790 | 3 | New | Automation, PAS10 Functional |  | Complete | 2016-07-06 | Gurpreet | Complete | 2016-07-08
611189 | Group 02 | Development Complete | Ready To Test | In Testing | In Testing | DEMO-42534 | DEMO-42465 Generate Privacy Information Notice at Bind | Varun | 26693 | D-T-HO-HO3-NV-786 | 2 | New | Automation, Content Validation, PAS10 Functional |  | Clarification Pending |  |  | Clarification Pending
620672 | Group 01 | In Testing | QA Approved | QA Approved | QA Approved | DEMO-42529 | DEMO-42470 BASIC: Capture Firearms Information | NA | 26821 | FP-C-PU-PUP-CL-767 | 1 | New | RBT, PAS10 Functional |  | RBT |  | NA | RBT
618707 | Group 02 | In Development | In Development | In Development | In Development | DEMO-42527 | DEMO-42479 When there is a 'No Hit' (998)/'No Score' (999)/'Declined' (0) and a valid Insurance Score. | Varun | 26808 | C-HO-HO3 -SCL-CT-766 | 2 | New | Automation, PAS10 Functional |  | Complete | 2016-07-05 | Siddhi | Complete | 2016-07-06
618709 | Group 01 | In Testing | In Testing | In Testing | In Testing | DEMO-42522 | DEMO-42462 Determine best Insurance Score during renewal batch | Chandni | 26802 | T-HO-HO4-DE-185 | 1 | Partial | Manual |  | Complete | 2016-08-07 | Siddhi | complete | 2016-07-08 | revised most part of the design

## Pivot_15 July
Design Status | Count of Scenario ID | Review status | Count of Scenario ID
Complete | 37 | complete | 35
Not in Sprint19 scope | 4 | (blank) | 6
Pending query | 2 | Not in Sprint19 scope | 4
Ready for Rereview | 4 | Pending query | 2
Grand Total | 47 | Grand Total | 47
Design status | (Multiple Items) | Design status | (Multiple Items)
Design Status | Count of Scenario ID | Design Status | Sum of Actual(Converted) AC Count
Automation | 33 | Automation | 55
Automation, Content Validation | 1 | Automation, Content Validation | 1
Manual | 7 | Manual | 6
Grand Total | 41 | Grand Total | 62

## Sheet1
Design status | (Multiple Items)
Row Labels | Sum of total delta count
PAS10_Designs_Delivered_Wk-15July | 19
PAS10_Designs_Delivered_Wk-26August | 22
PAS10_Designs_Delivered_Wk-29July | 62
(blank) | 7
Grand Total | 110

## Designs_Delivery
Scenario ID | Scenario Thread | Full | Partial | New | retired but not replaced | total delta count | Total AC counts | Design Author | Design status | Design complete date | Design Time | Reviewer | Review Status | Review Complete Date | Review comments | Review Time | Label | Delivery Label | Can be Delivered | Additonal Comments
D-T-HO-HO6-CL-752 | Automation | 0 | 1 | 0 | 0 | 1 | 1 | Varun | Complete | 2016-07-13 |  | Siddhi | complete | 2016-07-14 | Made design changes to add endorsement and US reference | 15m |  | PAS10_Designs_Delivered_Wk-15July | Yes
D-T-HO-HO6-CA-782 | Content Validation | 0 | 0 | 0 |  |  | 1 | NA | Not in Sprint19 scope |  |  |  | Not in Sprint19 scope | [6 empty] | In IT team Review
T-HO-HO4-DE-185 | Manual | 0 | 1 | 0 | 1 | 2 | 1 | Chandni | Complete | 2016-07-08 |  | Siddhi | complete | 2016-07-08 | revised most part of the design |  | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-15July | Yes
D-T-HO-HO3-CA-785 | 0 |  |  |  |  | 0 | 1 | NA | Not in Sprint19 scope |  |  |  | Not in Sprint19 scope | [6 empty] | In IT team Review
C-HO-HO3 -SCL-CT-766 | Automation | 0 | 0 | 1 |  | 1 | 1 | Varun | Merged with existing | 2016-07-05 |  | Siddhi | Complete | 2016-07-06 |  |  | Design started in week ending 8th July |  | No
D-T-HO-HO3-CA-786 | Automation | 0 | 0 | 0 | 0 | 0 | 1 | Varun | Merged with existing | 2016-07-28 |  | Siddhi | NA |  | Pattern merged with CA-808
C-HO-HO3-CL-790 | Automation | 0 | 0 | 1 |  | 1 | 1 | Varun | Merged with existing | 2016-07-06 |  | Gurpreet | Complete | 2016-07-08 |  | 20m | Design started in week ending 8th July |  | No
C-HO-HO6-CL-267 | Automation | 0 | 2 | 0 | 0 | 2 | 2 | Chandni | Complete | 2016-07-06 |  | Siddhi | Complete | 2016-07-08 | Added precondition during review |  | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-15July | Yes | Although Design is delivered later 1 AC has been blocked
T-PU-PUP-CL-691 | Automation | 6 | 0 | 0 | 1 | 1 | 6 | Chandni | Complete | 2016-07-06 |  | Siddhi | Complete | 2016-07-06 | 1. Update the modified release to PAS10 2. Update the author and date w.r.t. current release 3. R-R5: while reusing a design,existing information (steps/validations/US_AC references) are not to be deleted. They should be striked off in red. Secondary review: Corrected formatting in design sheet and removed valdiation #V11 |  | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-15July | Yes
D-T-HO-HO3-CA-779 | Manual | 0 | 0 | 2 | 0 | 2 | 2 | Varun | Complete | 2016-09-17 |  |  | Ready for Review |  |  |  |  | PAS10_Designs_Delivered_Wk-07Oct | No | Both AC's in Dev
F-AU-SS-MD-796 | Automation | NA | NA | NA |  | 0 | 1 | NA | Not in Sprint19 scope |  |  |  | Not in Sprint19 scope | [6 empty] | US Cancelled
C-HO-HO3-CO-801 | Automation | 0 | 0 | 1 |  | 1 | 1 | Chandni | Merged with existing | 2016-07-08 |  | Gurpreet | Complete | 2016-07-08 |  | 20m | Design started in week ending 8th July |  | No
C-AU-SS-CL-799 | Automation | 0 | 0 | 2 |  | 2 | 2 | Varun | Merged with existing | 2016-07-05 |  | Gurpreet | Complete | 2016-07-06 |  | 30m | Design started in week ending 8th July
C-AU-SS-CL-800 | Automation | 0 | 0 | 1 |  | 1 | 1 | Varun | Merged with existing | 2016-07-05 |  | Gurpreet | Complete | 2016-07-06 |  | 20m | Design started in week ending 8th July
C-AU-SS-CL-471 | Automation | 0 | 1 | 0 | 0 | 1 | 1 | Harsh | Complete | 2016-07-08 |  | Siddhi | Complete | 2016-10-06 | Scenario description updated Modified release updated Legends in the file are missing in Auto Signature series - 2. Corrected design changes | 20m | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-07Oct | Yes
C-AU-SS-CL-169 | Automation | 0 | 1 | 0 | 0 | 1 | 5 | Varun | Complete | 2016-07-04 |  | Siddhi | Complete | 2016-07-06 | Updated following during review 1. modified release 2. scenario description 3. Removed step#2 at R-R5 4. Added note regarding negative validation |  | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-15July | Yes
F-HO-HO3-OR-702 | Automation | 1 | 0 | 2 | 0 | 2 | 5 | Harsh | Ready for Rereview | 2016-07-13 |  | Siddhi | complete | 2016-07-14 | NA | 5m (For re-review) | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-29July | Yes
F-HO-HO3-ID-670 | Automation | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Ready for Rereview | 2016-07-13 |  | Siddhi | complete | 2016-07-14 | 1. Corrected Scenario description and formatiing of newly added AC | 15m | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-29July | Yes
F-HO-HO6-NV-658 | Automation | 1 | 2 | 0 | 0 | 2 | 4 | Chandni | Ready for Rereview | 2016-07-13 |  | Siddhi | Complete | 2016-07-14 | Counts mismatch | 25m | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-CA-804 | Manual | 0 |  | 1 | 0 | 1 | 1 | Harsh | Complete | 2016-07-06 |  | Gurpreet | Complete | 2016-07-08 |  | 20m | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-CL-805 | Manual | 0 |  | 1 | 0 | 1 | 1 | Harsh | Complete | 2016-07-06 |  | Gurpreet | Complete | 2016-07-08 |  | 20m | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO4-CL-676 | Manual | 0 | 1 | 0 | 0 | 1 | 2 | Chandni | Complete | 2016-07-06 |  | Gurpreet | Complete | 2016-07-08 |  | 20m | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-CL-798 | Automation | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Ready for Rereview | 2016-07-13 |  | Siddhi | Complete | 2016-07-14 | DD4-20 step#8:Corrected role | 15m | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-CL-802 | Automation | 0 | 0 | 7 | 0 | 7 | 7 | Harsh/Chandni | Complete | 7/6/2016 19-Jul-16 | 40m | Gurpreet | Complete | 2016-07-08 |  | 30m | Design started in week ending 8th July | PAS10_Designs_Delivered_Wk-29July | Yes | Pattern reopened after delivery to add 2 AC from HDES generic. Need to communicate again
C-HO-HO3-CL-803 | Automation | 0 | 0 | 1 |  | 1 | 1 | Chandni | Merged with existing | 2016-07-14 |  | Siddhi | Complete | 2016-07-14 | Combined #V1 and #V2 in single Validation | 15m
C-HO-HO6-UT-664 | Manual | 0 | 1 | 1 | 0 | 2 | 3 | Harsh | Complete | 2016-07-13 |  | Siddhi | Complete | 2016-07-15 | Updated Description and modified release | 15m |  | PAS10_Designs_Delivered_Wk-15July | Yes | Pattern reopened after delivery to add 1 AC from HDES generic. Need to communicate again
C-HO-HO3-KY-433 | Automation | 1 | 0 | 3 | 2 | 5 | 5 | Chandni/Varun | Ready for Re-Review | 2016-07-14 |  | Siddhi | complete | 2016-07-17 | 1. Added note for losses to be over 24 months and less than 36 months. 2. Losses should not be Hail/Earthquake/Wind/Freeze/Lightning/Tornado hence removed the step mentioning these loss types. 3. Total no. of Paid CAT/NON CAT should be 5 so retained the old values. | 1h |  | PAS10_Designs_Delivered_Wk-15July | Yes | Delta AC counts modified after delivery
F-HO-HO3-KY-434 | Automation | 0 | 3 | 0 | 2 | 5 | 3 | Chandni | Complete | 2016-07-15 |  | Varun | Complete | 2016-07-17 |  | .5h |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-KY-841 | Automation | 0 | 0 | 1 |  | 1 | 1 | Harsh | Merged with existing | 2016-07-14 |  | Gurpreet | Complete | 2016-07-15 |  | 20m
F-HO-HO4-SD-654 | Automation | 0 | 0 | 2 | 2 | 4 | 2 | Harsh | Complete | 2016-07-14 |  | Gurpreet | Complete | 2016-07-15 |  | 30m |  | PAS10_Designs_Delivered_Wk-29July | Yes
F-HO-HO3-KY-433-OR | Automation | 1 | 2 | 0 | 2 | 4 | 4 | Varun | Complete | 2016-07-15 |  | Gurpreet | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO6-OK-729 | Automation | 0 | 2 | 0 | 0 | 2 | 2 | Harsh | Complete | 2016-07-13 |  | Gurpreet | Complete | 2016-07-15 |  | 20m |  | PAS10_Designs_Delivered_Wk-15July | Yes
C-HO-HO6-OK-227 | Automation | 1 | 2 | 0 | 1 | 3 | 4 | Varun | Complete | 2016-07-14 |  | Gurpreet | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-29July | Yes
T-HO-HO3-CO-675 | Automation | 0 | 1 | 2 | 1 | 4 | 6 | Chandni | Complete | 14-Jul-16 19-Jul-16 | 40m | Siddhi | Complete | 2016-07-14 | Revised entire scenario reviewed merged sceanrio | 45m |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-CL-683 | Manual | 0 | 0 | 0 | 1 | 0 | 0 | Chandni | Complete | 2016-07-13 |  | Siddhi | Complete | 2016-07-14 |  | 15m |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-DP3-CL-174 | Automation | 0 | 4 | 0 | 1 | 5 | 4 | Varun | Complete | 2016-07-13 |  | Siddhi | Complete | 2016-07-14 | Removed condition 8a at DD0 | 1.2 |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO4-CL-180 | Automation | 0 | 1 | 1 | 2 | 4 | 2 | Varun | Complete | 2016-07-13 |  | Siddhi | Complete | 2016-07-14 | NA | 40m |  | PAS10_Designs_Delivered_Wk-29July | Yes | Pattern reopened after delivery to add 2 AC from HDES generic. Need to communicate again
C-HO-HO3-CL-201 | Automation | 0 | 4 | 2 | 1 | 7 | 9 | Varun | Complete | 2016-07-14 |  | Siddhi | Complete | 2016-07-15 | Updated multiple #V points | 35m |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-SD-842 | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh | Complete | 2016-07-14 |  | Gurpreet | Complete | 2016-07-15 |  | 20m |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-CCL-678 | Manual | 0 | 1 | 0 | 0 | 1 | 2 | Harsh | Complete | 2016-07-14 |  | Siddhi | complete | 2016-07-15 | DD0: Correted preconditions R-R5: corrected #V2 | 20m |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-CL-667 | Automation | 0 | 1 | 0 | 0 | 1 | 2 | Harsh | Complete | 2016-07-14 | 40m | Siddhi | Complete | 2016-07-15 | Corrected preconditions at DD0 | 20m |  | PAS10_Designs_Delivered_Wk-29July | Yes
F-HO-HO6-KY-425 | Automation | 1 | 0 | 0 | 0 | 0 | 3 | Varun | Complete | 2016-07-15 |  | Siddhi | complete | 2016-07-15 | Removed highlights from #V3 | 10m |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-HO-HO3-IN-806 | Automation | 0 | 0 | 3 | 0 | 3 | 3 | Chandni | Complete | 2016-07-13 |  | Siddhi | complete | 2016-07-15 | Removed property age step from R-R5, as this field s not editable at renewal. | 25m |  | PAS10_Designs_Delivered_Wk-29July | Yes
F-HO-HO3-SD-656 | Automation | 1 | 0 | 0 | 0 | 0 | 4 | Varun | Complete | 2016-07-15 |  | Gurpreet | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-29July | Yes
D-T-AU-SS-CL-807 | Automation, Content Validation | 0 | 0 | 4 | 0 | 4 | 4 | Varun | [9 empty] | Pending for design
C-HO-DP3-OK-149 | Automation | 0 | 0 | 0 | 1 | 1 | 4 | Varun | Complete | 2016-07-15 |  | Gurpreet | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-29July | Yes
D-T-HO-HO3-CA-808 | Automation, Content Validation | 0 | 0 | 2 | 0 | 2 | 2 | Chandni | Complete | 2016-08-04 |  | Gurpreet/Siddhi | complete | 2016-08-02 | RE-review complete (Siddhi) | 20m |  | PAS10_Designs_Delivered_Wk-29July | Yes
T-HO-HO3-CL-682 | Automation | 0 | 0 | 1 | 0 | 1 | 2 | Varun | Complete | 2016-07-18 | 25m | Siddhi | complete | 2016-07-19 |  | 15m | PAS10_Designs_Delivered_Wk-15July | PAS10_Designs_Delivered_Wk-15July | Yes
C-AU-SS-CL-472 | Automation | 0 | 0 | 3 | 0 | 3 | 4 | Varun | Complete | 2016-07-19 | 45m | Gurpreet | complete | 2016-07-19 |  | 15m | PAS10_Designs_Delivered_Wk-15July | PAS10_Designs_Delivered_Wk-15July | Yes
C-HO-HO3-CT-417 | Automation | 0 | 0 | 1 | 0 | 1 | 3 | Chandni | Complete | 2016-07-18 | 50m | Siddhi | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-29July | Yes
C-PU-PUP-CA-843-CNV | Automation | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete |  |  | Siddhi | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-16thSep | Yes
T-HO-DP3-CA-844-CNV | Automation | 0 | 0 | 2 | 0 | 2 | 2 | Harsh | Complete |  |  | Siddhi | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-26August | Yes
T-HO-DP3-CA-847-CNV | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh | Complete |  |  | Siddhi | complete |  |  |  | PAS10_Designs_Delivered_Wk-26August | PAS10_Designs_Delivered_Wk-26August | Yes
D-T-HO-DP3-CA-864-CNV | Automation | 0 | 0 | 2 | 0 | 2 | 2 | Harsh | Complete |  |  | Siddhi | complete |  |  |  | Yes | PAS10_Designs_Delivered_Wk-26August | Yes
D-T-HO-DP3-CA-866-CNV | Automation | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete |  |  | Siddhi | complete |  |  |  | PAS10_Designs_Delivered_Wk-26August | PAS10_Designs_Delivered_Wk-26August | Yes
C-PU-PUP-CA-863-CNV | Manual | 0 | 0 | 7 | 0 | 7 | 7 | Harsh | Ready for Review | 2016-10-03 |  | Siddhi | Re-Review | 2016-10-04 | 1. Description: Scenario has 7 AC's, however description is updated only for 6 AC's 2. R-48: At step#1.1, policy is not yet propose because of premium rule failure. Hence will not be appropriate to validate suppression of 615121 here. Instead, we can validate it once policy is proposed successfully at Step#15 3. PLease highlight the changes over already delivered design in Green 4. In JIRA, open 'Enhance Design' flow and make necessary updates | 20m |  | PAS10_Designs_Delivered_Wk-26August | Yes
C-HO-DP3-CA-865-CNV | Manual | 0 | 0 | 5 | 0 | 5 | 5 | Harsh | Complete |  |  | Gurpreet | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-26August | Yes
C-HO-DP3-CA-848-CNV | Manual | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete |  |  | Siddhi | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-16thSep | Yes
C-HO-DP3-CA-867-CNV | Manual | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete |  |  | Siddhi | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-26August | Yes
C-HO-HO3-CA-200 | Automation | 1 | 0 | 0 | 0 | 0 | 2 | Harsh | Complete | 2016-08-31 |  | Gurpreet | [5 empty] | PAS10_Designs_Delivered_Wk-9thSep | Yes
T-HO-HO3-CCL-677 | Automation | 0 | 1 | 1 | 0 | 2 | 5 | Harsh | Complete |  |  | Varun | Complete | 2016-09-07 |  |  |  | PAS10_Designs_Delivered_Wk-9thSep | Yes
T-HO-HO3-CL-680 | Automation | 0 | 0 | 0 | 1 | 1 | 1 | Harsh | Complete | 2016-08-31 |  | Gurpreet | [5 empty] | PAS10_Designs_Delivered_Wk-9thSep | Yes
C-HO-HO6-CA-134 | Automation | 0 | 0 | 0 | 0 | 0 | 6 | Harsh | Complete |  |  | Siddhi | complete |  |  |  | PAS10_Designs_Delivered_Wk-16thSep | PAS10_Designs_Delivered_Wk-16thSep | Yes
C-HO-HO3-CA-405 | Automation | 0 | 0 | 4 | 0 | 4 | 6 | Harsh | Complete |  |  | Varun | Complete | 2016-09-08 | 1. As per 25869_CA1 condition is "- If the value of all the detached structures(HO 40/HO 48) plus Cov B exceed 100% of Cov A" but in the design it is mentioned as Limit of Liability > Cov A which is incorrect. Please update the same. 2. V1 should correspond to Step 5 as error occurs on 'Purchase' and not on Rate. 3. Add steps for Click of 'Refer for Approval' on the error message for task generation during Bing for both the error messages at DD0 and R-R1 4. Update the note on R-R1 (Note : Ensure sum of limit of liability of all detached structures and coverage B of main dwelling does not exceed Coverage A of the Main dwelling else error <WM-9699> will be thrown) | 1h |  | PAS10_Designs_Delivered_Wk-9thSep | Yes
C-HO-HO4-CA-098 | Automation | 2 | 0 | 0 | 0 | 0 | 4 | Harsh | Complete | 2016-08-31 |  | Gurpreet | [5 empty] | PAS10_Designs_Delivered_Wk-9thSep | Yes
C-HO-HO3-CA-114 | Automation | 0 | 0 | 0 | 1 | 1 | 1 | Harsh | US analysis pending review | 2016-09-01 |  | Gurpreet | [5 empty] | PAS10_Designs_Delivered_Wk-9thSep | Yes
T-HO-HO3-CA-199 | Automation | 0 | 0 | 2 | 0 | 2 | 3 | Harsh | Complete | 2016-09-01 |  | Gurpreet | [5 empty] | PAS10_Designs_Delivered_Wk-9thSep | Yes
C-HO-HO4-CA-799-CNV | Manual | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete |  |  | Siddhi | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-16thSep | Yes
C-HO-HO3-CA-810-CNV | Automation | 0 | 0 | 4 | 0 | 3 | 3 | Harsh | Re-Open for Redesign |  |  | Varun | Re-Review |  |  |  |  | PAS10_Designs_Delivered_Wk-9thSep | Yes | Re-opened on 5th Oct to add inflation guard US.
C-HO-HO6-CA-861-CNV | Manual | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete |  |  | Siddhi | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-16thSep | Yes
C-HO-HO3-CA-813-CNV | Automation | 0 | 0 | 2 | 0 | 2 | 2 | Harsh | Complete |  |  | Siddhi | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-16thSep | Yes
D-T-HO-HO3-CA-814-CNV | Manual | 0 | 0 | 2 | 0 | 2 | 2 | Harsh | Complete |  |  | Siddhi | complete |  |  |  |  | PAS10_Designs_Delivered_Wk-16thSep | Yes
C-HO-HO3-CA-817-CNV | Automation | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete | 2016-09-02 |  | Varun | Complete | 2016-09-08 |  |  |  | PAS10_Designs_Delivered_Wk-9thSep | Yes
D-T-PU-PUP-CA-862-CNV | Automation | 0 | 0 | 4 | 0 | 4 | 4 | Harsh | Ready for Review | 2016-10-03 |  | Gurpreet/Siddhi (Re-review) | Re-Review | 2016-10-04 | 1. Please highlight the changes over already delivered design in Green 2. 4. In JIRA, open 'Enhance Design' flow and make necessary updates | 15m |  | PAS10_Designs_Delivered_Wk-9thSep | Yes
C-AU-SS-HC-MD-001 | Automation | 0 | 0 | 2 | 0 | 2 | 2 | Harsh | Complete | 2016-09-15 |  | Varun | complete |  | Validation "field 'Expiring Policy Premium' is displayed with the Legacy premium", need to check automation feasibility of this step as part of ADT. Validation at 2R-35 is missing |  |  | PAS10_Designs_Delivered_Wk-07Oct | No | Both Ac's Blocked
C-AU-SS-HC-VA-002 | Automation | 0 | 0 | 2 | 0 | 2 | 2 | Harsh | Complete | 2016-09-15 |  | Varun | complete |  | AC numbering missing. |  |  | PAS10_Designs_Delivered_Wk-07Oct | No | Both Ac's Blocked
C-AU-SS-HC-CL-002 | Automation | 0 | 0 | 2 | 0 | 2 | 2 | Harsh | Complete | 2016-09-15 |  | Varun | Design Complete |  |  |  |  | PAS10_Designs_Delivered_Wk-07Oct | Yes
C-AU-SS-HC-CL-003 | Automation | 0 | 1 | 0 | 0 | 1 | 1 | Harsh | Complete | 2016-10-05 | [7 empty] | PAS10_Designs_Delivered_Wk-07Oct | Yes
C-AU-SS-CL-849 | Manual | 0 | 0 | 1 | 0 | 1 | 1 | Harsh | Complete | [8 empty] | PAS10_Designs_Delivered_Wk-07Oct | Yes
C-HO-HO6-CA-812-CNV | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh | Complete | [8 empty] | PAS10_Designs_Delivered_Wk-07Oct | Yes
C-HO-HO4-CA-811-CNV | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh | Complete | [8 empty] | PAS10_Designs_Delivered_Wk-07Oct | Yes
C-HO-DP3-CA-816-CNV | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh | Complete | [8 empty] | PAS10_Designs_Delivered_Wk-07Oct | No
C-AU-SS-BKCAP-CL-001 | Automation | 0 | 0 | 6 | 0 | 6 | 6 | Harsh | Complete
C-AU-SS-BKCAP-CL-003 | Automation | 0 | 0 | 4 | 0 | 4 | 4 | Harsh | Complete
C-AU-SS-BKCAP-CL-005 | Automation | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete
C-AU-SS-BKCAP-CL-006 | Automation | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete
C-AU-SS-BKCAP-CL-008 | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh | Complete
C-AU-SS-BKCAP-CL-009 | Automation | 0 | 0 | 3 | 0 | 3 | 3 | Harsh | Complete
C-AU-SS-BKCAP-CL-010 | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh | Complete
C-HO-DP3-CA-803-CNV | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh
C-PU-PUP-CA-809-CNV | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh
C-HO-HO3-CA-846-CNV | Automation | 0 | 0 | 1 | 0 | 1 | 1 | Harsh | Complete | [8 empty] | PAS10_Designs_Delivered_Wk-07Oct | No
Note on F1: Chavan, Siddhi: Added newly to count AC removal efforts
Note on A36: Chavan, Siddhi: Only AC in the scenario removed, sceanrio no longer valid