## Summary (hidden)
Release | Start Date | PAS Milestone | End Date | PAS Milestone | No. of Resources | Effective No. of Billing Resources (removing PTOs) | No. of weeks | # WI | # AC
PAS8 | 2016-01-22 | PAS7- Mil3 wk3 | 2016-03-11 | PAS 8- Mil2 wk1 | 10 | 9 | 8 | 523 | 300
PAS9 | 2016-03-18 | PAS8- Mil2 wk2 | 2016-05-13 | PAS 9- Mil1 wk1 | 7 | 5.5 | 9 | 421 | 306
PAS10 | 2016-05-20 | PAS9- Mil1 wk2 | 2016-08-05 | PAS10- Mil1 wk1 | 4 | 2.5 | 12 | 230 | 208
Steady State Capacity as per last estimations |  |  |  | 5 FTE for 12 wks

## PAS10_Sp19 & BP Comparison
WI# | Description | Story Points (as per Business Priority deck) | Estimated US count | Estimated AC Count (derived from US) | Story Points (as per Sp-19) | Estimated US count | Estimated AC Count (derived from US) | Increase (SP) | Increase (US) | Increase (AC)
WI0304 | Auto - Auto CA/SS Report Redesign - Release 1 | 150 | 75 | 75 |  |  |  | -150 | -75 | -75
WI0320 | CA Structural Rate Changes (Fireline) | 35 | 17.5 | 13 | 29 | 11 | 8 | -6 | -6.5 | -5
WI0322 | MPD Validation | 15 | 7.5 | 8 |  |  |  | -15 | -7.5 | -8
WI0330 | Thirdparty coverpage for non-pay cancel notice CA Property | 5 | 3.3333 | 3 | 7 | 2 | 2 | 2 | -1.3333 | -1
WI0333 | UBI Enhancements | 66 | 33 | 40 | 30.5 | 17 | 20 | -35.5 | -16 | -20
WI0341 | BSS - PUP Simplification and PUP UW Simplification | 15 | 7.5 | 8 |  |  |  | -15 | -7.5 | -8
WI0342 | UW Simplification Phase-1 | 111 | 55.5 | 56 | 76.25 | 45 | 45 | -34.75 | -10.5 | -11
WI0344 | Left over - Auto and Property CRs | 93 | 46.5 | 35 | 49 | 21 | 16 | -44 | -25.5 | -19
WI0211 | Integration stories PAS10 | [6 empty] | 0 | 0 | 0
WI0340 | BSS - Enabling book roil in new business and capping | 30 | 15 | 11 | 36.5 | 16 | 12 | 6.5 | 1 | 1
WI0162 | CA HDES Conversion, Phase 2 (Org Scope) | 200 | 100 | 75 | 160.5 | 53 | 40 | -39.5 | -47 | -35
WI0208 | CA Property Conversions SIS (DP3) | 15 | 7.5 | 6 | 77.5 | 47 | 35 | 62.5 | 39.5 | 29
WI0329 | Grandfathering rules for MAIG states | 30 | 15 | 11 |  |  |  | -30 | -15 | -11
Sub totals | [7 empty] | 0 | 0 | 0
WI0316 | Property PAS Simplification Phase-2 | 27 | 9 |  | 22 | 9 |  | -5 | 0 | 0
Total |  | 792 | 392.3333 | 341 | 488.25 | 221 | 178 | -303.75 | -171.3333 | -163

## PAS10_Sprint19 PreliminaryScope
Track | Sprint | WI# | Description | Story Points (as per Business Priority deck) | Estimated US count | Estimated AC Count (derived from US) | Automation AC count- New | Manual only AC count | Integration AC count | Automation AC count - Reusable | Document automation AC Count | Assumptions | Complex US | Medium US | Simple US |  | Avg Scenarios | Complex (new) | Medium (new) | Simple (new) | Complex (update) | Medium (update) | Simple (update)
[6 empty] | A+B+C+D | A | B | C | D
| Sprint-19 & 20 | WI0320 | CA Structural Rate Changes (Fireline) | 29 | 11 | 8 | 7 |  | 1 |  | 1 | Assuming 90% will be in new automation, 10% will be integration. 10% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 4.4 | 3.85 | 2.75 | 7 | 2 | 1 | 2 | 1 |  |  |  | 4 | #N/A
|  | WI0330 | Thirdparty coverpage for non-pay cancel notice CA Property | 7 | 2 | 2 | 2 |  |  |  | 0 | Assuming 100% will be new automation. 20% will be in document content validation (this is already included in new automation). There will be no reusable automtable AC. 2SP = 1US | 0.2 | 0.8 | 1 | 2 | 1 | 1 | 1 |  |  |  |  | 2 | #N/A
|  | WI0333 | UBI Enhancements | 30.5 | 17 | 20 | 14 |  | 2 | 4 | 2 | Assuming 70% will be new automation, 20% will be reusable automation and 10% will be integration. 10% will be document automation AC (this is already included in new automation). 2SP = 1US | 5.95 | 5.95 | 5.1 | 18 | 6 | 2 | 3 | 2 | 2 | 2 | 1 | 12 | #N/A
|  | WI0342 | UW Simplification Phase-1 | 76.25 | 45 | 45 | 32 | 5 |  | 9 |  | Assuming 70% will be new automation, 10% will be manual, 20% will be resuable automation. There will be no integration AC and no document content validation AC in regression. 2SP = 1US | 15.75 | 18 | 11.25 | 46 | 15 | 5 | 5 | 2 | 4 | 3 | 3 | 22 | #N/A
|  | WI0344 | Left over - Auto and Property CRs | 49 | 21 | 16 | 10 | 2 | 2 | 3 | 3 | Assuming 60% will be new automation, 10% will be manual, 10% will be integration, 20% will be partially automatable AC. 20% document automation AC r(this is already included in new automation) 2SP = 1US | 6.3 | 8.4 | 6.3 | 15 | 5 | 2 | 4 | 2 | 1 | 1 | 1 | 11 | #N/A
Conv |  | WI0340 | Enable Book roll in New Business and Capping | 36.5 | 16 | 12 | 10 | 1 | 1 | 0 | 2 | Assuming 80% will be new automation, 10% will be integration and 10% will be manual. 20% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 6.4 | 5.6 | 4 | 11 | 4 | 2 | 2 | 1 |  |  |  | 5 | #N/A
Conv |  | WI0162 | CA HDES Conversion, Phase 2 (Org Scope) | 160.5 | 59 | 44 | 35 | 4 | 4 | 0 | 9 | Assuming 80% will be new automation, 10% will be integration and 10% will be manual. 20% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 23.6 | 20.65 | 14.75 | 39 | 13 | 5 | 5 | 3 |  |  |  | 13 | 1
Conv |  | WI0208 | CA Prop Conversion SIS-DP3 and Foxpro-PUP | 77.5 | 44 | 33 | 26 | 3 | 3 | 0 | 7 | Assuming 80% will be new automation, 10% will be integration and 10% will be manual. 20% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 17.6 | 15.4 | 11 | 29 | 10 | 4 | 4 | 2 |  |  |  | 10 | 1
| Business Priority Deck (WI not added to Sp-19) | WI0322 | MPD Validation | 15 | 7.5 | 8 | 7 |  |  | 1 |  | Assuming 90% will be in new automation, 10% will be reusable automation AC. There will not be any document content validation AC in regression. 2SP = 1US | 1.5 | 3 | 3 | 8 | 3 |  | 1 |  |  | 2 | 1 | 4 | #N/A
|  | WI0341 | BSS - PUP Simplification and PUP UW Simplification | 15 | 7.5 | 8 | 6 | 1 |  | 1 |  | Assuming 80% will be new automation, 10% reusable automation, 10% will be pure manual. There will be no integration AC and no document content validation AC in regression. 2SP = 1US | 2.25 | 2.625 | 2.625 | 8 | 3 | 1 | 1 | 1 |  | 1 |  | 4 | #N/A
|  | WI0304 | MVR Redesign - Phase 1 | 150 | 90 | 90 | 63 | 9 | 9 | 9 |  | Assuming 70% will be in new automation, 10% will be integration, 10% will be manual and 10% will be partially resuable AC. There will not be any document content validation AC in regression. 2SP = 1US | 36 | 31.5 | 22.5 | 81 | 27 | 8 | 9 | 7 | 1 | 1 | 1 | 27 | 1
|  | WI0329 | Grandfathering rules for MAIG states | 30 | 29 | 22 | 18 | 2 | 2 | 0 | 4 |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 1
Conv | Business Priority Deck (WI added to Sp-19 but difference in Story Points) | WI0162 | CA HDES Conversion, Phase 2 (Org Scope) | 39.5 | 59 | 44 | 35 | 4 | 4 | 0 | 9 | Assuming 80% will be new automation, 10% will be integration and 10% will be manual. 20% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 11.6 | 10.15 | 7.25 | 20 | 7 | 3 | 3 | 1 |  |  |  | 7 | 1
|  | WI0320 | CA Structural Rate Changes (Fireline) | 6 | 2.2727 | 2 | 2 |  | 0 |  | 0 | Assuming 90% will be in new automation, 10% will be integration. 10% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US |  | 20.65
|  | WI0333 | UBI Enhancements | 35.5 | 19.8324 | 24 | 17 |  | 2 | 5 | 2 | Assuming 70% will be new automation, 20% will be reusable automation and 10% will be integration. 10% will be document automation AC (this is already included in new automation). 2SP = 1US
|  | WI0344 | Left over - Auto and Property CRs | 44 | 18.8841 | 14 | 8 | 1 | 1 | 3 | 3 | Assuming 60% will be new automation, 10% will be manual, 10% will be integration, 20% will be partially automatable AC. 20% document automation AC r(this is already included in new automation) 2SP = 1US
INT
| Total |  |  | 801.25 | 349 | 308 | 230 | 27 | 24 | 27 | 28 |  | 131.55 | 146.575 | 91.525 | 284 | 96 | 34 | 40 | 22 | 8 | 10 | 7
[6 empty] | 0.88252 | [6 empty] | 37.6934 | 41.9986 | 26.2249 | 275.7591 |  | 35.42% | 41.67% | 22.92% | 8.333% | 10.42% | 7.292%
| Sub totals | WI0316 | Property PAS Simplification Phase-2 | 22 | 9
|  | WI0371 | PAS9 refactor to E-Folder is impacting the folder structure |  | 603
|  | WI0211 | Integration stories PAS10
|  |  | For 800 story points - 22 UI Simplification | 778 | 338.873 | 299.0627 | 223.3261 | 26.2165 | 23.3036 | 26.2165 | 27.1875 | [7 empty] | % | S.Count | AC Count | Avg AC
[17 empty] | New | Complex | 35.4167 | 34 | 100.5833 | 2.9583
[5 empty] | 2.2958 | [12 empty] | Medium | 41.6667 | 40 | 118.3333 | 2.9583
[5 empty] | 0.43557 | 0.81375 | [11 empty] | Simple | 22.9167 | 22 | 65.0833 | 2.9583
[17 empty] | Update | Complex | 8.3333 | 8 | 23.6667 | 2.9583
[9 empty] | AC | Scenarios | [7 empty] | Medium | 10.4167 | 10 | 29.5833 | 2.9583
|  |  | Design Scope | Automation | 257 | 284 | Update | 12.6761 | 27 | 9 | [7 empty] | Simple | 7.2917 | 7 | 20.7083 | 2.9583
|  |  |  | Manual | 27 |  | New | 90.493 | 257 | 85.6667 | [8 empty] | 126.0417 |  | 357.9583

## PAS10_Business Priority
Track | WI# | Description | Story Points (as per Business Priority deck) | Estimated US count (Base) | Estimated AC Count (Base) | Story Points (As per the latest scope of SP19 and SP20) | US Count (As per the latest scope of SP19 and SP20) | Estimated AC Count (derived from US) | Automation AC count- New | Manual only AC count | Integration AC count | Automation AC count - Reusable | Document automation AC Count | Assumptions | Complex US | Medium US | Simple US |  | Avg Scenarios | Complex (new) | Medium (new) | Simple (new) | Complex (update) | Medium (update) | Simple (update)
[8 empty] | A+B+C+D | A | B | C | D
| WI0304 | MVR Redesign - Phase 1 | 150 | 75 | 75 | 184 | 90 | 90 | 63 | 9 | 9 | 9 |  | Assuming 70% will be in new automation, 10% will be integration, 10% will be manual and 10% will be partially resuable AC. There will not be any document content validation AC in regression. 2SP = 1US | 36 | 31.5 | 22.5 | 81 | 27 | 8 | 9 | 7 | 1 | 1 | 1 | 27 | 1
| WI0320 | CA Structural Rate Changes (Fireline) | 35 | 17.5 | 13 | 27 | 11 | 8 | 7 |  | 1 |  | 1 | Assuming 90% will be in new automation, 10% will be integration. 10% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 4.4 | 3.85 | 2.75 | 7 | 2 | 1 | 2 | 1 |  |  |  | 4 | #N/A
| WI0322 | MPD Validation | 15 | 7.5 | 8 | 0 | 0 | 0 | 0 |  |  | 0 |  | Assuming 90% will be in new automation, 10% will be reusable automation AC. There will not be any document content validation AC in regression. 2SP = 1US | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  | 2 | 1 | 4 | #N/A
| WI0330 | Thirdparty coverpage for non-pay cancel notice CA Property | 5 | 3.3333 | 3 | 5 | 2 | 2 | 2 |  |  |  | 0 | Assuming 100% will be new automation. 20% will be in document content validation (this is already included in new automation). There will be no reusable automtable AC. 2SP = 1US | 0.2 | 0.8 | 1 | 2 | 1 | 1 | 1 |  |  |  |  | 2 | #N/A
| WI0333 | UBI Enhancements | 66 | 33 | 40 | 30 | 17 | 20 | 14 |  | 2 | 4 | 2 | Assuming 70% will be new automation, 20% will be reusable automation and 10% will be integration. 10% will be document automation AC (this is already included in new automation). 2SP = 1US | 5.95 | 5.95 | 5.1 | 18 | 6 | 2 | 3 | 2 | 2 | 2 | 1 | 12 | #N/A
| WI0341 | BSS - PUP Simplification and PUP UW Simplification | 15 | 7.5 | 8 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Assuming 80% will be new automation, 10% reusable automation, 10% will be pure manual. There will be no integration AC and no document content validation AC in regression. 2SP = 1US | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  | 1 |  | 4 | #N/A
| WI0342 | UW Simplification Phase-1 | 111 | 55.5 | 56 | 67 | 45 | 59 | 41 | 6 |  | 12 |  | Assuming 70% will be new automation, 10% will be manual, 20% will be resuable automation. There will be no integration AC and no document content validation AC in regression. 2SP = 1US | 15.75 | 18 | 11.25 | 59 | 20 | 5 | 5 | 2 | 4 | 3 | 3 | 22 | #N/A
| WI0344 | Left over - Auto and Property CRs | 93 | 46.5 | 35 | 46 | 21 | 16 | 10 | 2 | 2 | 3 | 3 | Assuming 60% will be new automation, 10% will be manual, 10% will be integration, 20% will be partially automatable AC. 20% document automation AC r(this is already included in new automation) 2SP = 1US | 6.3 | 8.4 | 6.3 | 15 | 5 | 2 | 4 | 2 | 1 | 1 | 1 | 11 | #N/A
INT | WI0211 | Integration stories PAS10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 1
Conv | WI0340 | BSS - Enabling book roll in new business and capping | 30 | 15 | 11 | 36 | 16 | 12 | 10 | 1 | 1 | 0 | 2 | Assuming 80% will be new automation, 10% will be integration and 10% will be manual. 20% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 6.4 | 5.6 | 4 | 11 | 4 | 2 | 2 | 1 |  |  |  | 5 | #N/A
Conv | WI0162 | CA HDES Conversion, Phase 2 (Org Scope) | 200 | 100 | 75 | 158 | 59 | 53 | 42 | 5 | 5 | 0 | 11 | Assuming 80% will be new automation, 10% will be integration and 10% will be manual. 20% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 23.6 | 20.65 | 14.75 | 47 | 16 | 6 | 6 | 3 |  |  |  | 15 | #N/A
Conv | WI0208 | BSS - CA Property Conversions SIS (DP3) | 15 | 7.5 | 6 | 84.5 | 44 | 33 | 26 | 3 | 3 | 0 | 7 | Assuming 80% will be new automation, 10% will be integration and 10% will be manual. 20% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 17.6 | 15.4 | 11 | 29 | 10 | 4 | 4 | 2 |  |  |  | 10 | 1
Conv | WI0329 | Grandfathering rules for MAIG states | 30 | 15 | 11 | 59.5 | 29 | 22 | 18 | 2 | 2 | 0 | 4 | Assuming 80% will be new automation, 10% will be integration and 10% will be manual. 20% will be document automation AC (this is already included in new automation). There will not be any reusable Automation AC. 2SP = 1US | 11.6 | 10.15 | 7.25 | 20 | 7 | 3 | 3 | 1 |  |  |  | 7 | 1
| Sub totals | [13 empty] | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 1
| WI0316 | Property PAS Simplification Phase-2 | 27 |  |  | 18 | 9 | [7 empty] | 3.6 | 3.15 | 2.25 | 0 | 0 | [6 empty] | 0 | 1
| Total |  | 792 | 383.3333 | 341 | 715 | 343 | 315 | 233 | 28 | 25 | 28 | 30 |  | 131.4 | 123.45 | 88.15 | 289 | 98 | 35 | 41 | 22 | 8 | 10 | 7
[12 empty] | 2.0845 |  |  | 38.309 | 35.9913 | 25.6997 | #REF! |  | 35.71% | 41.84% | 22.45% | 8.163% | 10.2% | 7.143%
[12 empty] | 0.47972 | 0.84257
| WI0371 | PAS9 refactor to E-Folder is impacting the folder structure |  |  |  | 2 | 603
[21 empty] | % | S.Count | AC Count | Avg AC
[19 empty] | New | Complex | 35.7143 | 35 | 103.2143 | 2.949 | [8 empty] | AC | Scenarios
[20 empty] | Medium | 41.8367 | 41 | 120.9082 | 2.949 |  |  |  | Automation | 261 | 289 | Update | 12.4567 | 28 | 9.3333
[20 empty] | Simple | 22.449 | 22 | 64.8776 | 2.949 |  |  |  | Manual | 28 |  | New | 90.3114 | 261 | 87
[19 empty] | Update | Complex | 8.1633 | 8 | 23.5918 | 2.949 |  |  |  |  | 2.0845
[20 empty] | Medium | 10.2041 | 10 | 29.4898 | 2.949
[20 empty] | Simple | 7.1429 | 7 | 20.6429 | 2.949
[21 empty] | 125.5102 |  | 362.7245
Manual
Integration

## Scope Sheets (hidden)
| Release | WI# | Executive Priorities | US Count | [5 empty] | Story Points | AC Count | Manual Ac count (incl. Content Validation and document automation) | Automation Ac count- New | Automation Ac count - Reusable | Integration AC count | Assumptions
| PAS8 | WI0047 | CT Property | 99 | [5 empty] | 216.5 | 74 | 15 | 52 | 7 | 7 | Assuming 80% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation)
| PAS8 | WI0033 | OH Property | 38 | [5 empty] | 99.5 | 29 | 6 | 20 | 3 | 3 | Assuming 80% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation)
| PAS8 | WI0283 | SS Automated Renewal Rules | 65 | [5 empty] | 69 | 14 | 3 | 10 | 1 | 1 | Assuming 70% will be out of regression and remaining 18 US are in regression scope 1SP = 1US
| PAS8 | WI0035 | KS Property | 26 | [5 empty] | 73 | 20 | 4 | 14 | 2 | 2 | Assuming 80% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation)
| PAS8 | WI0308 | Document Trigger Changes for Choice - Prod Enh | 42 | [5 empty] | 136 | 32 | 6 | 22 | 3 | 3 | Assuming 80% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation)
| PAS8 | WI0235 | Overall Prod Enhancements and Defect Debt PAS8 | 27 | [5 empty] | 59 | 20 | 4 | 14 | 2 | 2 | Assuming 80% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation)
| PAS8 | WI0300 | Usability Improvements - SS Bundle Simplifications - Prod Enh | 26 | [5 empty] | 18 | 20 | 4 | 14 | 2 | 2 | Assuming 80% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation)
| PAS8 | WI0205 | Document Redesign | 163 | [5 empty] | 396.5 | 98 | 20 | 69 | 10 | 10 | Assuming 60% will be new automation, 20% will be reusable automation. 20% will also be partially automatable (this is already included in new automation)
| PAS8 | WI0036 | KY Property | 30 | [5 empty] | 79.75 | 23 | 5 | 16 | 2 | 2 | Assuming 80% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation)
| PAS8 | ------ | PAS8 Vital Late-Breaking | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Assuming 80% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation)
| PAS8 | WI0174 | Integrations Stories PAS8 | 7 | [5 empty] | 0 | 5 | 1 | 4 | 1 | 1
| PAS8 | WI0275 | *Manual CNV + Auto Capping DE, VA, MD | 56 | [5 empty] | 158 |  | 0 | 0 | 0 | 0 | Not included in Factory scope as this WI covered in CR
| Totals (excluding Conversion items) |  |  | 523 | [5 empty] | 1305.25 | 335 | 68 | 235 | 33 | 33
| Release | WI# | Executive Priorities | Story Points (as per Groom Sheet from Jerry) | US Count (Per PAS9 Grooming Sheet from Jerry) | AC Count (as per Grooming Sheet from Jerry) | Story Points (as per latest sheet from Jen) | Approx US count (3SP = 1US for new state and 2SP = 1 US for others) | AC Count (derived from US) | Manual Ac count (incl. Content Validation and document automation) | Automation Ac count- New | Automation Ac count - Reusable | Integration AC count | Assumptions
| PAS9 | WI0036 | KY Property | 129 | 43 | 32 | 129 | 43 | 32 | 6 | 22 | 6 | 3 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS9 | WI0039 | WV Property | 147 | 51 | 38 | 147 | 49 | 37 | 7 | 26 | 7 | 4 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS9 | WI0038 | SD Property | 84 | 28 | 21 | 75 | 25 | 19 | 4 | 13 | 4 | 2 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS9 | WI0040 | NV Property | 114 | 38 | 29 | 102 | 34 | 26 | 5 | 18 | 5 | 3 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS9 | WI0309 | Manual changes to renewal image | 213 | 99 | 74 | 202 | 101 | 131 | 0 | 118 | 0 | 13 | 1. 65% of user stories will fall under regression 2. As the user stories are majorly rules related, 2 AC per user story in regression will be in scope. 3. As there are no form generation user stories, no scenario will be marked for manual content validation thread. 4. The estimates have been done based on quick analysis of 86 item under this work items
| Non UI Subtotal | [5 empty] | 655 | 252 | 245
| PAS9 | WI0315 | Product Simplification Phase 1 | 198 | 96 | 72 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | To be covered as part of separate estimates by RCA team
| PAS9 | WI0044 | WY Property | 57 | 19 | 14 | 28 | 9.3333 | 7 | 1 | 5 | 1 | 1 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS9 | WI0041 | MT Property | 177 | 59 | 44 | 157 | 52.3333 | 39 | 8 | 27 | 8 | 4 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS9 | WI0325 | ID Property Comp rater | 36 | 12 | 9 | 19 | 6.3333 | 5 | 1 | 4 | 1 | 1 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS9 | WI0326 | OR comprater | 54 | 18 | 14 | 45 | 15 | 11 | 2 | 8 | 2 | 1 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS9 | WI0046 | NY Property | 267 | 89 | 67 | 283 | 94.3333 | 71 | 14 | 50 | 14 | 7 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS9 |  | Vital Late-Breaking CRs | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total of Additional Scope Added To PAS9 | [5 empty] | 532 | 177.3333 | 133
| Totals |  |  | 1476 | 552 | 414 | 1350 | 429.3333 | 378 | 48 | 291 | 48 | 39
[5 empty] | 456 |  |  |  | 339 |  | 325 | 57
39.9
364.9
Pri |  | WI# | Description | Story Points (as per Groom Sheet from Jerry) | US Count (Per PAS9 Grooming Sheet from Jerry) | AC Count (as per Grooming Sheet from Jerry) | Story Points (as per latest sheet from Jen) | Approx US count (3SP = 1US for new state and 2SP = 1 US for others) | AC Count (derived from US) | Manual Ac count (incl. Content Validation and document automation) | Automation Ac count- New | Automation Ac count - Reusable | Integration AC count | Assumptions
| PAS10 | WI0041 | MT Property |  |  |  | 20 | 6.6667 | 5 | 1 | 4 | 1 | 1 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS10 | WI0044 | WY Property |  |  |  | 20 | 6.6667 | 5 | 1 | 4 | 1 | 1 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS10 | WI0042 | ID Property (Orig Scope) |  |  |  | 24 | 8 | 6 | 1 | 4 | 1 | 1 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS10 | WI0043 | OR Property (Orig Scope) |  |  |  | 17 | 5.6667 | 4 | 1 | 3 | 1 | 0 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS10 | WI0049 | DC Property (Orig Scope) |  |  |  | 108 | 36 | 27 | 5 | 19 | 5 | 3 | Assuming 70% will be new automation, 20% will be reusable automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 3SP = 1US
| PAS10 | WI0320 | CA Property Rate Change (Prod Enh) |  |  |  | 130 | 65 | 49 | 5 | 44 |  | 5 | Assuming 10% will be pure manual and 90% will be new automation. There will be no partially automtable AC and 10% will be integration 2SP = 1US
| PAS10 | WI0318 | Technical Design: Manual Change to Renewal Image (Orig Scope) |  |  |  | 85 | 10 | 30 | 6 | 21 | 3 | 3 | Per note from Jen, only 10 US will be in scope. Assuming 3 AC per US
| Sub Total | [5 empty] | 404 | 138 | 126
| PAS10 | WI0162 | CA HDES Conversion |  |  |  | 200 | 100 | 75 | 15 | 68 | 0 | 8 | Assuming 90% will be new automation, 10% will be integration. 20% will also be partially automatable (this is already included in new automation). 2SP = 1US
| PAS10 | WI0235 | PAS10 Minor Production Enhancements (ProdEnh) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PAS10 | WI0235 | PAS10 Vital Late-Breaking Production Enhancements (Prod Enh) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | [5 empty] | 604 | 238 | 201 | 35 | 167 | 12 | 22
[8 empty] | 175 | 154 |  | 133 | 3
170
[7 empty] | Story Points Estimates | Approx US count (3SP = 1US | AC Count (derived from US) | Manual Ac count (incl. Content Validation and document automation) | Automation Ac count- New | Automation Ac count - Reusable | Integration AC count
[6 empty] | PAS10 | 800 | 267 | 200 | 40 | 70 | 120 | 10
[6 empty] | No of Scenarios |  |  |  |  | 24 | 80
NB
CP
|  |  |  | US Count | AC Count
|  |  | PAS9 | 429 | 339
|  |  | PAS10 | 63 | 47
|  |  | PAS9 Revised Scope | 492 | 386
[7 empty] | 26 US | 235 AC | 33 AC | 1.2692
[7 empty] | 110 US |  | 86 AC | 0.78182

## Revised Scope Sheet Jen (hidden)
|  |  | Developed in 2014 | [8 empty] | Developed in 2015 | [8 empty] | Developed in 2016
PAS Sprint Planning Tool |  |  | Release June 2014 |  | Release Sept 2014 |  | Release Dec 2014 |  | Release Jun 2015 |  | Release Aug 2015 |  | Release Jan 2016 |  | Release March 2016 |  | Release June 2016 |  | Release Sep 2016 |  | Release Nov 2016 |  | Release Feb 2017 |  | Release May 2017 |  | Release Sep 2017
|  |  | PAS1 |  | PAS2 |  | PAS3 |  | PAS4 |  | PAS5 |  | PAS6 |  | PAS7 |  | PAS8 |  | PAS9 |  | PAS10 |  | PAS11 |  | PAS12 |  | PAS13
|  | STORIES DUE | [6 empty] | 2014-08-01 | 2014-09-19 | 2014-11-07 | 2014-12-12 | 2015-01-23 | 2015-03-20 | 2015-06-12 | 2015-07-24 | 2015-09-04 | 2015-10-16 | 2016-01-08 | 2016-02-19 | 2016-03-25 | 2016-03-25 | 2016-06-17 | 2016-06-17 | 2016-09-09 | 2016-09-09 | 2016-12-02 | 2016-12-02
|  | DEV STARTS | 2014-01-06 | 2014-02-10 | 2014-03-24 | 2014-04-28 | 2014-06-23 | 2014-07-28 | 2014-09-22 | 2014-11-03 | 2014-12-15 | 2015-01-26 | 2015-03-16 | 2015-04-27 | 2015-07-27 | 2015-09-07 | 2015-10-19 | 2015-11-30 | 2016-02-15 | 2016-03-28 | 2016-05-09 | 2016-06-20 | 2016-08-01 | 2016-09-12 | 2016-10-24 | 2016-12-05 | 2017-01-23 | 2017-03-10
|  | DEV ENDS | 2014-02-07 | 2014-03-21 | 2014-04-25 | 2014-06-20 | 2014-07-25 | 2014-09-05 | 2014-10-31 | 2014-12-12 | 2015-01-23 | 2015-03-20 | 2015-04-24 | 2015-06-12 | 2015-09-04 | 2015-10-16 | 2015-11-27 | 2016-02-12 | 2016-03-25 | 2016-05-06 | 2016-06-17 | 2016-07-01 | 2016-09-09 | 2016-10-21 | 2016-12-02 | 2017-01-20 | 2017-03-03 | 2017-04-14
WI # |  | Work Items | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | TOTAL | % Overall
WI0001 | WI0001 | NCNU Agent Hierarchy Phase 2 of 2 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 28 | 0.138%
WI0002 | WI0002 | Utah Property, Sprint 1 | 586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 586 | 2.887%
WI0001 | WI0003 | NCNU Agent Hierarchy, CR01 for Subproducers | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0.004927%
WI0003 | WI0004 | BP Fixes and Enhancements | 0 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12.5 | 0.06159%
WI0004 | WI0005 | New 6/12 Plan, incl. Renewal Notice CR. Phase 1 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 151 | 0.744%
WI0006 | WI0006 | Other Prioritized Prod Enhancements | 0 | 53.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 53.5 | 0.2636%
WI0007 | WI0007 | Doc System Upgrade | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | 0.08868%
WI0002 | WI0008 | Utah Property, Sprint 2 | 0 | 417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 417 | 2.055%
WI0080 | WI0009 | SAM Integration | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | 0.04434%
WI0011 | WI0010 | AZ Property, Sprint 3 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 119 | 0.5863%
WI0002 | WI0011 | Utah Property, Sprint 3 | 0 | 0 | 685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 685 | 3.375%
WI0011 | WI0012 | AZ Property, Sprint 4 | 0 | 0 | 0 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 344 | 1.695%
WI0079 | WI0013 | SFDC Integration | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5 | 0.02463%
WI0002 | WI0014 | Utah Property, Complete | 0 | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 988 | 4.868%
WI0002 | WI0015 | Utah Property, Deferred Scope | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 45 | 0.2217%
WI0011 | WI0016 | AZ Property, Deferred Scope | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10 | 0.04927%
WI0012 | WI0017 | Structural Services for CAS | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 40 | 0.1971%
WI0013 | WI0018 | CreateHomeQuote Service | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 44 | 0.2168%
WI0016 | WI0019 | PAS Upgrade 5.2 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 100 | 0.4927%
WI0017 | WI0020 | PA Property | 0 | 0 | 0 | 0 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 289 | 1.424%
WI0018 | WI0021 | VA Property | 0 | 0 | 0 | 0 | 308 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 396 | 1.951%
WI0019 | WI0022 | NJ Property | 0 | 0 | 0 | 0 | 0 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 620 | 3.055%
WI0014 | WI0023 | Comparative Rater AZ | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 21 | 0.1035%
WI0034 | WI0024 | CO Property | 0 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 286 | 1.409%
WI0029 | WI0025 | IN Property | 0 | 0 | 0 | 0 | 0 | 0 | 181.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 181.25 | 0.893%
WI0133 | WI0026 | UBI - Phase 1 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 99 | 0.4878%
WI0134 | WI0027 | AMEX/Discover | 0 | 0 | 0 | 0 | 0 | 0 | 70.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 70.5 | 0.3473%
WI0021 | WI0028 | CA Property | 0 | 0 | 0 | 0 | 0 | 0 | 36.25 | 541.6 | 845 | 785.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2208.55 | 10.88%
WI0202 |  | CAS Delta Work for CA Property | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 15 | 0.0739%
WI0270 |  | CA Property CRs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.8 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 89 | 0.4385%
WI0272 |  | CA Property Deferred Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | -22.5
WI0138 |  | HO4 Service Agent CR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0.3202%
WI0045 |  | DE Property | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207.5 | 1.022%
WI0162 | WI0029 | CA HDES Conversion, Phase 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.3 | 133.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202.5 | 0.9977%
WI0281 |  | CEA Q4 2015 Rate Change | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 0.5223%
WI0283 |  | SS Automated Renewal Rules, Phase 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0.06898%
WI0160 | WI0030 | UBI - Phase 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 0.5173%
WI0206 |  | 6/12 Bill Plan Property | Sprint 7: 0; Sprint 8: 0; Sprint 9: 0 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106
WI0032 | WI0031 | OK Property | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 0.5173%
WI0269 | WI0032 | UBI - Phase 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.08868%
WI0191 | WI0032 | Misc Prod Enhancements PAS7 | [10 empty] | 0 | 0.3 | 27.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
WI0048 | WI0033 | MD Property | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.5 | 1.914%
WI0022 | WI0034 | CA Auto Choice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.3 | 428.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645 | 3.178%
WI0204 | WI0035 | MD Auto Tiering (with new U/W companies) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0.1429%
WI0196 | WI0036 | Manual CNV + Auto Capping (NJ, PA) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.5 | 0.9041%
WI0291 | WI0037 | CA Select Changes (DOI) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.8 | 49.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 0.7193%
WI0047 | WI0038 | CT Property | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.5 | 1.067%
WI0033 | WI0039 | OH Property | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.5 | 0.4902%
WI0283 | WI0040 | SS Automated Renewal Rules, Phase 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0.34%
WI0035 | WI0041 | KS Property | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0.3597%
WI0275 | WI0042 | Manual CNV + Auto Capping (DE, VA, MD) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 0.7784%
WI0308 | WI0043 | Document Trigger Changes for Choice (ProdEnh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 0.6701%
WI0327 | WI0043 | UBI - Phase 4 (Prod Enh) | [10 empty] | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
WI0300 | WI0044 | Usability Improvements - SS Bundle Simplifications (ProdEnh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0.08868%
WI0311 | WI0045 | Production Defects Fixed in PAS6.1 | [10 empty] | 0 | 0 | 0 | 0 | 12.8 | 301.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314
WI0205 | WI0045 | Document Redesign | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396.5 | 1.954%
WI0328 | WI0045 | KY Property Comp Rater (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.75
WI0311 |  | Production Defects Fixed in PAS8 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 46.05 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.5
WI0036 | WI0046 | KY Property (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0.6356%
WI0039 | WI0047 | WV Property (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 0.7243%
WI0038 | WI0048 | SD Property (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0.3695%
WI0040 | WI0048 | NV Property (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 0.5025%
WI0315 | WI0048 | Property PAS Simplification Phase 1 (formerly CA Simplification) (ProdEnh) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163
WI0309 |  | Manual Changes to Renewal Image (Orig Scope) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202
WI0044 |  | WY Property (Orig Scope) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
WI0041 |  | MT Property (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.55 | 131.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 0.7735%
WI0325 |  | ID Property Comp Rater(Orig Scope) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.08
WI0326 |  | OR Property Comp Rater (Orig Scope) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.52
WI0046 |  | NY Property (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282.95 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283.02 | -283.02
WI0041 |  | MT Property (Orig Scope)- Dependency PAS10 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
WI0044 |  | WY Property (Orig Scope)- Dependency PAS10 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
WI0042 |  | ID Property (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.73 | 0.1169%
WI0043 |  | OR Property (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.95 | 0.08351%
WI0049 |  | DC Property (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108.48 | 0.5345%
WI0162 |  | CA HDES Conversion, Phase 2 (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0.9854%
WI0320 |  | CA Property Rate Change (Prod Enh) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130
WI0318 |  | Technical Design: Manual Change to Renewal Image (Orig Scope) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84.75
WI0316 |  | Property PAS Simplification Phase 2 (Prod Enh) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 39.98 | 0 | 0 | 0 | 0 | 0 | 40
WI0208 |  | CA Prop Conversion SIS (DP3) & Foxpro (PUP) (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.89 | 0 | 0 | 0 | 0 | 0 | 59.89 | 0.2951%
WI0301 |  | PAS System Controls (ProdEnh) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0 | 99.87 | 0 | 0 | 0 | 100 | 0.4927%
WI0037 |  | PAS Upgrade x.x (Orig Scope) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 300
WI0304 |  | MVR Refactoring Phase 1 of 4 (Prod Enh) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50
WI0305 |  | MVR Refactoring, Phase 2 of 4 (Prod Enh) | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 52
WI0312 |  | Manual CNV + Auto Capping (NY, OR, ID, AZ-ACIC) (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.36 | 0 | 0 | 0 | 81.36 | 0.4009%
WI0203 |  | Manual CNV + Auto Capping (CT, KS, KY,MT, SD, UT, WV, WY, DC) (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219.22 | 0 | 0 | 0 | 219.22 | 1.08%
WI0030 |  | Manual CNV + Prop Capping (DE, MD, NJ, PA, VA) (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.55 | 190.35 | 0 | 0 | 259.9 | 1.281%
WI0302 |  | Manual CNV + Prop Capping (SD, NV, NY, WV) (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302.84 | 0 | 0 | 302.84 | 1.492%
WI0276 |  | Manual CNV + Prop Capping (UT, AZ, CO, IN, OK, CT, OH, KS, KY) (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 358.81 | 322.58 | 0 | 681.39
WI0299 |  | CA Choice Conversion (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 0 | 113
WI0303 |  | Manual CNV + Prop Capping (MT, ID, OR, WY, DC) (Orig Scope) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378.55 | 0 | 378.55
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
#N/A |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | #N/A
|  | Sprint Allocation for WorkItems | 614 | 653 | 813 | 1337 | 836 | 729 | 673 | 541.6 | 845 | 889.5 | 364.5 | 587.5 | 632.5 | 738 | 872 | 823.5 | 872 | 478 | 604 | 0 | 100 | 0 | 872 | 852 | 814.13 | 0 | 16541.23 | 81.5%
|  | Maximimum Total Points Per Sprint | 655 | 711 | 892 | 1396 | 860 | 883 | 737.75 | 886 | 849 | 980 | 677 | 1171 | 831 | 910 | 872 | 845 | 872 | 503 | 604 | 29 | 100 | 20 | 872 | 872 | 872 | 872 | 19771.75 | 97.41%
|  | Maximum Points Per Sprint for WorkItems | 614 | 653 | 813 | 1337 | 836 | 729 | 673 | 541.6 | 845 | 889.5 | 364.5 | 587.5 | 632.5 | 738 | 872 | 823.5 | 872 | 478 | 604 | 0 | 100 | 0 | 872 | 852 | 872 | 852 | 17451.1 | 85.98%
|  | Points Reserved for Defect Debt | 36 | 50 | 68 | 24 | 2 | 50 | 0 | 45 | 0 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 1.848%
|  | Points Reserved Unknown Prod Enhancements / Fixes | 0 | 0 | 4 | 0 | 0 | 82 | 51.75 | 294.4 | 4 | 40.5 | 312.5 | 533.5 | 198.5 | 172 | 0 | 21.5 | 0 | 25 | 0 | 29 | 0 | 20 | 0 | 20 | 0 | 20 | 1828.65 | 9.01%
|  | Conversion Development Team | 5 | 8 | 7 | 35 | 22 | 22 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 0.5764%
TOTAL PAS SYSTEM EFFORT
|  | Core Development Team | 655 | 711 | 892 | 1396 | 860 | 883 | 737.75 | 886 | 849 | 980 | 677 | 1171 | 831 | 910 | 872 | 845 | 872 | 503 | 604 | 29 | 100 | 20 | 872 | 872 | 872 | 872 | 19771.75 | 97.41%
|  | Warranty & Dev Tiger Team Work (Non Sev 1 warranty) | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 345 | 1.7%
|  | Performance Fixes | Sprint 8: 20; Sprint 9: 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 0 | 180 | 0.8868%
|  | Additional QA Conversion work (i.e. Import Tool) | [26 empty] | 0
|  | TOTAL | 670 | 726 | 907 | 1411 | 875 | 898 | 752.75 | 921 | 864 | 1015 | 692 | 1206 | 846 | 945 | 887 | 880 | 887 | 538 | 619 | 64 | 115 | 55 | 887 | 892 | 872 | 872 | 20296.75 | 100%
Note on K120: Floor, Karla: Subrtacted 134.25 due to haitus while developers were reprioritized to clear defects on PAS3
Note on L120: Floor, Karla 2/3/15 841 Final Scope at Sprint 8 Kick-Off + 45 Earmark for Carry-Forward 886 Total Capacity 872 - 886 14 Above standard capacity
Note on M120: Floor, Karla: Updated per Sprint 10 Kick-Off deck
Note on N120: Tan, Jeffrey: Moved 89 points to PAS 5 so we increased capacity. +11 SPs increae capacity per Scott H. +20 SPs for CAS Delta work, per Nick RTC reconciliation in RTC on 1/20. 1/27, we increased capacity again by increase in SPs. See Rev notes. Floor, Karla 2/3/15 841 Final Scope at Sprint 10 Kick-Off 50 Earmark for Carry-Forward 891 Total Capacity 872 -891 19 Above standard capacity
Note on O120: 5/5/15 - Kat Freitas Added in 5 pts to capacity per 4/30 email from Jim Larkin stating he took 677 pts in PAS6 Sprint 11 2/18/2015: Removing 200 SPs. Developers and Functional testers to assist with regression defects in PAS 5. Tan, Jeffrey: Removing CR Factor from CA Property of 69 SPs from PAS 5 and reduced Capacity in PAS 6. Per Mark Discussion with Scott. Floor, Karla 2/3/15: Removed subtraction from 083 and created new earmark row for CR Factor to decrement total capacity 69 = CA CR Factor Spill Over Subtracting the 69 SPs per Mark and Karla on 2/6 meeting.
Note on P120: Kathleen Freitas 6/19/15: Removed the 1 pt to push MD to PAS7 as planned Kathleen Freitas 5/14/15: Removed the 62 pts added on 5/6/15 and added on 5/19/15 a full week of capacity 300 pts to accomodate all work planned for PAS6 (Per Jim 480 pts is a full week but you reduce by 12% for sick/holidays/PTO so you get 422 as the amount to use per week; however Scott Barth indicates it's 300 points not 422 so Mark asked that we use 300) Kathleen Freitas 5/6/15: Added 62 points to sprint capacityto align with a 4/30/15 email from Jim Larkin indicating that is what he has taken in to the Sprint as of the email date
Note on Q120: Kathleen Freitas: Jim indicated that he took 831 pts in S13
Note on R120: Kathleen Freitas: Jim added 68 pts to S14 capacity
Note on T120: Kathleen Freitas: Decreased capacity for PAS8, Sprint 16 by 90 points per Jim’s recommendation for how to handle QA's capacity need to complete testing of the Manual Conversion and Auto Capping for NJ and PA (which has no DEV work associated). This is PAS7 scope that cannot be tested until the import tooll is available. See email chain under WI0196 dated 9/18/15 Jim emailed on 10/19/15 5:37PM indicating we will add back 20 pts to S16 for Exigen who was under by 20pts in S15 but will be over 20pts in S16. Don Sievers provided his approval to Jim to add back in the 20pts to S16. 12/7/15: Updated PAS8 Release with actuals. As a result only 872 + 754 = 1626 Story Points are utilized. Adjusting SP16 Capacity down by 48 story points. 1/21/16: 54 SPs added as many CRs approved for PAS8
Note on Q122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on R122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on S122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on T122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on U122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on V122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on W122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on X122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on Y122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on Z122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on AA122: Kathleen Freitas: Budget for Defect Debt and Prod Enhancement were combined in to a single budget and now under Prod Enhancements/Fixes
Note on S123: AAA NCNU User: vital late breaking prod enhancements 6.1 defects included as line item
Note on T123: Kathleen Freitas: 126 Pts CRs processed
Note on U123: Kathleen Freitas: 7/23/15: TT requested that we take 1/2 Prod Enhancement pts and from S21 and add them to S17 (151/2=75.5)
Note on V123: Kathleen Freitas: 7/23/15: TT requested that we take 1/2 Prod Enhancement pts and from S22 and add them to S18 (151/2=75.5) Reduced Prod Enh by 100 pts to accommodate WI0301 Narayan- 20 pts for vital late breaking and 5 pts added for CR - WI0339 CR01 that was approved on01/28/16
Note on X123: Narayan- reserved for vital late breaking- 9 pts added for WI0330 CR01- CR approved
Note on Y123: Kathleen Freitas: 7/23/15: 151 pts to start. TT requested that we take half of the Prod Enhancement pts and from S21 and add them to S17 (151/2=75.5). Also reduced pts by 50pts due to WI0304 MVR Refactoring Phase 1
Note on Z123: Kathleen Freitas: 7/23/15: TT requested that we take half of the Prod Enhancement pts and from S22 and add them to S18 (151/2=75.5)
Note on AB123: Kathleen Freitas: 151 prod enh points reduced by 50pts for WI0305 MVR Refactoring Phase 2 Narayan: 20 pts reserved for vital late breaking
The maximum story points per sprint should be entered manually in the Maximum Total Points Per Sprint row. Also enter the points reserved for Production enhancements in the Points Reserved for Prod Enhancements row. These two data points will generate the Maximum Points Per Sprint for WorkItems. (These cell values are picked up by MaxPtsPerSprint1, MaxPtsPerSprint2, and so forth. It is important not to type over the formula!)
The Total Sprint Allocation formula is designed to add up the columns but ignore "#N/A". The formula should be =SUMPRODUCT(IFERROR(SUBTOTAL(9,OFFSET(C$2,ROW(C$2:C$26)-ROW(C$2),0,1)),0)) Remember that this is a Formula Array, so it must be entered by Shift + Control + Enter. The whole formula will then appear inside { }
PLEASE DO NOT type over the formula. This WorkItems & Sprint chart is generated automatically.
The formula in the cells under WorkItems should be =INDEX(SourceData!A:A,ROW())
If the WorkList is reordered on the SourceData tab, the WorkItems list will adjust automatically
The formula in the cells under the Sprint headers should be =MIN((INDEX(SourceData!$B:$B, MATCH($B2,SourceData!$A:$A, 0))-SUM($B2:B2)), (MaxPtsPerSprint1-SUM(C$1:C1))) Note that each column needs to refer to the correct Field Nam: MaxPtsPerSprint1, MaxPtsPerSprint2, etc.
Hide the rows not in use, as they will show N/A, which is not pleasing to the eye
Remember that this is a Formula Array, so it must be entered by Shift + Control + Enter.
LEGEND
Black Font Approved scope
Gray Font Pending further discussion or final decision
Sprint Planning Tool V4.7 Final

## Burndown 4FTE-12Wk
Week Ending | Analysis & Design for Release | Milestone as per PAS Program | Task | Total Resources | Unplanned PTO | Planned PTO | Other tracks/Buffer | Available Resources | No of Resources for Analysis including review | No of Resources for Design including review | Actual Rescources for Analysis | Actual Rescources for Review | Actual Resources for Design | Actual Resources for Review | Actual Resources for Other Analysis | No. of US covered | Cumulative User stories | No. of ACs Analyzed | No. of AC/TC/Defects covered in Design | Cumulative AC/TC/Defects for design | Analysis Hours | Review Hours (Analysis) | Design Hours | Review Hours (Design) | Other Analysis Time | Functional Queries/Defect Review/Meeting Hours | Total Hours (Required Capacity) | Available Capacity | No of Days | No of Hours/day | No of hours/Week | FTEs
380 US | 310 AC
2016-07-01 | PAS10 | TBC | PAS10 Analysis | 4 | 0.4 | 0 | 0 | 3.6 | 3.6 | 0 | 2.2872 | 0.68615 | 0 | 0 | 0.54 | 62 | 62 | 312 | 0 | 0 | 78 | 23.4 | 0 | 0 | 24.3 | 32.4 | 158.1 | 162 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini
2016-07-08 | PAS10 | TBC | PAS10 Analysis | 4 | 0.4 | 0 | 0 | 3.6 | 3.6 | 0 | 2.2868 | 0.68603 | 0 | 0 | 0.54 | 49 | 111 | 561.6 | 0 | 0 | 62.4 | 18.72 | 0 | 0 | 19.44 | 25.9 | 126.46 | 129.6 | 4 | 9 | 36 | Siddhi, Varun, Harsh and Chandini
2016-07-15 | PAS10 | TBC | PAS10 Analysis | 4 | 0.4 | 0 | 0 | 3.6 | 3.6 | 0 | 2.2872 | 0.68615 | 0 | 0 | 0.54 | 62 | 173 | 873.6 | 0 | 0 | 78 | 23.4 | 0 | 0 | 24.3 | 32.4 | 158.1 | 162 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini
2016-07-22 | PAS10 | TBC | PAS10 Analysis | 4 | 0.4 | 0 | 0 | 3.6 | 3.6 | 0 | 2.2872 | 0.68615 | 0 | 0 | 0.54 | 62 | 235 | 1185.6 | 0 | 0 | 78 | 23.4 | 0 | 0 | 24.3 | 32.4 | 158.1 | 162 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini
2016-07-29 | PAS10 | TBC | PAS10 Analysis | 4 | 0.4 | 0 | 0 | 3.6 | 3.6 | 0 | 2.2872 | 0.68615 | 0 | 0 | 0.54 | 62 | 297 | 1497.6 | 0 | 0 | 78 | 23.4 | 0 | 0 | 24.3 | 32.4 | 158.1 | 162 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini
2016-08-05 | PAS10 | TBC | PAS10 Analysis | 4 | 0.4 | 0.92 | 0 | 2.68 | 2.7 | 0 | 1.715 | 0.51451 | 0 | 0 | 0.402 | 46 | 343 | 1731.6 | 0 | 0 | 58.5 | 17.55 | 0 | 0 | 18.09 | 24.1 | 118.24 | 120.6 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini | Siddhi's planned PTO
2016-08-12 | PAS10 | TBC | PAS10 Analysis | 4 | 0.4 | 1.4 | 0 | 2.2 | 2.2 | 0 | 1.3977 | 0.41932 | 0 | 0 | 0.33 | 38 | 381 | 1922.2667 | 0 | 0 | 47.6667 | 14.3 | 0 | 0 | 14.85 | 19.8 | 96.6167 | 99 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini | Varun and Siddhi's planned PTO
2016-08-19 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.4 | 0.92 | 0 | 2.68 | 0.2 | 2.5 | 0.12707 | 0.038122 | 1.5884 | 0.47652 | 0.402 | 2 | 383 | 1936.1333 | 43.3333 | 43.3333 | 3.4667 | 1.04 | 43.3333 | 13 | 14.472 | 19.3 | 94.612 | 96.48 | 4 | 9 | 36 | Siddhi, Varun, Harsh and Chandini | Varun's planned PTO
2016-08-26 | PAS10 | TBC | PAS10 Design | 4 | 0.4 | 0.92 | 0 | 2.68 | 0 | 2.7 | 0 | 0 | 1.715 | 0.51451 | 0.402 | 0 | 383 | 1936.1333 | 58.5 | 101.8333 | 0 | 0 | 58.5 | 17.55 | 18.09 | 24.1 | 118.24 | 120.6 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini | Varun's planned PTO
2016-09-02 | PAS10 | TBC | PAS10 Design | 4 | 0.4 | 0 | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 2.2872 | 0.68615 | 0.54 | 0 | 383 | 1936.1333 | 78 | 179.8333 | 0 | 0 | 78 | 23.4 | 24.3 | 32.4 | 158.1 | 162 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini
2016-09-09 | PAS10 | TBC | PAS10 Design | 4 | 0.4 | 0 | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 2.2868 | 0.68603 | 0.54 | 0 | 383 | 1936.1333 | 62.4 | 242.2333 | 0 | 0 | 62.4 | 18.72 | 19.44 | 25.9 | 126.46 | 129.6 | 4 | 9 | 36 | Siddhi, Varun, Harsh and Chandini
2016-09-16 | PAS10 | TBC | PAS10 Design | 4 | 0.4 | 0 | 0 | 3.6 | 0 | 3.6 | 0 | 0 | 2.2872 | 0.68615 | 0.54 | 0 | 383 | 1936.1333 | 78 | 320.2333 | 0 | 0 | 78 | 23.4 | 24.3 | 32.4 | 158.1 | 162 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini
Assumptions
0.25 | Hr/ Work Item Analysis
1 | Hr/Work Item Design
0.3 | Hr/Review
0.2 | Hr for query or defect or meetings or others
0.15 | Hr for Other Analysis
5 | No. of detla AC in a US
Formulas:
Week Ending = +[Week Ending, row above]+7

## Burndown 4FTE-13Wk (Auto)
| Week Ending | Analysis & Design for Release | Milestone as per PAS Program | Task | Total Resources | Unplanned PTO | Planned PTO | Other tracks/Buffer | Available Resources | No of Resources for Analysis including review | No of Resources for Design including review | Actual Rescources for Analysis | Actual Rescources for Review | Actual Resources for Design | Actual Resources for Review | Actual Resources for Other Analysis | No. of US covered | Cumulative User stories | No. of ACs Analyzed | No. of AC/TC/Defects covered in Design | Cumulative AC/TC/Defects for design | Analysis Hours | Review Hours (Analysis) | Design Hours | Review Hours (Design) | Other Analysis Time | Functional Queries/Defect Review/Meeting Hours | Total Hours (Required Capacity) | Available Capacity | No of Days | No of Hours/day | No of hours/Week | FTEs
| 350 US | 312 AC | [33 empty] | AC in Regression | AC Buffer
Sp-19 | 2016-07-01 | PAS10 | TBC | PAS10 Analysis | 4 | 0.4 | 0 | 0 | 3.6 | 3.6 | 0 | 2.2868 | 0.68603 | 0 | 0 | 0.54 | 49 | 49 | 249.6 | 0 | 0 | 62.4 | 18.72 | 0 | 0 | 19.44 | 25.9 | 126.46 | 129.6 | 4 | 9 | 36 | Siddhi, Varun, Harsh and Chandini |  | 0.81579 | 39.9737 | 39.9737
| 2016-07-08 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.4 | 0 | 0 | 3.6 | 2.16 | 1.44 | 1.3721 | 0.41162 | 0.9147 | 0.27441 | 0.54 | 29 | 78 | 399.36 | 24.96 | 24.96 | 37.44 | 11.232 | 24.96 | 7.488 | 19.44 | 25.9 | 126.46 | 129.6 | 4 | 9 | 36 | Siddhi, Varun, Harsh and Chandini |  |  | 23.6579 | 38.6716
| 2016-07-15 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.4 | 0 | 0 | 3.6 | 1.152 | 2.448 | 0.7319 | 0.21957 | 1.5553 | 0.46658 | 0.54 | 19 | 97 | 499.2 | 53.04 | 78 | 24.96 | 7.488 | 53.04 | 15.912 | 24.3 | 32.4 | 158.1 | 162 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini |  |  | 15.5 | 1.1316
| 2016-07-22 | PAS10 | TBC | PAS10 Analysis | 4 | 0.4 | 0 | 0 | 3.6 | 3.6 | 0 | 2.2872 | 0.68615 | 0 | 0 | 0.54 | 8 | 105 | 811.2 | 0 | 78 | 78 | 23.4 | 0 | 0 | 24.3 | 32.4 | 158.1 | 162 | 5 | 9 | 45 | Siddhi, Varun, Harsh and Chandini |  |  | 6.5263 | 7.6579 | Conv
| 2016-07-29 | [5 empty] | PAS Core design, Invoice Document Testing activities
| 2016-08-05 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.4 | 0 | 0.9 | 2.7 | 2.1 | 0.6 | 1.3342 | 0.40026 | 0.3812 | 0.11436 | 0.405 | 21 | 126 | 993.2 | 3 | 81 | 45.5 | 13.65 | 13 | 3.9 | 18.225 | 24.3 | 118.575 | 121.5 | 5 | 9 | 45 | Siddhi, Varun, Harsh,Gurpreet |  |  | 17.1316 | 21.7895 | Conv
| 2016-08-12 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.4 | 0.8 | 0 | 2.8 | 1.2 | 1.6 | 0.76239 | 0.22872 | 1.0165 | 0.30496 | 0.42 | 6 | 132 | 1097.2 | 0 | 81 | 26 | 7.8 | 34.6667 | 10.4 | 18.9 | 25.2 | 122.9667 | 126 | 5 | 9 | 45 | Siddhi, Varun, Harsh,Gurpreet | Siddhi's and Varun's Planned PTO |  | 4.8947 | 26.6842
Sp-20 | 2016-08-19 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.4 | 0.92 | 0 | 2.68 | 1.2 | 1.48 | 0.76243 | 0.22873 | 0.94033 | 0.2821 | 0.402 | 16 | 148 | 1180.4 | 0 | 81 | 20.8 | 6.24 | 25.6533 | 7.696 | 14.472 | 19.3 | 94.1613 | 96.48 | 4 | 9 | 36 | Siddhi, Varun, Harsh,Gurpreet | Varun's planned PTO |  | 13.0526 | 39.7368
CA-CP optimization | 2016-08-26 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.2 | 0.92 | 2 | 0.88 | 0.2 | 0.6 | 0.12689 | 0.038067 | 0.38067 | 0.1142 | 0.132 | 15 | 163 | 1194.2667 | 14 | 95 | 3.4667 | 1.04 | 10.4 | 3.12 | 4.752 | 6.3 | 29.0787 | 31.68 | 4 | 9 | 36 | Siddhi, Varun, Harsh,Gurpreet | Varun's planned PTO |  | 12.2368 | 37.9737
CA-CP optimization | 2016-09-02 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.2 | 0 | 1.8 | 2 | 0.6 | 1.4 | 0.3812 | 0.11436 | 0.88946 | 0.26684 | 0.3 | 10 | 173 | 1246.2667 | 30.3333 | 125.3333 | 13 | 3.9 | 30.3333 | 9.1 | 13.5 | 18 | 87.8333 | 90 | 5 | 9 | 45 | Siddhi, Varun, Harsh,Gurpreet | Siddhi and Gurpreet working on CP optimization |  | 8.1579 | 15.7982
| 2016-09-09 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.2 | 0.4 | 0 | 3.4 | 2.1 | 1.3 | 1.3345 | 0.40034 | 0.82609 | 0.24783 | 0.51 | 29 | 202 | 1391.8667 | 22.5333 | 147.8667 | 36.4 | 10.92 | 22.5333 | 6.76 | 18.36 | 24.5 | 119.4733 | 122.4 | 4 | 9 | 36 | Siddhi, Varun, Harsh,Gurpreet | Gurpreet's planned PTO |  | 23.6579 | 16.9228
| 2016-09-16 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.2 | 0.6 | 0 | 3.2 | 2 | 1.2 | 1.2707 | 0.3812 | 0.76239 | 0.22872 | 0.48 | 34 | 236 | 1565.2 | 26 | 173.8667 | 43.3333 | 13 | 26 | 7.8 | 21.6 | 28.8 | 140.5333 | 144 | 5 | 9 | 45 | Siddhi, Varun, Harsh,Gurpreet | Siddhi's planned PTO |  | 27.7368 | 18.6596
| 2016-09-23 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.2 | 0 | 0 | 3.8 | 2 | 1.8 | 1.2707 | 0.3812 | 1.1436 | 0.34308 | 0.57 | 34 | 270 | 1738.5333 | 39 | 212.8667 | 43.3333 | 13 | 39 | 11.7 | 25.65 | 34.2 | 166.8833 | 171 | 5 | 9 | 45 | Siddhi, Varun, Harsh,Gurpreet |  |  | 27.7368 | 7.3965
| 2016-09-30 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.2 | 0 | 0 | 3.8 | 2.1 | 1.7 | 1.3342 | 0.40026 | 1.0801 | 0.32402 | 0.57 | 36 | 306 | 1920.5333 | 36.8333 | 249.7 | 45.5 | 13.65 | 36.8333 | 11.05 | 25.65 | 34.2 | 166.8833 | 171 | 5 | 9 | 45 | Siddhi, Varun, Harsh,Gurpreet
| 2016-10-07 | PAS10 | TBC | PAS10 Analysis + Design | 4 | 0.2 | 0 | 0 | 3.8 | 2 | 1.8 | 1.2707 | 0.3812 | 1.1436 | 0.34308 | 0.57 | 34 | 340 | 2093.8667 | 39 | 288.7 | 43.3333 | 13 | 39 | 11.7 | 25.65 | 34.2 | 166.8833 | 171 | 5 | 9 | 45 | Siddhi, Varun, Harsh,Gurpreet
| 2016-10-14 | PAS10 | TBC | PAS10 Analysis + Design | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 1.2707 | 0.3812 | 0.3 | 0 | 340 | 2093.8667 | 43.3333 | 332.0333 | 0 | 0 | 43.3333 | 13 | 13.5 | 18 | 87.8333 | 90 | 5 | 9 | 45 | Siddhi, Varun, Harsh,Gurpreet
Assumptions
| 0.25 | Hr/ Work Item Analysis
| 1 | Hr/Work Item Design
| 0.3 | Hr/Review
| 0.2 | Hr for query or defect or meetings or others
| 0.15 | Hr for Other Analysis
| 5 | No. of detla AC in a US
Formulas:
Week Ending = +[Week Ending, row above]+7
Note on R7: Chavan, Siddhi: 15 more US analyzed but not closed, since conversion designs decision is pending
Note on U9: Kurapati, Venkata Shireesh: Conv AC design if nothing materialized from Sp-20
Note on U10: Kurapati, Venkata Shireesh: Conv AC design if nothing materialized from Sp-20

## Burndown 12 Weeks (hidden)
Week Ending | Analysis & Design for Release | Milestone as per PAS Program | Task | Total Resources | Unplanned PTO | Planned PTO | Other tracks | Available Resources | No of Resources for Analysis including review | No of Resources for Design including review | Actual Rescources for Analysis | Actual Rescources for Review | Actual Resources for Design | Actual Resources for Review | Actual Resources for Other Analysis | No. of US covered | Cumulative User stories | No. of ACs Analyzed | No. of AC/TC/Defects covered in Design | Cumulative AC/TC/Defects for design | Analysis Hours | Review Hours (Analysis) | Design Hours | Review Hours (Design) | Other Analysis Time | Functional Queries/Defect Review/Meeting Hours | Total Hours (Required Capacity) | Available Capacity | No of Days | No of Hours/day | No of hours/Week | Resources
2015-12-25 | PAS8 | PAS 7-mil 2 | PAS8 Analysis | 2 | 0.5 | 0 | 0 | 1.5 | 1.5 | 0 | 1.0385 | 0.31154 | 0 | 0 | 0.15 | 14 | 14 | 72.6923 | 0 | 0 | 21.8077 | 6.5423 | 0 | 0 | 4.05 | 8.1 | 36.45 | 40.5 | 3 | 9 | 27 | Shireesh, Anugya
2016-01-01 | PAS8 | PAS 7-mil 2 | PAS8 Analysis | 2 | 0 | 2 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9 | 27
2016-01-08 | PAS8 | PAS 7-mil 3 | PAS8 Analysis | 2 | 0.2 | 0.5 | 0 | 1.3 | 1.3 | 0 | 0.9 | 0.27 | 0 | 0 | 0.13 | 21 | 35 | 105 | 0 | 0 | 31.5 | 9.45 | 0 | 0 | 5.85 | 11.7 | 58.5 | 58.5 | 5 | 9 | 45 | Shireesh
2016-01-15 | PAS8 | PAS 7-mil 3 | Analysis | 2 | 0.2 | 1 | 0 | 0.8 | 0.8 | 0 | 0.55385 | 0.16615 | 0 | 0 | 0.08 | 12 | 47 | 64.6154 | 0 | 0 | 19.3846 | 5.8154 | 0 | 0 | 3.6 | 7.2 | 36 | 36 | 5 | 9 | 45 | Shireesh
2016-01-22 | PAS8 | PAS 7-mil 3 | Analysis | 7 | 0.7 | 1.5 | 0 | 4.8 | 4.8 | 0 | 3.3231 | 0.99692 | 0 | 0 | 0.48 | 77 | 124 | 387.6923 | 0 | 0 | 116.3077 | 34.8923 | 0 | 0 | 21.6 | 43.2 | 216 | 216 | 5 | 9 | 45 | Shireesh, Siddhi, Ravi, Varun, Gurpreet, Harsh, Anugya
2016-01-29 | PAS8 | PAS 7-mil 4 | Analysis | 8 | 1 | 2.5 | 0 | 4.5 | 4.5 | 0 | 3.1154 | 0.93462 | 0 | 0 | 0.45 | 58 | 182 | 290.7692 | 0 | 0 | 87.2308 | 26.1692 | 0 | 0 | 16.2 | 32.4 | 162 | 162 | 4 | 9 | 36 | Shireesh, Siddhi, Ravi, Varun, Upasana, Ved, Harsh, Anugya
2016-02-05 | PAS8 | PAS 7-mil 4 | Analysis | 8 | 1 | 0 | 0 | 7 | 7 | 0 | 4.8462 | 1.4538 | 0 | 0 | 0.7 | 113 | 295 | 565.3846 | 0 | 0 | 169.6154 | 50.8846 | 0 | 0 | 31.5 | 63 | 315 | 315 | 5 | 9 | 45 | Shireesh, Siddhi, Ravi, Varun, Upasana, Ved, Harsh, Anugya
2016-02-12 | PAS8 | PAS 7-mil 4 | Analysis | 8 | 1 | 1 | 0 | 6 | 6 | 0 | 4.1538 | 1.2462 | 0 | 0 | 0.6 | 96 | 391 | 484.6154 | 0 | 0 | 145.3846 | 43.6154 | 0 | 0 | 27 | 54 | 270 | 270 | 5 | 9 | 45 | Shireesh, Siddhi, Ravi, Varun, Upasana, Ved, Harsh, Anugya
2016-02-19 | PAS8 | PAS 8-mil 1 | Analysis | 9 | 1 | 1.5 | 0 | 6.5 | 6.5 | 0 | 4.5 | 1.35 | 0 | 0 | 0.65 | 105 | 496 | 525 | 0 | 0 | 157.5 | 47.25 | 0 | 0 | 29.25 | 58.5 | 292.5 | 292.5 | 5 | 9 | 45 | Shireesh, Siddhi, Ravi, Varun, Upasana, Ved, Gurpreet, Harsh, Anugya
2016-02-26 | PAS8 | PAS 8-mil 1 | Analysis & Design | 9 | 1 | 1.5 | 0 | 6.5 | 1.7 | 4.8 | 1.1769 | 0.35308 | 3.3231 | 0.99692 | 0.65 | 27 | 523 | 137.3077 | 83.0769 | 83.0769 | 41.1923 | 12.3577 | 116.3077 | 34.8923 | 29.25 | 58.5 | 292.5 | 292.5 | 5 | 9 | 45 | Shireesh, Siddhi, Ravi, Varun, Upasana, Ved, Gurpreet, Harsh, Anugya
2016-03-04 | PAS8 | PAS 8-mil 1 | Design | 9 | 1 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 5.5385 | 1.6615 | 0.8 | 0 | 523 | 0 | 138.4615 | 221.5385 | 0 | 0 | 193.8462 | 58.1538 | 36 | 72 | 360 | 360 | 5 | 9 | 45 | Shireesh, Siddhi, Ravi, Varun, Upasana, Ved, Gurpreet, Harsh, Anugya
2016-03-11 | PAS8 | PAS 8-mil 2 | Design + Buffer (additional 3.5 resource 9-5.5) | 9 | 1 | 0 | 0 | 8 | 0 | 4.5 | 0 | 0 | 3.1154 | 0.93462 | 0.8 | 0 | 523 | 0 | 77.8846 | 299.4231 | 0 | 0 | 109.0385 | 32.7115 | 36 | 72 | 249.75 | 360 | 5 | 9 | 45 | Shireesh, Siddhi, Ravi, Varun, Upasana, Ved, Gurpreet, Harsh, Anugya
429 US | 325 AC
2016-03-18 | PAS9 | PAS 8-mil 2 | PAS9 Analysis | 5 | 0.5 | 0 | 0 | 4.5 | 4.5 | 0 | 3.1154 | 0.93462 | 0 | 0 | 0.45 | 72 | 72 | 363.4615 | 0 | 0 | 109.0385 | 32.7115 | 0 | 0 | 20.25 | 40.5 | 202.5 | 202.5 | 5 | 9 | 45
2016-03-25 | PAS9 | PAS 8-mil 2 | PAS9 Analysis | 5 | 0.5 | 0 | 0 | 4.5 | 4.5 | 0 | 3.1154 | 0.93462 | 0 | 0 | 0.45 | 72 | 144 | 363.4615 | 0 | 0 | 109.0385 | 32.7115 | 0 | 0 | 20.25 | 40.5 | 202.5 | 202.5 | 5 | 9 | 45
2016-04-01 | PAS9 | PAS 8-mil 3 | PAS9 Analysis | 5 | 0.5 | 0 | 0 | 4.5 | 4.5 | 0 | 3.1154 | 0.93462 | 0 | 0 | 0.45 | 58 | 202 | 290.7692 | 0 | 0 | 87.2308 | 26.1692 | 0 | 0 | 16.2 | 32.4 | 162 | 162 | 4 | 9 | 36
2016-04-08 | PAS9 | PAS 8-mil 3 | PAS9 Analysis | 5 | 0.5 | 0 | 0 | 4.5 | 4.5 | 0 | 3.1154 | 0.93462 | 0 | 0 | 0.45 | 72 | 274 | 363.4615 | 0 | 0 | 109.0385 | 32.7115 | 0 | 0 | 20.25 | 40.5 | 202.5 | 202.5 | 5 | 9 | 45
2016-04-15 | PAS9 | PAS 8-mil 3 | PAS9 Analysis | 5 | 0.5 | 0 | 0 | 4.5 | 4.5 | 0 | 3.1154 | 0.93462 | 0 | 0 | 0.45 | 58 | 332 | 290.7692 | 0 | 0 | 87.2308 | 26.1692 | 0 | 0 | 16.2 | 32.4 | 162 | 162 | 4 | 9 | 36
2016-04-22 | PAS9 | PAS 8-mil 4 | PAS9 Analysis | 5 | 0.5 | 0 | 0 | 4.5 | 4.5 | 0 | 3.1154 | 0.93462 | 0 | 0 | 0.45 | 72 | 404 | 363.4615 | 0 | 0 | 109.0385 | 32.7115 | 0 | 0 | 20.25 | 40.5 | 202.5 | 202.5 | 5 | 9 | 45
2016-04-29 | PAS9 | PAS 8-mil 4 | PAS9 Analysis | 5 | 0.5 | 0 | 0 | 4.5 | 1.5 | 3 | 1.0385 | 0.31154 | 2.0769 | 0.62308 | 0.45 | 24 | 428 | 121.1538 | 51.9231 | 51.9231 | 36.3462 | 10.9038 | 72.6923 | 21.8077 | 20.25 | 40.5 | 202.5 | 202.5 | 5 | 9 | 45
2016-05-06 | PAS9 | PAS 8-mil 4 | PAS9 Analysis + PAS9 Design | 5 | 0.5 | 0 | 0 | 4.5 | 0 | 4.5 | 0 | 0 | 3.1154 | 0.93462 | 0.45 | 0 | 428 | 0 | 77.8846 | 129.8077 | 0 | 0 | 109.0385 | 32.7115 | 20.25 | 40.5 | 202.5 | 202.5 | 5 | 9 | 45
2016-05-13 | PAS9 | PAS9-mil 1 | PAS9 Design | 5 | 0.5 | 0 | 0 | 4.5 | 0 | 4.5 | 0 | 0 | 3.1154 | 0.93462 | 0.45 | 0 | 428 | 0 | 77.8846 | 207.6923 | 0 | 0 | 109.0385 | 32.7115 | 20.25 | 40.5 | 202.5 | 202.5 | 5 | 9 | 45
2016-05-20 | PAS9 | PAS9-mil 1 | PAS9 Design | 5 | 0.5 | 0 | 0 | 4.5 | 0 | 4.5 | 0 | 0 | 3.1154 | 0.93462 | 0.45 | 0 | 428 | 0 | 77.8846 | 285.5769 | 0 | 0 | 109.0385 | 32.7115 | 20.25 | 40.5 | 202.5 | 202.5 | 5 | 9 | 45
2016-05-27 | PAS9 | PAS9-mil 1 | PAS9 Design | 5 | 0.5 | 0 | 1 | 3.5 | 0 | 3.5 | 0 | 0 | 2.4231 | 0.72692 | 0.35 | 0 | 428 | 0 | 60.5769 | 346.1538 | 0 | 0 | 84.8077 | 25.4423 | 15.75 | 31.5 | 157.5 | 157.5 | 5 | 9 | 45
2016-06-03 | PAS9 | PAS9-mil 2 | PAS9 Design + Buffer | 5 | 0.5 | 0 | 4.5 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 428 | 0 | 0 | 346.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 45
238 US | 175 AC
2016-06-10 | PAS10 | PAS9-mil 2 | PAS10 Analysis | 4 | 1 | 0 | 0 | 3 | 3 | 0 | 2.0769 | 0.62308 | 0 | 0 | 0.3 | 48 | 48 | 242.3077 | 0 | 0 | 72.6923 | 21.8077 | 0 | 0 | 13.5 | 27 | 135 | 135 | 5 | 9 | 45
2016-06-17 | PAS10 | PAS9-mil 2 | PAS10 Analysis | 4 | 1 | 0 | 0 | 3 | 3 | 0 | 2.0769 | 0.62308 | 0 | 0 | 0.3 | 48 | 96 | 242.3077 | 0 | 0 | 72.6923 | 21.8077 | 0 | 0 | 13.5 | 27 | 135 | 135 | 5 | 9 | 45
2016-06-24 | PAS10 | PAS9-mil 2 | PAS10 Analysis | 4 | 1 | 0 | 0 | 3 | 3 | 0 | 2.0769 | 0.62308 | 0 | 0 | 0.3 | 48 | 144 | 242.3077 | 0 | 0 | 72.6923 | 21.8077 | 0 | 0 | 13.5 | 27 | 135 | 135 | 5 | 9 | 45
2016-07-01 | PAS10 | PAS9-mil 3 | PAS10 Analysis | 4 | 1 | 0 | 0 | 3 | 3 | 0 | 2.0769 | 0.62308 | 0 | 0 | 0.3 | 29 | 173 | 145.3846 | 0 | 0 | 43.6154 | 13.0846 | 0 | 0 | 8.1 | 16.2 | 81 | 81 | 3 | 9 | 27
2016-07-08 | PAS10 | PAS9-mil 3 | PAS10 Analysis | 4 | 1 | 0 | 0 | 3 | 3 | 0 | 2.0769 | 0.62308 | 0 | 0 | 0.3 | 48 | 221 | 242.3077 | 0 | 0 | 72.6923 | 21.8077 | 0 | 0 | 13.5 | 27 | 135 | 135 | 5 | 9 | 45
2016-07-15 | PAS10 | PAS9-mil 3 | PAS10 Analysis | 4 | 1 | 0 | 0 | 3 | 1.5 | 1.5 | 1.0385 | 0.31154 | 1.0385 | 0.31154 | 0.3 | 24 | 245 | 121.1538 | 25.9615 | 25.9615 | 36.3462 | 10.9038 | 36.3462 | 10.9038 | 13.5 | 27 | 135 | 135 | 5 | 9 | 45
2016-07-22 | PAS10 | PAS9-mil 4 | PAS10 Design | 4 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 2.0769 | 0.62308 | 0.3 | 0 | 245 | 0 | 51.9231 | 77.8846 | 0 | 0 | 72.6923 | 21.8077 | 13.5 | 27 | 135 | 135 | 5 | 9 | 45
2016-07-29 | PAS10 | PAS9-mil 4 | PAS10 Design | 4 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 2.0769 | 0.62308 | 0.3 | 0 | 245 | 0 | 51.9231 | 129.8077 | 0 | 0 | 72.6923 | 21.8077 | 13.5 | 27 | 135 | 135 | 5 | 9 | 45
2016-08-05 | PAS10 | PAS9-mil 4 | PAS10 Design | 4 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 2.0769 | 0.62308 | 0.3 | 0 | 245 | 0 | 51.9231 | 181.7308 | 0 | 0 | 72.6923 | 21.8077 | 13.5 | 27 | 135 | 135 | 5 | 9 | 45
2016-08-12 | PAS10 | PAS10-mil 1 |  | 4 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 245 | 0 | 0 | 181.7308 | 0 | 0 | 0 | 0 | 13.5 | 27 | 40.5 | 135 | 5 | 9 | 45
2016-08-19 | PAS10 | PAS10-mil 1 |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 245 | 0 | 0 | 181.7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 45
2016-08-26 | PAS10 | PAS10-mil 1 |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 245 | 0 | 0 | 181.7308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 45
Assumptions
0.3 | Hr/ Work Item Analysis
1.4 | Hr/Work Item Design
0.3 | Hr/Review
0.2 | Hr for query or defect or meetings or others
0.1 | Hr for Other Analysis
5 | No. of AC in a US
Formulas:
Week Ending = [Week Ending, row above]+7

## PAS 7 Burndown (hidden)
Adding 3 resources
Type | Comments | Week Ending | Task | Available Resources | Total Resources | No of Resources for Scenario Pattern Creation | No. of US covered in Pattern Analysis | Cumulative User stories | No. of Calenar ACs covered in Pattern Analysis | AC | Approx. No. of Patterns | No of Resources for Scenario Designing | No. of ACs covered in Design | Approx. No. of Scenarios | Pattern Creation Hours | Review Hours (Pattern Creation) | Scenario Designing Hours | Review Hours (Design) | Other Analysis Time | Functional Queries/Defect Review Hours | Total Hours (Required Capacity) | Available Capacity | No of Days | No of Hours/day | No of hours/Week
PAS7 | Pas 6-mil 3 | 2015-09-04 | Sprint 13 analysis | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 45
PAS7 | Pas 6-mil 3 | 2015-09-11 | Sprint 13 analysis | 2 | 1 | 1 | 16 | 16 | 80.0415 |  |  | 0 | 0 | 0 | 26.6805 | 8.0041 | 0 | 0 | 4.95 | 9.9 | 44.5846 | 49.5 | 5.5 | 9 | 49.5
PAS7 | Pas 6-mil 3 | 2015-09-18 | Sprint 13 analysis | 3 | 2.5 | 2.5 | 29 | 45 | 145.53 |  |  | 0 | 0 | 0 | 48.51 | 14.553 | 0 | 0 | 9 | 18 | 81.063 | 90 | 4 | 9 | 36
PAS7 | Pas 6-mil 4 | 2015-09-25 | Sprint 13 analysis | 3 | 2.5 | 2.5 | 43 | 88 | 218.295 |  |  | 0 | 0 | 0 | 72.765 | 21.8295 | 0 | 0 | 13.5 | 27 | 121.5945 | 135 | 6 | 9 | 54
PAS7 | Pas 6-mil 4 | 2015-10-02 | Sprint 13 analysis | 9 | 8.5 | 8.5 | 98 | 186 | 494.802 |  |  | 0 | 0 | 0 | 164.934 | 49.4802 | 0 | 0 | 30.6 | 61.2 | 275.6142 | 306 | 4 | 9 | 36
PAS7 | Pas 6-mil 4 | 2015-10-09 | Sprint 13 analysis | 9 | 8.5 | 7 | 122 | 308 | 611.226 |  |  | 1.5 | 21.8295 | 4.3659 | 203.742 | 61.1226 | 43.659 | 13.0977 | 45.9 | 91.8 | 413.4213 | 459 | 6 | 9 | 54
PAS7 |  | 2015-10-16 | Sprint 13 analysis + Design | 9 | 8.5 | 0 | 0 | 308 | 0 |  |  | 8.5 | 123.7005 | 24.7401 | 0 | 0 | 247.401 | 74.2203 | 45.9 | 91.8 | 413.4213 | 459 | 6 | 9 | 54
PAS7 |  | 2015-10-23 | Sprint 13 design | 9 | 8.5 | 7.5 | 87 | 395 | 436.59 |  |  | 1 | 9.702 | 1.9404 | 145.53 | 43.659 | 19.404 | 5.8212 | 30.6 | 61.2 | 275.6142 | 306 | 4 | 9 | 36
PAS7 | Pas 7-mil 1 | 2015-10-30 | Sprint 13 design + Sprint 14 analysis | 7.5 | 7 | 7 | 101 | 496 | 509.355 |  |  | 0 | 0 | 0 | 169.785 | 50.9355 | 0 | 0 | 31.5 | 63 | 283.7205 | 315 | 5 | 9 | 45
PAS7 | Pas 7-mil 1 | 2015-11-06 | Sprint 14 analysis | 8.5 | 8 | 7.5 | 109 | 605 | 545.7375 |  |  | 0.5 | 6.0637 | 1.2127 | 181.9125 | 54.5737 | 12.1275 | 3.6382 | 36 | 72 | 324.252 | 360 | 5 | 9 | 45
PAS7 | Pas 7-mil 1 | 2015-11-13 | Sprint 14 analysis | 7.5 | 7 | 0 | 0 | 605 | 0 |  |  | 7 | 67.914 | 13.5828 | 0 | 0 | 135.828 | 40.7484 | 25.2 | 50.4 | 226.9764 | 252 | 4 | 9 | 36
PAS7 | Pas 7-mil 2 | 2015-11-20 | Sprint 14 analysis + Design | 7.5 | 7 | 0 | 0 | 605 | 0 |  |  | 7 | 84.8925 | 16.9785 | 0 | 0 | 169.785 | 50.9355 | 31.5 | 63 | 283.7205 | 315 | 5 | 9 | 45
PAS7 | Pas 7-mil 2 | 2015-11-27 | Sprint 14 design | 6.5 | 0 | 0 | 0 | 605 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 45
PAS7 | Pas 7-mil 2 | 2015-12-04 | Expected Rework |  | 0 | 0 | 0 | 605 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 36
PAS7 | Pas 7-mil 3 | 2015-12-11 | Expected Rework |  | 0 | 0 | 0 | 605 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 45
PAS7 | Pas 7-mil 3 | 2015-12-18 | Estimated buffer |  | 0 | 0 | 0 | 605 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 9 | 45
PAS7 | Pas 7-mil 3 | 2015-12-25 |  |  | 0 | 0 | 0 | 605 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 36
Pas 7-mil 4
Assumptions
1 | This does not include any rework required if scope changes
2 | Gurpreet's effort is added as .5 from Week ending 30 oct
3 | if two resource are added strating week ending 30 oct
Assumptions
| No of PTOs (Planned, Holidays, Unplanned) |  | 1
| Hr/AC for Analysis |  | 0.33333 | [14 empty] | reusability
| Hr/AC for Design |  | 1.5
| Hr/Bug/TC analysis and design |  | 2
| Hr/Review |  | 0.3
| Hr/query or defect or meetings or others |  | 0.2 |  | jira | reporting | manual queries
| Hr/Other Analysis |  | 0.1
| No. of ACs per Pattern |  | 5
| Hours per week |  | 45
CL - Initial Analysis
Note on X4: Kabra, Shreevardhan: 1 DAY WEEKEND WORK
Note on X6: Kabra, Shreevardhan: 1 DAY WEEKEND WORK
Note on X8: Kabra, Shreevardhan: 1 DAY WEEKEND WORK
Note on X9: Kabra, Shreevardhan: 1 DAY WEEKEND WORK

## PAS2,3,4 estimates (hidden)
Comments
Original
[5 empty] | Part of Scenarios | [5 empty] | Individual TCs
|  | Total |  |  | Sub Total |  | Automated (Fully/Partially) | Fully Automatable | Partially Automatable | Not Automatable | Sub Total | Automated (Fully/Partially) | Fully Automatable | Partially Automatable | Not Automatable
Property (Approx) |  | 432 |  |  | 291 |  | 69 | 63 | 149 | 10 | 141 | 0 | 54 | 45 | 42 |  | 240
Auto (Approx) |  | 259 |  |  | 122 |  | 3 | 19 | 94 | 6 | 137 | 1 | 49 | 50 | 37
Total PAS2,3,4 TCs |  | 691 |  |  | 413 |  | 72 | 82 | 243 | 16 | 278 | 1 | 103 | 95 | 79
Progress
[5 empty] | Part of Scenarios | [5 empty] | Individual TCs
|  | Total |  |  | Sub Total |  | Automated (Fully/Partially) | Fully Automatable | Partially Automatable | Not Automatable | Sub Total | Automated (Fully/Partially) | Fully Automatable | Partially Automatable | Not Automatable
Property (Approx) |  | 432 |  |  | 291 |  | 69 | 63 | 149 | 10 | 141 | 0 | 54 | 45 | 42
Auto (Approx) |  | 259 |  |  | 122 |  | 3 | 19 | 94 | 6 | 137 | 1 | 49 | 50 | 37 | 6 UBI TCs in Scope of Manual team of 26 in UBI Dump
Total PAS2,3,4 TCs |  | 691 |  |  | 413 |  | 72 | 82 | 243 | 16 | 278 | 1 | 103 | 95 | 79
Burndown
Week Ending | No. of Resources | Hrs/TC | No of Working Days | Available Capacity | No of Test cases | Cumulative TC Count | Category | No. of Scenarios - To Be Delivered
4th Sept | 1 | 2.5 | 2 | 18 | 7.2 | 7.2 | UBI Test Cases | 1.8
11th Sept | 2 | 2.5 | 5 | 90 | 36 | 43.2 | UBI Test Cases Property Individual Test Cases - Fully/Partially Automatable | 9
18th Sept | 2 | 2.5 | 4 | 72 | 28.8 | 72 | Property Individual Test Cases - Fully/Partially Automatable | 7.2
25th Sept | 2 | 2 | 5 | 90 | 45 | 117 | Property Individual Test Cases - Fully/Partially Automatable | 11.25
2nd Oct | 2 | 2 | 4 | 72 | 36 | 153 | Property Individual Test Cases - Fully/Partially Automatable Property Scenarios Fully/Partially Automatable Optimization | 9
9th Oct | 2 | 2 | 5 | 90 | 45 | 198 | Property Scenarios Fully/Partially Automatable Optimization | 11.25
16th Oct | 2 | 2 | 5 | 90 | 45 | 243 | Property Scenarios Fully/Partially Automatable Optimization | 11.25
23rd Oct | 2 | 2 | 4 | 72 | 36 | 279 | Property Scenarios Fully/Partially Automatable Optimization | 9
30th Oct | 2 | 2 | 5 | 90 | 45 | 324 | Property Scenarios Fully/Partially Automatable Optimization | 11.25
6th Nov | 2 | 2 | 5 | 90 | 45 | 369 | Property Scenarios Fully/Partially Automatable Optimization Auto Individual Test Cases - Fully/Partially Automatable | 11.25
13th Nov | 2 | 2 | 4 | 72 | 36 | 405 | Auto Individual Test Cases - Fully/Partially Automatable | 9
20th Nov | 2 | 2 | 5 | 90 | 45 | 450 | Auto Individual Test Cases - Fully/Partially Automatable Auto Scenarios Fully/Partially Automatable Optimization | 11.25
27th Nov | 2 | 2 | 5 | 90 | 45 | 495 | Auto Scenarios Fully/Partially Automatable Optimization | 11.25
4th Dec | 2 | 2 | 4 | 72 | 36 | 531 | Auto Scenarios Fully/Partially Automatable Optimization | 9
11th Dec | 2 | 2 | 5 | 90 | 45 | 576 | Auto Scenarios Fully/Partially Automatable Optimization Property Test Cases - Not Automable | 11.25
18th Dec | 2 | 2 | 5 | 90 | 45 | 621 | Property Test Cases - Not Automable Auto Test Cases - Not Automable | 11.25
25th Dec | 2 | 2 | 4 | 72 | 36 | 657 | Auto Test Cases - Not Automable | 9
1st Jan | 2 | 2 | 4 | 72 | 36 | 693 |  | 9
Assumptions:
1. Hrs/TC from Week ending 25th Sept reduced to 2hrs due to expected feedback from manual team post M3
2. PTOs not accounted for in the burndown
3. 691+20 = 711 TCs
4. 1 Scenario = 4 TCs

## PAS5,6 estimates (hidden)
|  | Count of AC/Scenarios | Hours
PAS5 | CA CP design review | 5 |  | 4 - Ready for review
|  |  | 10 | 3 - Primary review
5 - Secondary review
| Policy Life cycle scenario creation | 75 | 450
| Time point scenario review | 1 | 2
PAS6 | Regression Analysis | 7 | 1 | 2 - Primary Review
|  |  | 73.47 | 5 - Clarification Pending
| CA CP design review | 10 | 20
| Policy Life cycle scenario creation | 10 | 50
| Time point scenario review | 1 | 2
PAS2,3,4 |  |  |  | Planned St.Dt | Revised St.Dt | Planned End.Dt | Revised End.Dt
week ending | 4th Sep | PAS6 | 3 | Mon EOD 2 sep | Wed EOD 3 sep | Mon EOD 7 sep | Wed EOD 9 sep | Reasons for the revision in the delivery date: 1. 3 resources were involved in incorporating the CP updates in the CL PLC scenarios on 09/02, hence no progress on CA CP reviews 2. Unplanned PTO (Gurpreet) 3. I could not review any scenarios as I was tied up with back to back meetings on Stabilization call, UBI CR Assessment, PAS6 design numbers, VC meeting and some follow ups made with the team in terms of pending CA items 4. We have to spend some hours on preparation of WSR (approximately 4-5 hours for 2 resources)
| 4th Sep | PAS2,3,4 | 1
| 4th Sep | PAS7 | 1
| 4th Sep | Review | 2
| 11th Sep |  | 3 |  |  |  |  | Varun, Siddhi and Shiriesh for review for 3 weeks
425 | 11th Sep

## CA Select Approaches (hidden)
Category | Total count of US | Assumptions
All CA Auto US | 598 | No of PTOs (Planned, Holidays, Unplanned) |  | 1
CA Select stories in QA approved/In production/test execution complete | 268 | Hr/AC for Analysis |  | 0.33333
Target release CA_Auto | 211 | Hr/AC for Design |  | 1.5
Target Release PAS1.1, 4,4.1 | 18 | Hr/Bug/TC analysis and design |  | 2
Target Release (upcoming) 5.1,6 core, 7,7.1 | 25 | Hr/Review |  | 0.3
|  | Hr/query or defect or meetings or others |  | 0.25
CP related: |  | Hr/Other Analysis |  | 0.1
Already implemented | 46 | No. of ACs per Pattern |  | 5
Upcoming release | 8 | Hours per week |  | 45
Total US: | 54 | No of AC per US in CP for Regression |  | 3.5
|  | No of AC per US in NB for Regression |  | 2
NB Related
Already implemented | 183
Upcoming release | 17
Total US: | 200
US related to Define/Capture details (UI Validation) | 45
CP related |  | NBP Related
Approach 1: |  | Approach 1:
Use Conversion CP patterns as base | Coverage expected 40% | Use Existing test cases
CA mapping effort | 18 | Total existing New business/MTC/Billing test cases | 208
GAP analysis + Pattern designing effort | 54 | Hour/test case to analyse for regression scope and pattern fitment | 1.5
Total Pattern creation effort | 72 | Total time to revit /Fit all test cases | 312
Design reusability : | 20% | Total regression coverage analysed | 10%
Design effort | 226.8 | Gap analysis of test cases with US + gap fitment | 1.6667
Review effort | 68.04 | time for US GAP analysis + remaining pattern creation | 300
Total Design effort | 294.84 | Total Pattern creation effort | 612
Total CP effort | 367 | Design reusability : | 5%
|  | Design effort | 570
Approach 2: |  | Review effort | 171
Use Property CP patterns as base | Coverage expected 80% | Total Design effort | 741
CA mapping effort | 36 | Total NB effort | 1353
GAP analysis + Pattern designing effort | 54
Total Pattern creation effort | 90 | Approach 2:
Design reusability : | 45% | Create new patterns
Design effort | 155.925 | Analysis effort | 333.3333
Review effort | 46.7775 | Design effort | 465
Total Design effort | 202.7025 | Review effort | 139.5
Total CP effort | 293 | Total Design effort | 604.5
|  | Total NB effort | 938
Approach 3:
Create new patterns
Analysis effort | 90
Design effort | 241.5
Review effort | 72.45
Total Design effort | 313.95
Total CP effort | 404

## CA Select Estimates ALT 1 (hidden)
Type | Comments | Week Ending | Task | Total Resources | No of Resources for Scenario Pattern Creation | No. of US covered in Pattern Analysis | Cumulative User stories | No. of Calenar ACs covered in Pattern Analysis | AC | Approx. No. of Patterns | No of Resources for Scenario Designing | No. of ACs covered in Design | Approx. No. of Scenarios | Pattern Creation Hours | Review Hours (Pattern Creation) | Total Analysis hours | Scenario Designing Hours | Review Hours (Design) | Total Designing hours | Other Analysis Time | Functional Queries/Defect Review Hours | Total Hours (Required Capacity) | Available Capacity | No of Days | No of Hours/day | No of hours/Week
PAS7 | Pas 6-mil 3 | 2015-09-04 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 5 | 9 | 45
PAS7 | Pas 6-mil 3 | 2015-09-11 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 4.5 | 9 | 40.5
PAS7 | Pas 6-mil 3 | 2015-09-18 |  | 2 | 2 | 21 | 21 | 108.108 |  |  | 0 | 0 | 0 | 36.036 | 10.8108 | 46.8468 | 0 | 0 | 0 | 7.2 | 18 | 64.8468 | 72 | 4 | 9 | 36
PAS7 | Pas 6-mil 4 | 2015-09-25 |  | 2 | 2 | 27 | 48 | 135.135 |  |  | 0 | 0 | 0 | 45.045 | 13.5135 | 58.5585 | 0 | 0 | 0 | 9 | 22.5 | 81.0585 | 90 | 5 | 9 | 45
PAS7 | Pas 6-mil 4 | 2015-10-02 |  | 2 | 0 | 0 | 48 | 0 |  |  | 2 | 18.018 | 3.6036 | 0 | 0 | 0 | 36.036 | 10.8108 | 46.8468 | 7.2 | 18 | 64.8468 | 72 | 4 | 9 | 36
PAS7 | Pas 6-mil 4 | 2015-10-09 |  | 2 | 0 | 0 | 48 | 0 |  |  | 2 | 22.5225 | 4.5045 | 0 | 0 | 0 | 45.045 | 13.5135 | 58.5585 | 9 | 22.5 | 81.0585 | 90 | 5 | 9 | 45
PAS7 |  | 2015-10-16 |  | 2 | 0 | 0 | 48 | 0 |  |  | 2 | 22.5225 | 4.5045 | 0 | 0 | 0 | 45.045 | 13.5135 | 58.5585 | 9 | 22.5 | 81.0585 | 90 | 5 | 9 | 45
PAS7 |  | 2015-10-23 |  | 2 | 0 | 0 | 48 | 0 |  |  | 2 | 18.018 | 3.6036 | 0 | 0 | 0 | 36.036 | 10.8108 | 46.8468 | 7.2 | 18 | 64.8468 | 72 | 4 | 9 | 36
PAS7 | Pas 7-mil 1 | 2015-10-30 |  | 4 | 4 | 54 | 102 | 270.27 |  |  | 0 | 0 | 0 | 90.09 | 27.027 | 117.117 | 0 | 0 | 0 | 18 | 45 | 162.117 | 180 | 5 | 9 | 45
PAS7 | Pas 7-mil 1 | 2015-11-06 |  | 4 | 4 | 54 | 156 | 270.27 |  |  | 0 | 0 | 0 | 90.09 | 27.027 | 117.117 | 0 | 0 | 0 | 18 | 45 | 162.117 | 180 | 5 | 9 | 45
PAS7 | Pas 7-mil 1 | 2015-11-13 |  | 4 | 4 | 43 | 199 | 216.216 |  |  | 0 | 0 | 0 | 72.072 | 21.6216 | 93.6936 | 0 | 0 | 0 | 14.4 | 36 | 129.6936 | 144 | 4 | 9 | 36
PAS7 | Pas 7-mil 2 | 2015-11-20 |  | 4 | 0 | 0 | 199 | 0 |  |  | 4 | 45.045 | 9.009 | 0 | 0 | 0 | 90.09 | 27.027 | 117.117 | 18 | 45 | 162.117 | 180 | 5 | 9 | 45
PAS7 | Pas 7-mil 2 | 2015-11-27 |  | 4 | 0 | 0 | 199 | 0 |  |  | 4 | 45.045 | 9.009 | 0 | 0 | 0 | 90.09 | 27.027 | 117.117 | 18 | 45 | 162.117 | 180 | 5 | 9 | 45
PAS7 | Pas 7-mil 2 | 2015-12-04 |  | 4 | 0 | 0 | 199 | 0 |  |  | 4 | 36.036 | 7.2072 | 0 | 0 | 0 | 72.072 | 21.6216 | 93.6936 | 14.4 | 36 | 129.6936 | 144 | 4 | 9 | 36
PAS7 | Pas 7-mil 3 | 2015-12-11 |  | 4 | 0 | 0 | 199 | 0 |  |  | 4 | 45.045 | 9.009 | 0 | 0 | 0 | 90.09 | 27.027 | 117.117 | 18 | 45 | 162.117 | 180 | 5 | 9 | 45
PAS7 | Pas 7-mil 3 | 2015-12-18 |  | 4 | 0 | 0 | 199 | 0 |  |  | 4 | 45.045 | 9.009 | 0 | 0 | 0 | 90.09 | 27.027 | 117.117 | 18 | 45 | 162.117 | 180 | 5 | 9 | 45
PAS7 | Pas 7-mil 3 | 2015-12-25 |  | 2 | 0 | 0 | 199 | 0 |  |  | 2 | 18.018 | 3.6036 | 0 | 0 | 0 | 36.036 | 10.8108 | 46.8468 | 7.2 | 18 | 64.8468 | 72 | 4 | 9 | 36
Pas 7-mil 4
Assumptions |  |  |  |  | CP Analysis Effort | [5 empty] | 90
| Using alternate 2 for CP designing |  |  |  | CP Design effort | [5 empty] | 203
Using alternate 2 for NBP designing
[5 empty] | NBP Analysis effort | [5 empty] | 334
[5 empty] | NBP Design effort | [5 empty] | 605
Assumptions
| No of PTOs (Planned, Holidays, Unplanned) |  | 1
| Hr/AC for Analysis |  | 0.33333
| Hr/AC for Design |  | 1.5
| Hr/Bug/TC analysis and design |  | 2
| Hr/Review |  | 0.3
| Hr/query or defect or meetings or others |  | 0.25 | jira | reporting | manual queries
| Hr/Other Analysis |  | 0.1
| No. of ACs per Pattern |  | 5
| Hours per week |  | 45
CL - Initial Analysis