## del (hidden)
WI0344 Left-over Auto or Property CRs
| Functional + Regression |  |  | Regression Only
| Analysis & Design |  |  | Analysis & Design
| US | 37 |  | US | 37
| AC | 440 |  | AC | 440
| Analysis effort/ US | 59.2 | Hours | Analysis effort/ US | 59.2 | Hours
| Design effort/ AC | 484 | Hours | Design effort/ AC | 30.8 | Hours
| Total Analysis + Design Efforts | 543.2 | Hours | Total Analysis + Design Efforts | 90 | Hours
| Executions |  |  | Executions
| US | 37 |  | US | 37
| AC | 440 |  | AC | 28
| Execution effort/ AC | 550 | Hours | Execution effort/ AC | 35 | Hours
| Total Hours | 1093.2 | Hours | Total Hours | 125 | Hours
| Assumptions | Hours |  | Assumptions | Hours
| Hr/ User story Analysis (including reviews) | 1.6 |  | Hr/ User story Analysis (including reviews) | 1.6
| Hr/Work Item Design (including reviews) | 1.1 |  | Hr/Work Item Design (including reviews) | 1.1
| Hr/ AC execution (1 AC = 1 Test case) | 1.25 |  | Hr/ AC execution (1 AC = 1 Test case) | 1.25

## 2 0_ PAS10 Planned Scope
Assignee (06/15/2016) | Type | Id | Target Release | Has Ren/MTC/RW Delta? | Work Item | Project | Bug Type | QC ID String | QC Status | Status | Resolution | TP Status | Preliminary Story Points | Story Points | QA Story Points | Summary | RRC ID | Story ID | Story ID Root | Version Number | Sub Version Number | Tags | Unified Business Backlog | Unified Business Priority | Planned For | Responsible For | Group Ownership | Original Scope | Added To Scope | Related To | Delta State | Final Scope | Final Scope Date | Removed from Scope | CR Number | Scope | Lockdown | Ready IT Team Review Date | IT Team Review Start Date | Story Approved Date | Feature Area | Epic - Activity | Use Case | HO Product | Priority Group | BSS Number | Resolved By | Resolves | Forms
| Story - Common Library | 631730 | PAS10 | Yes | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | H-EN-HS0490-CL 23319: US CL Add Endorsement HS 04 90 v3 | 23319 | H-EN-HS0490-CL | H-EN-HS0490 | 3 | 0 |  | TRUE | 9999 | IE_PHX-1_Reviews_Current | Srinivasan, Jagadeesan (gqe4sri) | Program |  | PAS10 | CL | CL |  |  |  | WI0344 CR03, CR JE34 | WI0344 CR03 | FALSE | 2016-05-25 07:09 | 2016-05-26 10:02 |  | General | Define Endorsement | NONE | HO3,HO4,HO6 | NONE | 596886 |  | #596886 | FALSE
Harsh | Story - Common Library | 613283 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | C-DOC-GENDEC-CL 26707: Generate Declaration Document-All Products v2 | 26707 | C-DOC-GENDEC-CL | C-DOC-GENDEC | 2 | 0 |  | TRUE | 60000 | IE_PHX-3_Reviews_Current | R, Lakshmipriya | Program |  | PAS10 | CL | CL |  |  |  | WI0344 CR04, J161 | WI0344 CR04 | TRUE | 2016-05-03 07:26 | 2016-05-11 17:56 |  | General | Forms | NONE | DP3,HO3,HO4,HO6,PUP | NONE | 596884 |  | #596884 | TRUE
Harsh | Story - Delta | 618709 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 3 | NONE | NONE | H-INT-INSCRR-DE 26801: Insurance Score – Determine best insurance score during Renewal | 26801 | H-INT-INSCRR-DE | H-INT-INSCRR | 1 | 0 |  | TRUE | 60000 | IE_PHX-2_Reviews_Current | R, Lakshmipriya | Program | Unplanned | PAS10 | DE | DE |  |  |  | WI0344 CR04, WH43 | WI0344 CR04 | TRUE | 2016-04-13 06:49 | 2016-04-17 18:52 |  | Renew Policy | Integration - Renewal | NONE | DP3,HO3,HO4,HO6 | NONE | 602741 |  | #602741 | FALSE
| Story - Common Library | 613287 | PAS10 | Yes | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | 2 | NONE | H-EN-VIEW-CL 24611: View Endorsement v3 | 24611 | H-EN-VIEW-CL | H-EN-VIEW | 3 | 0 |  | TRUE | 60000 | IE_PHX-1_Reviews_Current | Prabhu, Venkatesh M (gm0xpra) | Program | Unplanned | PAS10 | CL | CL |  |  |  | WI0344 CR04, J161 | WI0344 CR04 | TRUE | 2016-04-12 08:48 | 2016-04-17 18:52 |  | General | Define Endorsement | NONE | DP3,HO3,HO4,HO6 | NONE | 596884 |  | #596884 #542301 | FALSE
Harsh | Story - Delta | 618708 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | H-INT-INSSCR-DE 26803: Insurance Score – Batch ordering every 2nd renewal v2 | 26803 | H-INT-INSSCR-DE | H-INT-INSSCR | 2 | 0 |  | TRUE | 60000 | IE_PHX-2_Reviews_Current | Raveendra Mani, Prakash Khanna (gpq6rav) | Program | Unplanned | PAS10 | SCL | DE |  |  |  | WI0344 CR04, WH43 | WI0344 CR04 | TRUE | 2016-04-13 06:49 | 2016-04-17 18:53 |  | Renew Policy | Integration - Renewal | NONE | DP3,HO3,HO4,HO6 | NONE | 602741 |  | #602741 | FALSE
Harsh | Story - Delta | 611189 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | C-DOC-AHPNXX-CA 26665: Generate Privacy Information Notice v2 | 26665 | C-DOC-AHPNXX-CA | C-DOC-AHPNXX | 2 | 0 |  | TRUE | 60000 | IE_PHX-3_Reviews_Current | Alexander, Vinay (g8nalex) | Program | Unplanned | PAS10 | CA | CA |  |  |  | WI0344 CR04, CB49 | WI0344 CR04 | TRUE | 2016-04-07 07:43 | 2016-04-17 18:54 |  | Forms | Forms - Endorsement | NONE | DP3,HO3,HO4,HO6,PUP | NONE | 602743 |  | #541668 #602743 | TRUE
| Story - Common Library | 611191 | PAS10 | Yes | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | P-BND-ELGNAEUW-CL 22774: Underwriting rules with neither Automatic Exception model nor UW Approval v4 | 22774 | P-BND-ELGNAEUW-CL | P-BND-ELGNAEUW | 4 | 0 |  | TRUE | 60000 | IE_PHX-2_Reviews_Current | Alexander, Vinay (g8nalex) | Program | Unplanned | PAS10 | CL | CL |  |  |  | WI0344 CR04, UW42 | WI0344 CR04 | TRUE | 2016-04-07 07:43 | 2016-04-17 18:54 |  | Create New Policy | PUP - New Business | NONE | PUP | NONE | 596879 |  | #542805 #596879 | FALSE
Harsh | Story - Delta | 624044 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | E-APP-GENAPP-CA 26881: Generate Application Document HO4 HO6 v2 | 26881 | E-APP-GENAPP-CA | E-APP-GENAPP | 2 | 0 |  | TRUE | 60000 | IE_PHX-3_Reviews_Current | Sankaran, Manikandan (gm70san) | Program |  | PAS10 | CA | CA |  |  |  | WI0344 CR04, CB57 | WI0344 CR04 | TRUE | 2016-04-27 07:14 | 2016-05-11 17:56 |  | Forms | CEA - Forms | NONE | CEA | NONE | 593657 |  | #593657 | TRUE
Harsh | Story - Common Library | 624045 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | H-INT-INSCRR-CL 26873 : Insurance Score - FR Score comparison - Renewal v2 | 26873 | H-INT-INSCRR-CL | H-INT-INSCRR | 2 | 0 |  | TRUE | 60000 | IE_PHX-2_Reviews_Current | P, Nalini (gm02p) | Program |  | PAS10 | CL | CL |  |  |  | WI0344 CR04, AW36 | WI0344 CR04 | TRUE | 2016-04-21 08:33 | 2016-05-11 17:57 |  | General | Integration - General | NONE | DP3,HO3,HO4,HO6 | NONE | 596883 |  | #596883 #542136 | FALSE
Harsh | Story - Delta | 624046 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | E-APP-GENAPP-CA 26892: Generate Application Document HO3 DP3 v3 | 26892 | E-APP-GENAPP-CA | E-APP-GENAPP | 3 | 0 |  | TRUE | 60000 | IE_PHX-3_Reviews_Current | Sankaran, Manikandan (gm70san) | Program |  | PAS10 | CA | CA |  |  |  | WI0344 CR04, CB57 | WI0344 CR04 | TRUE | 2016-04-27 07:14 | 2016-05-11 17:57 |  | Forms | CEA - Forms | NONE | CEA | NONE | 593657 |  | #593657 | TRUE
Varun | Story - Common Library | 620672 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | 2.5 | NONE | P-ULR-FIREARM-CL 24770: PUP Capture Firearms Information v3 | 24770 | P-ULR-FIREARM-CL | P-ULR-FIREARM | 3 | 0 |  | TRUE | 60000 | IE_PHX-1_Reviews_Current | Alexander, Vinay (g8nalex) | Program | Unplanned | PAS10 | CL | CL |  |  |  | WI0344 CR04, U110 | WI0344 CR04 | TRUE | 2016-04-07 07:43 | 2016-04-17 18:56 |  | General | PUP - New Business | NONE | PUP | NONE | 596885 |  | #596885 #542788 | FALSE
| Story - Common Library | 620673 | PAS10 | Yes | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | 1 | NONE | P-BND-ELGEXP-CL 22604: Eligibility related to the count of the exposure units/risks v3 | 22604 | P-BND-ELGEXP-CL | P-BND-ELGEXP | 3 | 0 |  | TRUE | 60000 | IE_PHX-2_Reviews_Current | Alexander, Vinay (g8nalex) | Program | Unplanned | PAS10 | CL | CL |  |  |  | WI0344 CR04, U110 | WI0344 CR04 | TRUE | 2016-04-12 08:48 | 2016-04-17 18:57 |  | General | PUP - New Business | NONE | PUP | NONE | 596885 |  | #596885 #542813 | FALSE
Varun | Story - Common Library | 620675 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | P-TSK-TASK-CL 26854: Task Management for PUP v2 | 26854 | P-TSK-TASK-CL | P-TSK-TASK | 2 | 0 |  | TRUE | 60000 | IE_PHX-2_Reviews_Current | Alexander, Vinay (g8nalex) | Program | Unplanned | PAS10 | CL | CL |  |  |  | WI0344 CR04, U110 | WI0344 CR04 | TRUE | 2016-04-07 07:43 | 2016-04-17 18:57 |  | General | Task Management - General | NONE | PUP | NONE | 596885 |  | #596885 #542870 | FALSE
| Story - Common Library | 627377 | PAS10 | Yes | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In TA Review |  | In BA Review | 2 | NONE | NONE | H-INT-PRF-CL 23757: Prefill and add Other active AAA policies v2 | 23757 | H-INT-PRF-CL | H-INT-PRF | 2 | 0 |  | TRUE | 60000 | Property Backlog | Alexander, Vinay (g8nalex) | Program |  | PAS10 | CL | CL |  |  |  | WI0344 CR04 | WI0344 CR04 | TRUE |  |  |  | General | Integration - General | NONE | HO3,HO4,HO6 | NONE | 606062 |  | #606062 #542166 | FALSE
Varun | Story - Delta | 627378 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In TA Review |  | Peer Review | 2 | NONE | NONE | H-INT-PRF-CA 22932: Prefill Other active AAA v5 | 22932 | H-INT-PRF-CA | H-INT-PRF | 5 | 0 |  | TRUE | 60000 | Property Backlog | P, Nalini (gm02p) | Program |  | PAS10 | CA | CA |  |  |  | WI0344 CR04 | WI0344 CR04 | TRUE |  |  |  | General | Integration - General | NONE | HO3,HO4,HO6 | NONE | 606062 |  | #606062 #542167 | FALSE
Varun | Story - Common Library | 625732 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | C-APP-GENAPP-CL 23038: Generate Application Document-All Products v8 | 23038 | C-APP-GENAPP-CL | C-APP-GENAPP | 8 | 0 |  | TRUE | 60000 | IE_PHX-3_Reviews_Current | Sankaran, Manikandan (gm70san) | Program |  | PAS10 | CL | CL |  |  |  | WI0344 CR04, CB57; J161 | WI0344 CR04 | TRUE | 2016-04-21 08:33 | 2016-05-11 17:58 |  | General | Forms | NONE | DP3,HO3,HO4,HO6,PUP | NONE | 593657; 596884 |  | #593657 #596884 | FALSE
| Story - Common Library | 618703 | PAS10 | Yes | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | H-PCQ-DISRAT-CL 23298:NB & MTC - Display Quote Details v5 | 23298 | H-PCQ-DISRAT-CL | H-PCQ-DISRAT | 5 | 0 |  | TRUE | 60000 | IE_PHX-2_Reviews_Current | Sankaran, Manikandan (gm70san) | Program |  | PAS10 | CL | CL |  |  |  | WI0344 CR04, U301 | WI0344 CR04 | TRUE | 2016-04-28 07:18 | 2016-05-11 17:58 |  | General | Save Quote | NONE | DP3,HO3,HO4,HO6 | NONE | 596882 |  | #596882 | FALSE
Varun | Story - Delta | 625733 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | H-DOC-APP-CA 22432: Generate Application Document HO3 HO4 HO6 DP3 PUP v7 | 22432 | H-DOC-APP-CA | H-DOC-APP | 7 | 0 |  | TRUE | 60000 | IE_PHX-3_Reviews_Current | Sankaran, Manikandan (gm70san) | Program |  | PAS10 | CA | CA |  |  |  | WI0344 CR04, CB57 | WI0344 CR04 | TRUE | 2016-05-06 08:54 | 2016-05-11 17:59 |  | Forms | Forms | NONE | DP3,HO3,HO4,HO6,PUP | NONE | 593657 |  | #593657 | FALSE
| Story - Delta | 618706 | PAS10 | Yes | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | H-INT-INS-CL 23846:Order Insurance Score Report v4 | 23846 | H-INT-INS-CL | H-INT-INS | 4 | 0 |  | TRUE | 60000 | IE_PHX-2_Reviews_Current | A, Andrews (gwya) | Program |  | PAS10 | CL | CL |  |  |  | WI0344 CR04, U301; AW36 | WI0344 CR04 | TRUE | 2016-05-25 07:09 | 2016-05-25 18:15 |  | Create New Policy | Integration - General | NONE | DP3,HO3,HO4,HO6 | NONE | 596882; 596883 |  | #602741 #596882 #596883 | FALSE
Varun | Story - Common Library | 618707 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 3 | NONE | NONE | H-INT-INSCRR-SCL 26807: Insurance Score – FR Score Comparison - Renewal | 26807 | H-INT-INSCRR-SCL | H-INT-INSCRR | 1 | 0 |  | TRUE | 60000 | IE_PHX-2_Reviews_Current | Prabhu, Venkatesh M (gm0xpra) | Program |  | PAS10 | SCL | SCL |  |  |  | WI0344 CR04, WH45; AW36 | WI0344 CR04 | TRUE | 2016-05-09 07:53 | 2016-05-12 18:11 |  | General | Integration - General | NONE | DP3,HO3,HO4,HO6 | NONE | 602738; 596883 |  | #602738 #542136 #596883 | FALSE
| Story - Delta | 613285 | PAS10 | Yes | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | H-EN-VIEW-WV 22283: View Endorsement v3 | 22283 | H-EN-VIEW-WV | H-EN-VIEW | 3 | 0 |  | TRUE | 60000 | IE_PHX-1_Reviews_Current | Prabhu, Venkatesh M (gm0xpra) | Program | Unplanned | PAS10 | WV | WV |  |  |  | WI0344 CR04, J161 | WI0344 CR04 | TRUE | 2016-04-12 08:48 | 2016-04-17 18:51 |  | General | Define Endorsement | NONE | DP3,HO3,HO4,HO6 | NONE | 596884 |  | #596884 #542301 | FALSE
Varun | Story - Common Library | 613286 | PAS10 | No | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | NONE | NONE | C-DOC-GENQTE-CL 26543: Generate Quote Document-All Products v5 | 26543 | C-DOC-GENQTE-CL | C-DOC-GENQTE | 5 | 0 |  | TRUE | 60000 | IE_PHX-3_Reviews_Current | R, Lakshmipriya | Program |  | PAS10 | CL | CL |  |  |  | WI0344 CR04, J161 | WI0344 CR04 | TRUE | 2016-05-03 07:26 | 2016-05-11 17:55 |  | General | Forms | NONE | DP3,HO3,HO4,HO6,PUP | NONE | 596884 |  | #596884 | TRUE
| Story - Delta | 613282 | PAS10 | Yes | WI0344 Left-over Auto or Property CRs | Property |  |  |  | In IT Team Review |  | Ready for IT Team Review | 2 | 3 | NONE | H-EN-VIEW-CO 22741: View Endorsement v3 | 22741 | H-EN-VIEW-CO | H-EN-VIEW | 3 | 0 |  | TRUE | 60000 | IE_PHX-1_Reviews_Current | Prabhu, Venkatesh M (gm0xpra) | Program | Unplanned | PAS10 | CO | CO |  |  |  | WI0344 CR04, J161 | WI0344 CR04 | TRUE | 2016-04-12 08:48 | 2016-04-17 18:51 |  | General | Define Endorsement | NONE | DP3,HO3,HO4,HO6 | NONE | 596884 |  | #596884 #542301 | FALSE