## Pivot
Row Labels | Count of Id | Action required
Conversion | 11 | Should be closed with analysis and review
Generic | 28 | Existing scenarios getting impacted should be reopened and updated, however US will remain open till decision for converted policy scenario is not finalized
Generic and Conversion | 1 | Existing scenarios getting impacted should be reopened and updated, however US will remain open till decision for converted policy scenario is not finalized
Non-CA | 7 | Should be closed with analysis and review
NA | 6 | Integration/HVT etc
Grand Total | 53
Count of Id | Column Labels
Row Labels | Closed | Integration | PASCore Scenarios/No Coverage in factory | Though NON CA it is dependent on some of the US 25835 and CA US 25836 (Open) | Update | WI Analysis | (blank) | Grand Total
Conversion | 10 |  |  |  | 1 |  |  | 11
Generic |  |  | 1 |  |  |  | 27 | 28
Generic and Conversion | [6 empty] | 1 | 1
NA |  | 1 |  |  |  | 1 | 4 | 6
Non-CA | 6 |  |  | 1 |  |  |  | 7
Grand Total | 16 | 1 | 1 | 1 | 1 | 1 | 32 | 53

## Effort Estimates
Alternates | Description | Effort estimate (%) | Approximate count of impacted existing scenarios | Effort Estimates (Hrs) | Additional comments
Alternate 1 | Creating separate scenarios for conversions + Redesigning/optimizing CPs which are impacted by PAS10 Delta/ most imp CP's | 200% | 36 | 54 | Efforts required -for modifying the existing scenario -optimizing the existing scenario before merging in conversion scenario
Alternate 2 | Reusing the existing CP's for converted policies, by only modifying the Delta portions. | 150% | 36 | 40.5 | Efforts required -for modifying the existing scenario - Creating conversion scenario only
Assumption | 100% is the effort required to modify existing scenario
Count of AC per scenario is 1.5
Efforts required to modify 1 AC is .5 hrs
36*N*100%

## Legends
Category | description
Conversion | US specific to converted policies
Generic | US does not specify behaviour for converted policies
Generic and Conversion | US has combination of AC's which are generic and conversion specifc
Non-CA | delta state is other than CA

## WI0162 CA HDES Conversion
Target Release | Id | Work Item | Story ID | Status | Story Points | Preliminary Story Points | Summary | Scope | Oversight | Resolution | Forms | Project | Group Ownership | TP Status | CR Number | BSS Number | QC ID String | Business Impact | Priority | Related To | Delta State | Planned For | Unified Business Priority | Unified Business Backlog | Bug Type | Priority Group | Epic - Activity | Feature Area | Lockdown | Tags | Delivery Risk | Delivery Risk Comment | RRC ID | Ready IT Team Review Date | IT Team Review Start Date | Story Approved Date | Added To Scope | Final Scope | Original Scope | Removed from Scope | Final Scope Date | Target Sprint | Responsible For | Resolves | Category (Conversion Only/Generic) | Patterns Impacted | Count of Patterns Impacted | Additional Comments | Analysis_16_Aug
PAS10 | 586844 | WI0162 CA HDES Conversion | H-REN-AUTOINF-CA | Test Execution Complete | 2.5 | 2 | H-REN-AUTOINF-CA 25379:Apply Inflation Guard factors HO3 DP3 v2 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | F0128 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_DNK | 10000 | TRUE |  | Group 01 | Renewal | Renew Policy | TRUE |  | NONE |  | 25379 | 2016-03-10 08:13 | 2016-03-10 19:17 | 2016-05-25 10:32 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Raghunandhan, Muthuramalingam (gn02rag) | #542599 #593043 | Generic and Conversion | CA-CP-109 CA-CP-108 CA-CP-117 C-H-Renewal-CA-1618 C-H-Renewal-CA-1617 | 1
PAS10 | 586620 | WI0162 CA HDES Conversion | C-DOC-AH67XX-CA | Test Execution Complete | 4 | 3 | C-DOC-AH67XX-CA 26252:Generate Lapse Notice-Eligible for Reinstatement |  | S19 Kickoff |  | TRUE | Property | Program | In IT Team Review | CR MO031 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 02 | Forms | Forms | TRUE |  | NONE |  | 26252 | 2016-03-28 22:39 | 2016-03-29 18:22 | 2016-05-18 15:44 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Khivasara, Himanshu (gk9ikhi) | #541658 #593043 | Generic | CA-CP-101 CA-CP-103 | 2
PAS10 | 587153 | WI0162 CA HDES Conversion | H-UWA-ACSMGT-CL | In Testing | 4 | 2 | H-UWA-ACSMGT-CL-26508-UW Rules Authority Level - New Business & Endorsements |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WH46 | 593043 |  | 3 - High | NONE | CL | CL | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 04 | Access Management - UW Rules Override | General | TRUE |  | NONE |  | 26508 | 2016-03-28 22:39 | 2016-03-29 18:22 | 2016-06-06 00:37 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Ganesan, Mahendar (ghe6mah) | #593043 | Non-CA |  |  | Closed
PAS10 | 586898 | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 1.5 | 3 | H-CONV-SUP-CA :26331 : Generate Renewal Offer Cover Letter Mortgagee Bill form 61 5155 - RETIRED |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review |  | 593043 |  | 3 - High | NONE | NONE | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 01 | NONE | NONE | TRUE |  | NONE |  | 26331 | 2016-03-24 07:19 | 2016-03-24 19:31 | 2016-05-18 00:46 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 #541869 | Conversion |  |  | Closed
PAS10 | 589302 | WI0162 CA HDES Conversion | H-BND-ELGSCH-CCL | QA Approved | 1 | 2 | H-BND-ELGSCH-CCL 22531:Determine Eligibility Secondary/Seasonal home v3 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WH46 | 593043 |  | 3 - High | NONE | CCL | CCL | IE_Sprint_19_PHX-2 | 10000 | TRUE |  | Group 01 | Determine Eligibility | General | TRUE |  | NONE |  | 22531 | 2016-03-07 12:55 | 2016-03-07 18:43 | 2016-05-06 05:54 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalakrishnan, Venkat K | #542288 #593043 | Generic | C-HO-HO3-CCL-678 | 1
PAS10 | 587148 | WI0162 CA HDES Conversion | H-UWA-ACSMGT-CA | Test Execution Complete | 4 | 2 | H-UWA-ACSMGT-CA-26507-UW Rules Authority Level - New Business |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WH46 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 03 | Access Management - UW Rules Override | General | TRUE |  | NONE |  | 26507 | 2016-03-30 07:20 | 2016-03-30 18:50 | 2016-06-06 00:37 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Ganesan, Mahendar (ghe6mah) | #593043 | Generic | C-HO-HO3-CA-236 | 1
PAS10 | 587117 | WI0162 CA HDES Conversion | H-INT-AAAMEM-CA | Test Execution Complete | 2 | 2 | H-INT-AAAMEM-CA-25723-Capture AAA Membership |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 01 | Integration - General | General | TRUE |  | NONE |  | 25723 | 2016-03-25 12:25 | 2016-03-27 17:32 | 2016-06-12 22:17 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Ganesan, Mahendar (ghe6mah) | #593043 | NA | Integration
PAS10 | 586893 | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 3 | 3 | H-CONV-SUP-CA :26293: Generate Expiration Notice form 61 6533_RETIRED |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | CRMO048 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 02 | NONE | NONE | TRUE |  | NONE |  | 26293 | 2016-03-28 07:31 | 2016-03-28 17:53 | 2016-05-11 10:34 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 #541869 | Conversion |  |  | Closed
PAS10 | 586622 | WI0162 CA HDES Conversion | C-DOC-AH64XX-CA | Blocked | 4 | 3 | C-DOC-AH64XX-CA 26203:Generate AH64XX Expiration Notice |  | S19 Kickoff | Blocked from QA | TRUE | Property | Program | Ready for IT Team Review | MO030 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 03 | Forms | Forms | TRUE |  | NONE |  | 26203 | 2016-03-23 07:33 | 2016-03-23 19:05 | 2016-05-27 02:08 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Raghunandhan, Muthuramalingam (gn02rag) | #541662 #593043 | Generic | No Coverage
PAS10 | 589306 | WI0162 CA HDES Conversion | H-BND-LIADED-CA | QA Approved | 1 | 2 | H-BND-LIADED-CA 24586:Validate Liability Limit and Deductible for Multiple Primary v2 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WH46 | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 01 | Determine Coverage | General | TRUE |  | NONE |  | 24586 | 2016-03-09 21:56 | 2016-03-10 19:18 | 2016-06-14 17:23 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Balasubramaniyam, Saranya (gekxbal) | #542253 #593043 | Generic | C-HO-HO3-CA-114 | 1
PAS10 | 408227 | WI0162 CA HDES Conversion | H-DOC-RENREM-CA | QA Approved | 2 | 2 | H-DOC-RENREM-CA 25176:Renewal WURRCA Insurance Renewal Reminder v2 |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | WI0208 CR04 | 593043, 566291 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 02 | Forms | Forms | TRUE |  | NONE |  | 25176 | 2016-02-19 12:39 | 2016-02-21 17:57 | 2016-06-19 17:13 | Unplanned | PAS10 | PAS10 | Unplanned | 2016-06-27 12:00 | Sprint 19 | Balasubramaniyam, Saranya (gekxbal) | #542016 #593043 | Generic | CA-CP-107 | 1
PAS10 | 586906 | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 4 | 3 | H-CONV-SUP-CA: 26327 :Generate Renewal Reminder (Mortgagee) form 61 0071_RETIRED |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review |  | 593043 |  | 3 - High | NONE | NONE | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 01 | NONE | NONE | TRUE |  | NONE |  | 26327 | 2016-03-23 07:33 | 2016-03-23 19:06 | 2016-06-07 23:57 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 #541869 | Conversion |  |  | Closed
PAS10 | 587156 | WI0162 CA HDES Conversion | H-BND-ELGMBR-UT | QA Approved | 3 | 2 | H-BND-ELGMBR-UT 25837 : Determine Eligibility - Membership v03 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 | 593043 |  | 3 - High | NONE | UT | UT | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 01 | Capture Membership Info | NONE | TRUE |  | NONE |  | 25837 | 2016-03-29 07:10 | 2016-03-29 18:23 | 2016-05-25 00:34 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalakrishnan, Venkat K | #593043 | Non-CA |  |  | Closed
PAS10 | 586623 | WI0162 CA HDES Conversion | C-DOC-WU64CA-CA | Test Execution Complete | 2 | 2 | C-DOC-WU64CA-CA 25734:Generate WU64CA Expiration Notice V03 |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | CR MO030 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 02 | Forms | Forms | TRUE |  | NONE |  | 25734 | 2016-03-15 07:59 | 2016-03-15 13:38 | 2016-05-23 10:00 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Khivasara, Himanshu (gk9ikhi) | #541662 #593043 | Generic | CA-CP-102 C-HO-HO3-CA-200 | 2
PAS10 | 589297 | WI0162 CA HDES Conversion | H-BND-VALMULTIPRIM-CCL | Test Execution Complete | 1 | 2 | H-BND-VALMULTIPRIM-CCL: 24729 Bind Policy - Validate Multiple Primary Dwelling v2 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WH46 | 593043 |  | 3 - High | NONE | CCL | CCL | Exigen_Sprint_19_DNK | 10000 | TRUE |  | Group 02 | Determine Eligibility | General | TRUE |  | NONE |  | 24729 | 2016-02-29 08:14 | 2016-02-29 18:14 | 2016-05-31 09:22 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalakrishnan, Venkat K | #542516 #593043 | Generic | No Coverage
PAS10 | 591571 | WI0162 CA HDES Conversion | P-BND-ELGNAEUW-CA | In Testing | 6 | 2 | P-BND-ELGNAEUW-26028 CA PUP Underwriting rules with neither Automatic Exception model nor UW Approval v03 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 ; UW42 | 593043 ; 596879 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 04 | PUP - New Business | General | TRUE |  | NONE |  | 26028 | 2016-03-29 07:10 | 2016-03-29 18:23 | 2016-06-24 00:29 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #542805 #593043 | Generic | PC72-A-C-PUP-CA-3484 PC81-A-C-PUP-CA-3525 | 2 | PASCore Scenarios/No Coverage in factory
PAS10 | 587114 | WI0162 CA HDES Conversion | H-TSK-TASK-CL | QA Approved | 7 | 2 | H-TSK-TASK-CL-25746-Task Management - New Business & Endorsements |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 & WH46 | 593043 |  | 3 - High | NONE | CL | CL | Exigen_Sprint_19_RIX | 10000 | TRUE |  | Group 04 | Task Management - New Business | General | TRUE |  | NONE |  | 25746 | 2016-03-30 07:20 | 2016-03-30 18:50 | 2016-06-15 09:38 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Ganesan, Mahendar (ghe6mah) | #593043 | Non-CA |  |  | Though NON CA it is dependent on some of the US 25835 and CA US 25836 (Open)
PAS10 | 557691 | WI0162 CA HDES Conversion | H-PRI-PROPVAL-CA | QA Approved | 2 | 2 | H-PRI-PROPVAL-CA 25814: Capture Property Value v3 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | CR F0128 | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-2 | 10000 | TRUE |  | Group 02 | Capture Property Info | Create New Policy | TRUE |  | NONE |  | 25814 | 2016-03-01 08:15 | 2016-03-01 18:08 | 2016-06-13 05:16 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopinath, Babu (gn03gop) | #542497 #593043 | Generic | No Coverage
PAS10 | 586897 | WI0162 CA HDES Conversion | C-DOC-PRERENCNV-CA | In Testing | 2.5 | 2 | C-DOC-PRERENCNV-CA Generate Pre-renewal form 61 5151 V02 |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | WI0208 CR04 | 593043, 566291 |  | 3 - High | NONE | NONE | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 03 | NONE | NONE | TRUE |  | NONE |  | 26407 | 2016-03-31 07:30 | 2016-03-31 18:03 | 2016-06-30 12:10 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 | Conversion |  |  | Closed
PAS10 | 586905 | WI0162 CA HDES Conversion | C-DOC-RENREM-CA | Test Execution Complete | 3 | 2 | C-DOC-WUNECACNV-CA 26530:Renewal WUNECA Insurance Renewal Reminder (non-Escrow Payment) V02 |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | WI0208 CR04 | 566291 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 03 | Forms | Forms | TRUE |  | NONE |  | 26530 | 2016-03-31 07:30 | 2016-03-31 18:04 | 2016-06-07 00:02 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 | Generic | CA-CP-102 | 1 |  | Analysis Complete
PAS10 | 589304 | WI0162 CA HDES Conversion | H-BND-LIADED-CL | QA Approved | 1 | 2 | H-BND-LIADED-CL-22851-Validate Liability Limit and Deductible for Multiple Primary v3 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WH46 | 593043 |  | 3 - High | NONE | CL | CL | Exigen_Sprint_19_DNK | 10000 | TRUE |  | Group 02 | Determine Coverage | General | TRUE |  | NONE |  | 22851 | 2016-03-09 07:34 | 2016-03-09 19:20 | 2016-05-31 07:24 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalakrishnan, Venkat K | #542253 #593043 | Non-CA | T-HO-HO3-CL-680 | 1 | Closed
PAS10 | 586882 | WI0162 CA HDES Conversion | H-DOC-615154CNV-CA | Ready To Test | 1.5 | 3 | H-DOC-615154CNV-CA 26445:Generate Renewal Offer Cover Letter Mortgagee Bill form 61 5154 |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | WI0208 CR04 | 566291 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-2 | 10000 | TRUE |  | Group 04 | Forms | Forms | TRUE |  | NONE |  | 26445 | 2016-03-28 07:31 | 2016-03-28 17:54 | 2016-06-19 17:13 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Jeraldin, Kavitha (gntjera) | #593043 | Conversion | No Coverage |  | Update
PAS10 | 589294 | WI0162 CA HDES Conversion | H-PCQ-PRIMDWELL-CCL | Test Execution Complete | 2 | 2 | H-PCQ-PRIMDWELL-CCL 24401:Calculate Premium - Check Primary Dwelling v2 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WH46 | 593043 |  | 3 - High | NONE | CCL | CCL | Exigen_Sprint_19_DNK | 10000 | TRUE |  | Group 02 | Capture Property Info | General | TRUE |  | NONE |  | 24401 | 2016-03-11 08:32 | 2016-03-13 18:13 | 2016-05-26 08:08 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalakrishnan, Venkat K | #542504 #593043 | Generic | C-HO-HO6-CA-134 | 1
PAS10 | 587150 | WI0162 CA HDES Conversion | H-TSK-TASK-CA | In Testing | 11 | 2 | H-TSK-TASK-CA-25736-Task Management - New Business & Endorsements |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 & WH46 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_RIX | 10000 | TRUE |  | Group 04 | Task Management - New Business | General | TRUE |  | NONE |  | 25736 | 2016-03-30 07:20 | 2016-03-30 18:50 | 2016-06-13 10:20 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Ganesan, Mahendar (ghe6mah) | #593043 | Generic
PAS10 | 586625 | WI0162 CA HDES Conversion | C-DOC-AHCWXX-CCL | Test Execution Complete | 4 | 3.5 | C-DOC-AHCWXX-CCL 26248: Generate AHCWXX Cancel Withdraw Notice Document |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | MO023 | 593043 |  | 3 - High | NONE | CCL | CCL | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 02 | Forms | Forms | TRUE |  | NONE |  | 26248 | 2016-03-23 07:33 | 2016-03-23 19:09 | 2016-05-20 01:18 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | TDV, Satish (gwftdv) | #541659 #593043 | Generic | CA-CP-106 CA-CP-105 CA-CP-101 CA-CP-100 | 4
PAS10 | 587159 | WI0162 CA HDES Conversion | H-BND-ELGDEST-CL | QA Approved | 2 | 2 | H-BND-ELGDEST-CL 25835:Determine Eligibility - Detached Structure v5 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 | 593043 |  | 3 - High | NONE | CL | CL | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 01 | Determine Eligibility | NONE | TRUE |  | NONE |  | 25835 | 2016-03-03 00:18 | 2016-03-03 18:09 | 2016-06-24 05:31 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 #542268 | Non-CA | RBT |  | Closed
PAS10 | 586891 | WI0162 CA HDES Conversion | C-DOC-AHRBXX-CA | In Testing | 6 | 3 | C-DOC-AHRBXX-CA Generate AHRBXX Renewal Bill |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review |  | 593043 |  | 3 - High | NONE | NONE | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 04 | NONE | NONE | TRUE |  | NONE |  | 26446 | 2016-03-31 07:30 | 2016-03-31 18:04 | 2016-06-27 19:41 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 | Generic | CA-CP-105,CA-CP-106,CA-CP-102 | 3
PAS10 | 557373 | WI0162 CA HDES Conversion | H-PCQ-COVHO4-CA | Test Execution Complete | 1.5 | 2 | H-PCQ-COVHO4-CA 24672: Determine Coverage HO-4 v4 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | CR F0128 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_DNK | 10000 | TRUE |  | Group 03 | Determine Coverage | General | TRUE |  | NONE |  | 24672 | 2016-01-19 08:38 | 2016-01-19 21:33 | 2016-06-22 05:05 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Raghunandhan, Muthuramalingam (gn02rag) | #542251 #593043 | Generic | C-HO-HO4-CA-098 | 1
PAS10 | 500517 | WI0162 CA HDES Conversion | H-BND-ELGAE6-CA | Test Execution Complete | 2.5 | 2 | H-BND-ELGAE6-CA: 25090:Determine Eligibility Automated Exception 6 v2 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | CR UW41 | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 01 | Determine Eligibility | Create New Policy | TRUE | pas8.1 | NONE |  | 25090 | 2015-08-04 12:49 | 2015-08-04 20:21 | 2016-06-08 05:09 | Unplanned | PAS10 | PAS10 | Unplanned | 2016-06-27 12:00 | Sprint 19 | Vivek, Kunal (gljvive) | #542273 #593043 | Generic | No Coverage/PAS5 pilot
PAS10 | 587161 | WI0162 CA HDES Conversion | H-BND-ELGDEST-CA | Test Execution Complete | 2 | 2 | H-BND-ELGDEST-CA 25834: Determine Eligibility - Detached Structure v2 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 02 | NONE | NONE | TRUE |  | NONE |  | 25834 | 2016-03-31 07:30 | 2016-03-31 18:05 | 2016-06-30 09:03 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 #542268 | Generic | No Coverage
PAS10 | 499278 | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 2 | 3 | H-CONV-SUP-CA: 25430: Generate Property Installment Bill (Auto Pay) form 61 6130 _RETIRED |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review |  | 593043 |  | 3 - High | NONE | NONE | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 03 | NONE | NONE | TRUE | conv | NONE |  | 25430 | 2015-08-03 14:03 | 2015-08-03 20:01 | 2016-06-13 00:58 | Unplanned | PAS10 | PAS10 | Unplanned | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 #541869 | Conversion |  |  | Closed
PAS10 | 499281 | WI0162 CA HDES Conversion | H-DOC-610069CNV-CA | Test Execution Complete | 3 | 2 | H-DOC-610069CNV-CA 25358:Generate Renewal Reminder (Home Banking) form 61 0069 V02 |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | WI0208 CR04 | 566291 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 03 | Forms | Forms | TRUE | conv | NONE |  | 25358 | 2015-08-03 14:03 | 2015-08-03 20:02 | 2016-06-14 23:52 | Unplanned | PAS10 | PAS10 | Unplanned | 2016-06-27 12:00 | Sprint 19 | Balasubramaniyam, Saranya (gekxbal) | #541863 #593043 | Conversion |  |  | Closed
PAS10 | 499274 | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 2 | 3 | H-CONV-SUP-CA: 25434: Generate Property Installment Bill form 61 6129 _RETIRED |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review |  | 593043 |  | 3 - High | NONE | NONE | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 03 | NONE | NONE | TRUE | conv | NONE |  | 25434 | 2015-08-07 12:03 | 2015-08-09 18:49 | 2016-06-03 00:11 | Unplanned | PAS10 | PAS10 | Unplanned | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 #541869 | Conversion |  |  | Closed
PAS10 | 452300 | WI0162 CA HDES Conversion | H-INT-CLAIMS-CA | Cancelled | 4 | 3 | H-INT-CLAIMS-CA 25186:Internal Claims – Batch | WI0191 CR03 | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WI0191 CR03 | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | NONE | Integration - General | Conversion | TRUE | conv | NONE |  | 25186 | 2015-04-30 16:16 | 2015-04-30 16:53 | 2015-06-28 19:15 | Unplanned | PAS10 | PAS10 | Unplanned | 2016-06-27 12:00 | Sprint 19 | Balasubramaniyam, Saranya (gekxbal) | #541871 #593043 | NA | Integration
PAS10 | 586903 | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 2 | 3 | H-CONV-SUP-CA: 26329:Generate Renewal Reminder (Mortgagee) form 61 5156_RETIRED |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review |  | 593043 |  | 3 - High | NONE | NONE | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 01 | NONE | NONE | TRUE |  | NONE |  | 26329 | 2016-03-28 07:31 | 2016-03-28 17:56 | 2016-05-25 23:39 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 #541869 | Conversion |  |  | Closed
PAS10 | 586818 | WI0162 CA HDES Conversion | H-REN-AUTOINF-CA | Test Execution Complete | 3 | 2 | H-REN-AUTOINF-CA 25378: Apply Inflation Guard factors HO6 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | F0128 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_DNK | 10000 | TRUE |  | Group 03 | Renewal | Renew Policy | TRUE |  | NONE |  | 25378 | 2016-03-09 07:34 | 2016-03-09 19:21 | 2016-05-26 08:08 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopinath, Babu (gn03gop) | #542598 #593043 | Generic | CA-CP-108, CA-CP-109 CA-CP-112, CA-CP-109 | 4
PAS10 | 589298 | WI0162 CA HDES Conversion | H-PRI-PRIMPERC-CCL | QA Approved | 3.5 | 2 | H-PRI-PRIMPERC-CCL 24400:Capture percentage usage for multiple Primary HO policy v2 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WH46 | 593043 |  | 3 - High | NONE | CCL | CCL | IE_Sprint_19_PHX-2 | 10000 | TRUE |  | Group 01 | Capture Applicant Info | General | TRUE |  | NONE |  | 24400 | 2016-03-01 08:15 | 2016-03-01 18:06 | 2016-06-08 05:09 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalakrishnan, Venkat K | #542504 #593043 #589297 | Generic | No Coverage
PAS10 | 591572 | WI0162 CA HDES Conversion | P-BND-ELGNAEUW-UT | QA Approved | 1 | 2 | P-BND-ELGNAEUW-26010 UT-Underwriting rules with neither Automatic Exception model nor UW Approval v03 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 | 593043 |  | 3 - High | NONE | UT | UT | Exigen_Sprint_19_DNK | 10000 | TRUE |  | Group 02 | NONE | NONE | TRUE |  | NONE |  | 26010 | 2016-03-31 07:30 | 2016-03-31 18:05 | 2016-06-09 08:09 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #542805 #593043 | Non-CA |  |  | Closed
PAS10 | 589311 | WI0162 CA HDES Conversion | C-DOC-AHTPC-CA | Test Execution Complete | 3 | 2 | C-DOC-AHTPC-CA 26300: Generate Third Party Designee Cover Page v3 |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | CRMO031/30 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 04 | Forms | Forms | TRUE |  | NONE |  | 26300 | 2016-03-23 07:33 | 2016-03-23 19:09 | 2016-05-24 00:59 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Khivasara, Himanshu (gk9ikhi) | #541694 #593043 | Generic | CA-CP-122 | 1
PAS10 | 557388 | WI0162 CA HDES Conversion | H-PCQ-COVHO6-CA | Test Execution Complete | 2 | 2 | H-PCQ-COVHO6-CA 24705: Determine Coverage HO-6 v3 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | CR F0128 | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 01 | Determine Coverage | General | TRUE |  | NONE |  | 24705 | 2016-01-19 08:38 | 2016-01-19 21:41 | 2016-06-14 17:23 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Raghunandhan, Muthuramalingam (gn02rag) | #593043 | Generic | No Coverage
PAS10 | 586895 | WI0162 CA HDES Conversion | H-DOC-RENREM-CA | In Testing | 3 | 3 | H-DOC-RENREM-CA-Generate Renewal Offer Cover Letter (HO) form 61 5152 |  | S19 Kickoff |  | FALSE | Property | Program | In IT Team Review |  | 593043 |  | 3 - High | NONE | NONE | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 04 | NONE | NONE | TRUE |  | NONE |  | 26413 | 2016-03-28 07:31 | 2016-03-29 18:24 | 2016-05-25 23:41 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 | Conversion
PAS10 | 587157 | WI0162 CA HDES Conversion | H-INT-MEM-UT | QA Approved | 2 | 2 | H-INT-MEM-UT- 25838: AAA Membership V02 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 | 593043 |  | 3 - High | NONE | UT | UT | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 01 | Capture Membership Info | NONE | TRUE |  | NONE |  | 25838 | 2016-03-15 07:59 | 2016-03-15 13:39 | 2016-05-27 11:03 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #542142 #593043 | Non-CA |  |  | Closed
PAS10 | 589328 | WI0162 CA HDES Conversion | C-DOC-PRTODR-CA | In Testing | 2 | 2 | 26783: C-DOC-PRTODR-CA Generate Story for NB Amend Ren and Rev Ren Forms in correct order of packet |  | S19 Kickoff |  | TRUE | Property | Program | In IT Team Review |  | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 04 | Forms | Forms | TRUE |  | High | This US is dependent on 586626 (team 3), which is in turn dependent on 464784(team 2). This team 2 story will only be delivered by Monday. | 26783 | 2016-03-28 07:31 | 2016-03-28 17:57 | 2016-06-21 05:28 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Khivasara, Himanshu (gk9ikhi) | #593043 | NA | HVT
PAS10 | 586624 | WI0162 CA HDES Conversion | C-DOC-WUCWCA-CA | Test Execution Complete | 3 | 2 | C-DOC-WUCWCA-CA 26148:Generate WUCWCA Withdrawn Notice Document v2 |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | MO023 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 03 | Forms | Forms | TRUE |  | NONE |  | 26148 | 2016-03-16 08:29 | 2016-03-16 18:30 | 2016-06-07 23:56 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Khivasara, Himanshu (gk9ikhi) | #541659 #593043 | Generic | CA-CP-100 CA-CP-101 CA-CP-105 CA-CP-106 CA-CP-110 CA-CP-120 | 6 |  | Analysis Complete
PAS10 | 586890 | WI0162 CA HDES Conversion | C-INT-MOVPOLCNV-CA | In Testing | 3 | 3 | C-INT-MOVPOLCNV-CA 27167: Move Policy from one customer to another |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WI0162; WI0208 CR04; | 593043; 566291; 596890 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 03 | Integration - General | NONE | TRUE |  | NONE |  | 27167 | 2016-03-23 16:11 | 2016-03-23 19:10 | 2016-06-29 15:16 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Prabhu, Venkatesh M (gm0xpra) | #593043 #566291 #596890 | Conversion | No Coverage |  | Closed
PAS10 | 586887 | WI0162 CA HDES Conversion | H-CONV-HMEBNK-CA | Test Execution Complete | 3 | 3 | 26489:H-CONV-HMEBNK-CA - Home Banking feed |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review |  | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 01 | Integration - Renewal | NONE | TRUE |  | NONE |  | 26489 | 2016-03-15 16:56 | 2016-03-15 18:39 | 2016-07-01 00:01 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalakrishnan, Venkat K | #593043 | NA | Integration |  | WI Analysis
PAS10 | 586626 | WI0162 CA HDES Conversion | C-DOC-BFC-CA | In Testing | 3 | 2 | C-DOC-BFC-CA 26204: BFC Requirements and Print Order v3 |  | S19 Kickoff |  | TRUE | Property | Program | In IT Team Review | CR MO023/030/031 | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | Group 04 | Forms | Other - Document Management | TRUE |  | High | 464784 is still in progress and per team 2, this will be delivered only by Monday (07/25). | 26204 | 2016-03-31 07:30 | 2016-03-31 18:05 | 2016-07-06 10:45 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopinath, Babu (gn03gop) | #541667 #593043 | NA | HVT
PAS10 | 586588 | WI0162 CA HDES Conversion | C-DOC-WU67CA-CA | Test Execution Complete | 3 | 2 | C-DOC-WU67CA-CA 25418:Generate Lapse Notice-Eligible for Reinstatement v3 |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review | CR MO031 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 01 | Forms | Forms | TRUE |  | NONE |  | 25418 | 2016-03-16 08:29 | 2016-03-16 18:31 | 2016-05-26 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Khivasara, Himanshu (gk9ikhi) | #541922 #593043 | Generic | CA-CP-122 | 1
PAS10 | 452307 | WI0162 CA HDES Conversion | P-INT-CLAIMS-CA | Cancelled | 6 | 3 | P-INT-CLAIMS-CA 25516: US CONV PUP Internal Claims – Batch | WI0191 CR03 | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | WI0191 CR03 | 593043 |  | 3 - High | NONE | CA | CA | IE_Sprint_19_PHX-3 | 10000 | TRUE |  | NONE | Integration - General | Conversion | TRUE | conv | NONE |  | 25516 |  | 2015-04-12 16:48 | 2015-06-28 19:15 | Unplanned | PAS10 | PAS10 | Unplanned | 2016-06-27 12:00 | Sprint 19 | Gopinath, Babu (gn03gop) | #542704 #593043 | NA | Integration |  | Integration
PAS10 | 586845 | WI0162 CA HDES Conversion | H-REN-AUTOINF-CA | Test Execution Complete | 2 | 2 | H-REN-AUTOINF-CA 25380:Apply Inflation Guard CPI HO4 v2 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | F0128 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_DNK | 10000 | TRUE |  | Group 02 | Renewal | Renew Policy | TRUE |  | NONE |  | 25380 | 2016-03-07 12:55 | 2016-03-07 18:46 | 2016-06-01 10:01 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Raghunandhan, Muthuramalingam (gn02rag) | #542603 #593043 | Generic | CA-CP-109 CA-CP-117 C-H-Renewal-CA-1422 | 3
PAS10 | 587158 | WI0162 CA HDES Conversion | H-BND-ELGLOGH-CCL | Test Execution Complete | 4 | 2 | H-BND-ELGLOGH-CCL 25836 : Determine Eligibility - Log Home v05 |  | S19 Kickoff |  | FALSE | Property | Program | Ready for IT Team Review | UW46 | 593043 |  | 3 - High | NONE | CCL | CCL | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 03 | Determine Eligibility | General | TRUE |  | NONE |  | 25836 | 2016-03-28 07:31 | 2016-03-28 17:58 | 2016-06-16 00:02 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopalan, Srividya (gyagopa) | #593043 #542282 | Generic | T-HO-HO3-CCL-677 | 1
PAS10 | 490382 | WI0162 CA HDES Conversion | H-CONV-SUP-CA | Test Execution Complete | 4 | 2 | H-CONV-SUP-CA 25179:Suppress form Generation for conversion policies |  | S19 Kickoff |  | TRUE | Property | Program | Ready for IT Team Review |  | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_SZV | 10000 | TRUE |  | Group 04 | Forms | Forms | TRUE |  | NONE |  | 25179 | 2015-08-03 14:03 | 2015-08-03 20:02 | 2016-05-27 00:22 | Unplanned | PAS10 | PAS10 | Unplanned | 2016-06-27 12:00 | Sprint 19 | Balasubramaniyam, Saranya (gekxbal) | #541869 #593043 | Conversion |  |  | Closed
PAS10 | 557724 | WI0162 CA HDES Conversion | H-PRI-CAPPV-CA | Test Execution Complete | 1.5 | 2 | H-PRI-CAPPV-CA 25377: Capture Property Value - HO4 v2 |  | S19 Kickoff |  | FALSE | Property | Program | In IT Team Review | CR F0128 | 593043 |  | 3 - High | NONE | CA | CA | Exigen_Sprint_19_DNK | 10000 | TRUE |  | Group 02 | Capture Property Info | General | TRUE |  | NONE |  | 25377 | 2016-03-01 08:15 | 2016-03-01 18:09 | 2016-05-31 09:22 |  | PAS10 | PAS10 |  | 2016-06-27 12:00 | Sprint 19 | Gopinath, Babu (gn03gop) | #542519 #593043 | Generic | No Coverage |  |  | Analysis Complete